## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 7100
Job Title: | Project Management and Integration
Job Manager: | Ron Strykowsky
Description:
Management and engineering oversight of the NSTX Upgrade Project. This project includes the addition of a second neutral beam on NSTX and the design, fabrication and installation of a new centerstack as well as upgrades to coil structures to support the new loads. Also included is the updating of the General Arrangement Drawings for the NSTX Test Cell and funds for independent reviewers.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1170
| Job Number: |  |  | 7100
| Job Title: |  |  | Project Management and Integration
| Job Manager: |  |  | Ron Strykowsky
Estimate (user input)
[5 empty] | SCHEDULE | [5 empty] | FY09$K |  |  |  |  | HOURS
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated |  |  | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | DURATION in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category
numb | P3 cross ref (optinal) | [9 empty] | 1.22 | 1.22 | 1.63 | 1.1 | 1.63 | 185.5 | 125.09 | 143.5 | 144.4 | 175.93 | 151.07 | 165.37 | 145.35 | 150.77 | 142.83 | 180.23 | 150 | 150 | 150
| was |  | Project Manager - Strykowsky
| 0% |  | FY10 50% | [20 empty] | 863 | [5 empty] | strykowsky | 2,8
| 0% |  | FY11 50% | [20 empty] | 863 | [5 empty] | strykowsky | 2,8
| 0% |  | FY12 50% | [20 empty] | 863 | [5 empty] | strykowsky | 2,8
| 0% |  | FY13 50% | [20 empty] | 863 | [5 empty] | strykowsky | 2,8
Deputy Project Manager - Perry
| 70% |  | FY10 50% | [18 empty] | 863 | [7 empty] | perry | 2,8
| 70% |  | FY11 50% | [18 empty] | 863 | [7 empty] | perry | 2,8
| 100% |  | FY12 100% | [18 empty] | 1726 | [7 empty] | perry | 2,8
| 100% |  | FY13 100% | [18 empty] | 1726 | [7 empty] | perry | 2,8
Project Controls Manager - Strykowsky
| 50% |  | FY10 50% | [20 empty] | 863 | [5 empty] | strykowsky | 2,8
| 50% |  | FY11 50% | [20 empty] | 863 | [5 empty] | strykowsky | 2,8
| 50% |  | FY12 50% | [20 empty] | 863 | [5 empty] | strykowsky | 2,8
| 50% |  | FY13 50% | [20 empty] | 863 | [5 empty] | strykowsky | 2,8
Planner/Scheduler - Guzman
| 50% |  | FY10 50% | [20 empty] | 863 | [5 empty] | guzman | 2,8
| 50% |  | FY11 50% | [20 empty] | 863 | [5 empty] | guzman | 2,8
| 50% |  | FY12 50% | [20 empty] | 863 | [5 empty] | guzman | 2,8
| 50% |  | FY13 50% | [20 empty] | 863 | [5 empty] | guzman | 2,8
Systems Engineering Support - Simmons
| 20% |  | FY10 20% | [12 empty] | 345.2 | [13 empty] | simmons | 8
| 20% |  | FY11 20% | [12 empty] | 345.2 | [13 empty] | simmons | 8
| 20% |  | FY12 20% | [12 empty] | 345.2 | [13 empty] | simmons | 8
| 20% |  | FY13 20% | [12 empty] | 345.2 | [13 empty] | simmons | 8
Work Control Center
FY10 0%
|  |  | FY11 25% each of Winston and Langella (EMSM) | [17 empty] | 863 | [8 empty] | winston | 4
|  |  | FY12 50% each of Winston and Langella (EMSM) | [17 empty] | 1726 | [8 empty] | winston | 4
|  |  | FY13 50% each of Winston and Langella (EMSM) | [17 empty] | 1726 | [8 empty] | winston | 4
50% Mitchel for updating of General Arrangement drawings
|  |  | FY10 | [13 empty] | 863 | [12 empty] | mitchel | 2
|  |  | FY11 | [13 empty] | 863 | [12 empty] | mitchel | 2
|  |  | FY12 | [13 empty] | 863 | [12 empty] | mitchel | 2
|  |  | FY13 | [13 empty] | 863 | [12 empty] | mitchel | 2
two independent reviewers 80mh every 6 months plus $3K every six months for airfare, hotel and meals
|  |  | FY10 | [10 empty] | 6 |  | 160 | [14 empty] | 8
|  |  | FY11 | [10 empty] | 6 |  | 160 | [14 empty] | 8
|  |  | FY12 | [10 empty] | 6 |  | 160 | [14 empty] | 8
|  |  | FY13 | [10 empty] | 6 |  | 160 | [14 empty] | 8
|  |  | Independent reviewers 480 mh to support ORA during last two months of project | [10 empty] | 20 | [7 empty] | 480 | [8 empty] | 8
Misc purchases (ie computers, supplies)
| 0 |  | FY10 | [7 empty] | 5 | [19 empty] | 8
| 0 |  | FY11 | [7 empty] | 5 | [19 empty] | 8
| 0 |  | FY12 | [7 empty] | 5 | [19 empty] | 8
| 0 |  | FY13 | [7 empty] | 5 | [19 empty] | 8
|  | TOTALS | [8 empty] | 20 | 0 | 0 | 44 | 0 | 2020.8 | 3452 | 0 | 0 | 0 | 4315 | 5658 | 0 | 10356 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 4028.3737 | [5 empty] | 24.4 | 0 | 0 | 48.4 | 0 | 374.8584 | 431.8107 | 0 | 0 | 0 | 651.867 | 935.6635 | 0 | 1561.3741 | 0 | 0 | 0 | 0 | 0
| Notes: | [18 empty] | CATEGORIZATION CODES:
[9 empty] | Weeks | [10 empty] | 1 - National Standards
[9 empty] | 3 | [10 empty] | 2 - Engineering Judgement/Experience
[9 empty] | 5 | [10 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
[9 empty] | 8 | [10 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
[9 empty] | 9 | [10 empty] | 5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 7100
Job Title: |  | Project Management and Integration
Job Manager: |  | Ron Strykowsky
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks) | Retirement Date
1 | EVMS Implementation requires more projects controls support for training etc, than expected |  |  |  | U | Assignment of experienced engrs as CAM's. Minimize the number of CAM'sNew PM office to augment project staff |  |  | 1/2 fte for one year | 150 | 150 | none | none | CD-3
2 | PPPL Overhead rates |  |  |  | L | continue to ensure outyear rates are conservative |  |  | Rates are typically conservative when set but fluctuate as a function of the total lab fundinmg. Pressure from the indirect department may result in increased staff thus higher rates. -1% to +1% | - $682k | + $682k | none | none | sliding scale through project completion
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1170
Job Number: | 7100
Job Title: | Project Management and Integration
Job Manager: | Ron Strykowsky
Materials and Subcontracts (M&S)
Description:
see Tab B for reviewer funds required
n/a