## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 7700
Job Title: | NSTX Upgrade HP Allocations
Job Manager: | Ron Strykowsky
Description:
Health Physics allocated costs are collected in a cost account managed by the PPPL Health Physics Manager. These costs include labor and materials to support the collection of radiological analyses of various environmental samples and bioassay samples, and the collection of analyses of data on the gamma radiation spectra of radioactive material at PPPL. The cost of this activity is "allocated" to the various DOE funded direct programs based on Health Physics field technician support provided.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: |  |  | 1170
Job Number: |  |  | 7700
Job Title: |  |  | NSTX Upgrade HP Allocations
Job Manager: |  |  | Ron Strykowsky
Estimated NSTX Upgrade Health Physics Allocations
Basis of estimate
FY2009 HP Allocated Costs totaled $289K
FY2010 "Projected" HP Allocated Costs total $349K*
* from PPPL Great Plains Budget Data-Base 11/10/09
Assume NSTX Upgrade will have to cover 75% of the HP Allocated Costs Through Completion of the upgrades
For reference in FY2009 NSTX Upgrade Decon activity covered only 58% of the HP Allocated Costs
Allocation map
|  | FY09 | FY10-13 guestimate) |  | base $
FY2010 HP Allocation Budget | NSTX CC
CC-5430 | 1150 | 14% | 12.5% |  | 43.625
349 | 1180 | 58% | 75% |  | 261.75
| 1393 | 14% | 12.5% |  | 43.625
| 9450 | 14% | 0% |  | 0
ESTIMATED DIRECT ALLOCATIONS FOR NSTX UPGRADES
FY10 K$
[7 empty] | FY10 | FY11 | FY12 | FY13
|  |  |  | Base HP allocated costs assigned/year to NSTX upgrade = 75% of $349K= | 261.75
Escalation
[6 empty] | Site Burden | 0.45 | 0.48 | 0.48 | 0.48
[6 empty] | Science Ed | 0.05
[6 empty] | G&A | 0.115 | 0.12 | 0.12 | 0.12
[6 empty] | LDRD | 0.02
[6 empty] | HP ALLOCATION ESTIMATED (loaded)= | 453.2304 | 433.8768 | 433.8768 | 433.8768
[5 empty] | Total= | 1754.8608

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 7700
Job Title: |  | NSTX Upgrade HP Allocations
Job Manager: |  | Ron Strykowsky
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X
| Design Complexity | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Volatility of over head rates |  |  |  | L |  |  |  | -2% +2% | -35 | 35
2 | Volatility of base estimates for the allocated cost centers |  |  |  | L |  |  |  | -2% +2% | -35 | 35
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended