## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 7710
Job Title: | NSTX Upgrade Direct Allocations
Job Manager: | Ron Strykowsky
Description:
The NSTX Upgrade Direct Allocations covers: Laboratory Engineering and Scientific Computer Maintenance and Operations that are "allocated" to various laboratory DOE funded programs based on their Research Staff, Computational Scientist and Mechanical Engineering Division Analysis Engineers FTEs that charge each project. Since the NSTX Upgrades will use Mechanical Engineering Analysis Engineers; a portion of the Direct Allocations are assumed to be "allocated" to the NSTX Upgrades based on the ME Analysis Engineer FTEs charging the NSTX Upgrades as a ratio to the total Lab Scientific FTEs. Laboratory Environmental Services Costs that are "allocated" to all DOE OFES laboratory funded projects based on total operating costs. Since a portion of the NSTX Upgrade scope will be funded with operating funds in FY2010 a portion of the Environmental Services Costs are assumed to be allocated to the NSTX Upgrades.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: |  |  | 1170
Job Number: |  |  | 7710
Job Title: |  |  | NSTX Upgrade Direct Allocations
Job Manager: |  |  | Ron Strykowsky
Estimated NSTX Upgrade Direct Allocations
Basis of estimate = FY09 budgets and anticipated out year allocation maps
|  | FY09 | FY10-13 Estimate |  | base $
FY10 Environmental Services Cost Allocated Budget CC-5450 | 1150 | 32.3% | 32% |  | 537.4048 | CC-5450 ERWM allocations only map to lab "OPERATING" expenses
1679.39 | 1170 | 4.8% | 5% |  | 83.9695 | assuming FY11, FY12, FY13 will be capital expense, no ERWM allocations
| 1180 | 3.8% | 4% |  | 67.1756 | map to the NSTX upgrade project
FY10 Engineering & Scientific Computer M&O Allocated Budget CC-5450 | 1150 | 1.9% | 1.9% |  | 21.6895
1141.554 | 1170 | 1.7% | 2% |  | 22.8311
ESTIMATED DIRECT ALLOCATIONS FOR NSTX UPGRADES
FY10 K$
[7 empty] | FY10 | FY11 | FY12 | FY13
|  |  |  | Base ( unloaded)= | 173.9762
Escalation
[6 empty] | Site Burden | 0.45 | 0.48 | 0.48 | 0.48
[6 empty] | Science Ed | 0.05
[6 empty] | G&A | 0.115 | 0.12 | 0.12 | 0.12
[6 empty] | LDRD | 0.02
[6 empty] | ALLOCATION ESTIMATED (loaded)= | 301.2466 | 37.8448 | 37.8448 | 37.8448
[5 empty] | Total= | 414.781

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 7710
Job Title: |  | NSTX Upgrade Direct Allocations
Job Manager: |  | Ron Strykowsky
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X
| Design Complexity | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Volatility of over head rates |  |  |  | L |  |  |  | -2% +2% | -10 | 10
2 | Volatility of base estimates for the allocated cost centers |  |  |  | L |  |  |  | -2% +2% | -10 | 10
3
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended