## Tab A Description
Work Approval Form (WAF)
Cost Center: 1170
Job Number: 7900
Job Title: Integrated System Test
Job Manager: Charles Gentile
Description: | ACC Review and ISTP development & Implementation
Convene the NSTX Activity Certification Committee (ACC) for comprehensive review of NBI-2 and the new Center Stack upgrade. Prepare and make presentation to the PPPL ES&H Executive Safety Board for issuance of appropriate Safety Certificate parameters for opertion of NSTX with new enhanced operating capabilities. Prepare documentation (procedure) for safely integrating NBI-2 and the new center stack for operations within NSTX safe operating parameters. Work with NSTX Operations Group for the successful intergration of NBI-2 and new CS sub-systems. Participate in cost & schedueling reviews. Report on progress as required.
Schedule:
See Tab B or attached
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
Cost Center: 1170
Job Number: 7900
Job Title: Integrated System Test
Job Manager: Charles Gentile
Estimate (user input)
[5 empty] | SCHEDULE | [10 empty] | FY09$K |  |  |  |  | HOURS | [15 empty] | FY09 | [11 empty] | FY10
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT |  |  | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 |  |  |  | 116.7
task | TASK DESCRIPTION |  |  | Responsible | Duration in WORK DAYS | OPTIONAL Logical Pre-requisites (one task numbers in each column ,any order) | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** DM (Designer) | EC** EM (computing Engr) | EC** SM/TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM/TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM/TB (FO&M Tech) | FC** AM (P&C Officer) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | Other:__________ | Other:__________ | Other:__________ | Basis of Estimate and Names of req'd skills if known | Category | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2010-01-01 | 2010-02-01 | 2010-03-01 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
numb | P3 cross ref (optinal) | [14 empty] | 1.22 | 1.22 | 1.63 | 1.1 | 1.63 | 185.5 | 125.09 | 143.5 | 144.4 | 175.93 | 151.07 | 165.37 | 145.35 | 150.77 | 142.83 | 180.23 | 150 | 150 | 150
1 |  | Physics Requirements | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
2 | [9 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
3 |  | Conceptual Design | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
4 |  | PREPARE WORK PLANNING FORM | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
5 |  | Prep System Description | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
6 |  | Prep System Requirements | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
7 |  | R&D | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
8 |  | Ananlysis | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
9 |  | CDR | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
10 | [9 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
11 |  | Preliminary Design | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
12 |  | Thermal Analysis | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
13 |  | Seismic Analysis | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
14 |  | FMEA Analysis | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
15 |  | Prepare NEPA Form | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
16 |  | Update Cost & Schedule Estimate | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
17 |  | Design Drawings | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
18 |  | PDR Prep | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
19 |  | CONDUCT PDR | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
20 | [9 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
21 |  | Final Design | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
22 |  | Disposition PDR Chits | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
23 |  | Design Drawings | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
24 |  | Update Analyses | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
25 |  | Update Cost & Schedule Estimate | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
26 |  | Prep Procurement Specs | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
27 |  | FDR Prep | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
28 |  | CONDUCT FDR | [7 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
29 | [9 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
30 | [9 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
31 |  | OTHER TASKS |  | Commence at Completion of C D 3 | [5 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
32 |  |  | Conduct ACC Review of upgrades | C. Gentile | [6 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | [10 empty] | 80 |  | 80 | [8 empty] | 4-Previous NSTX Experience
33 |  |  | Prepare NBI-2 & CS ISTP Test Procedure(s) | C. Gentile | [5 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | #REF! | [12 empty] | 120 | [8 empty] | 4-Previous NSTX Experience
34 |  |  | Participate in cost & scheduleing reviews | C. Gentile | [6 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | [13 empty] | 40 | [8 empty] | 4-Previous NSTX Experience
35 |  |  | Perform ISTP ( per NCSX 02) | NSTX Ops | [5 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | [12 empty] | 80 | [8 empty] | 4-Previous NSTX Experience
[10 empty] | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12 | 2009-11-12 12:12
|  | TOTALS | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.0744 | 0 | 52.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CATEGORIZATION CODES:
| The basis of estimate for the ACC review of these NSTX Upgrades as well as preparing test procedures and performing the ISTPs is based on prior experince of commissioning other upgrades to NSTX and performing their required ISTPs. The logic used in developing the ISTP & ACC WAF is similiar to when we bring any new NSTX sub-system on-line ( ie, LiTER, CHI, etc.....). The sub-sytem cogs perform the PTP's. NSTX operations integrates the system into the project via the ISTP(s). Cost and time estimates are based on actual experience for running the past NSTX ACC reviews, and for bringing new sub-systems on board via NSTX-02 ( + the specific ISTP). The risk to the project at the point of the ISTP is relatively low. The higher risk is with the sub-system cog's and their PTP's. | [27 empty] | 1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: 1170
Job Number: 7900
Job Title: Integrated System Test
Job Manager: Charles Gentile
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X | 20%
| Design Complexity |  | X |  | 30%
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Conduct ACC review of NSTX upgrades |  |  |  | 90% | Create puch list of outstanding items. Have sub-system cog address prior to making presentation to PPPL ES&H Ex Safety Board |  |  | ACC Review of NSTX Commissioning
2 | Prepare ISTP procedure(s) for Integration of NBI-2 and new CS into NSTX operations |  |  |  | 90% | Using past experience with similar sub-system ISTP follow similar startup criteria |  |  | Integration of other sub-systems into NSTX Operations
3 | Commence ISTP's via NSTX-02 Startup Procedure |  |  |  | 90% | Run NSTX 02 in accordance with NSTX Operations group |  |  | Experience from performing other ISTP's on NSTX
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended