## Tab A Description
Work Approval Form (WAF)
Cost Center: | 1170
Job Number: | 8200
Job Title: | Installation of the Support System
Job Manager: | Mike Viola
Project Start Date: | 2010-10-01
Description:
The scope of this job includes the PF and TF support upgrade. This involves removing diagnostic equipment for clearance and accessibility, moving the existing PF coils, cutting off existing supports mounted on the vessel, installing a new external cage support system. NSTX is an operating machine complete with a full complement of diagnostics in every bay. In order to reach the existing structure for modification, one must first catalogue as built conditions bay by bay and remove most of the existing diagnostic systems. Then the coils will be demounted and raised or lowered carefully within the profile of the TF coils in order to gain access to the existing ribs and supports. Tooling and fixtures will be needed to accomplish this. At that point the existing ribs need to be modified (cut) and new ribs and reinforcement plates and hardware need to be welded on. After the vessel structure is modified then the cage supports will be installed and the coils relocated into position. A significant metrology effort will be needed to realign all coils back to their precise previous positions. Finally, the diagnostic systems previously removed must be reinstalled, tested and recommissioned.
Schedule:
Refer to Primavera Data-Base
Approvals:
___________________________________________________________
Job Manager
___________________________________________________________
Project Manager
__________________________________________________________
Engineering Department Head

## Tab B Cost & Schedule Estimate
| Cost Center: |  |  | 1170
| Job Number: |  |  | 8200
| Job Title: |  |  | Installation of the Support System
| Job Manager: |  |  | Mike Viola
| Project Start Date: |  |  | 2010-10-01
Estimate (user input)
[5 empty] | SCHEDULE | [13 empty] | FY09$K |  |  |  |  | HOURS (priced at FY09 rates) | [19 empty] | % | % |  |  | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
| USER INPUT TASKS AND DESCRIPTIONS |  |  |  | USER INPUT | [5 empty] | Calculated | [7 empty] | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 |  | 128.59 | 108.44 | 78.33 | 78.33 | 78.33 | 180.79 |  |  |  |  | 116.7 | 116.7
task | TASK DESCRIPTION |  |  | Responsible | Dutration in WORK DAYS | Crew Size | Logical Pre-requisites (one task numbers in each column ,any order) |  |  | User Input Start Date (optional) | START DATE | FINISH DATE | [5 empty] | actual= A | M&S (41) | CREDIT CARD (43) | OTHER (39) | TRAVEL (35) | OVERTIME (31) | EA** EM (analysis engr) | EA** (Designer) | EC** EM (computing Engr) | EC** SB (Computing Tech) | EC** TB (Computing Tech) | EE** EM (Elctr Engr) | EE** SM (Senior Electr Tech) | EE** SB (Electr Tech) | EE** TB (Electr Tech) | EM** EM (FO&M Engr) | EM** SM Senior Tech) | EM** SB (FO&M Tech) | EM** TB (FO&M Tech) | DP** SB/TB (HP Tech) | R*** RM (Researcher) | D*** RM2 (Researcher) | FC** AM (P&C Officer) |  |  |  | COST CONTIGNECY % | SCHED CONTIGNECY % | Names of req'd skills if known | Basis of Estimate Category | time axis 2008-10-01 to 2012-09-01
numb | The scope of this job includes the PF and TF support upgrade. This involves removing diagnostic equipement for clearance and accessibility, moving the existing PF coils, cutting off existing supports mounted on the vessel and installing a new external cage support system. | [17 empty] | 1.226 | 1.226 | 1.712 | 1.232 | 1.892 | 188.6 | 124.9 | 139.7 | 101.3 | 74.4 | 173.4 | 151 | 119 | 84.4 | 159.9 | 150.9 | 119.2 | 90.3 | 142.83 | 177 | 208.3 | 150.77 | 1 | 1 | 1
[13 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
1 |  | Milestone dates | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
2 |  |  | Designs complete | Mangra | 1 | [5 empty] | 2010-10-01 | 2010-10-02 09:36 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
3 |  |  | Sequence complete | Mangra | 1 | [5 empty] | 2010-10-01 | 2010-10-02 09:36 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
4 |  |  | Parts arrived | Mangra | 1 | [5 empty] | 2010-10-01 | 2010-10-02 09:36 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
5 |  |  | Start procedural development | Viola | 1 |  |  |  |  | 2010-10-01 | 2010-10-01 | 2010-10-02 09:36 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
6 |  |  | Mobilize crews | Viola | 1 |  |  |  |  | 2011-01-03 | 2011-01-03 | 2011-01-04 09:36 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
7 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
8
9 |  | Management | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
10 |  |  | Opening Duration | Viola | 400 |  |  |  |  | 2011-01-03 | 2011-01-03 | 2012-07-16 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 0
11 |  |  | Shop Fabrication oversight 20% FTE for duration | Langish | 400 | 0.2 |  |  |  | 2011-01-03 | 2011-01-03 | 2012-07-16 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 640
12 |  |  | Shop Fabrication support 1.5 FTE for duration | Langish | 400 | 1.5 |  |  |  | 2011-01-03 | 2011-01-03 | 2012-07-16 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 4800
13 |  |  | Assembly oversight .75 FTE | Viola | 400 | 0.75 |  |  |  | 2011-01-03 | 2011-01-03 | 2012-07-16 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 2400
14 |  |  | OT for efficiency (2 crews 1 weekend a month) | Techs | 400 | 0.2 |  |  |  | 2011-01-03 | 2011-01-03 | 2012-07-16 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 640
15 |  |  | MISC M&S $250 per day* 2 crews * 75 weeks | Techs | [5 empty] | 2011-01-03 |  |  | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 |  | 190
16
17
18 |  | Documentation | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
19 |  |  | PREPARE WORK PLANNING FORM | Viola | 3 | 1 |  |  |  | 2010-10-01 | 2010-10-01 | 2010-10-05 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 24
20 |  |  | Fab/AssyInstallation Procedure | Viola | 20 | 1 | 19 |  |  | 2010-10-01 | 2010-10-05 04:48 | 2010-11-02 04:48 | 2010-10-01 | 2010-10-05 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 160
21
22 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
23 |  | UPGRADE | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
24 |  | BAY BY BAY DIAGNOSTIC CATALOGUE | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
25 |  | Assume 8 lower 8 midplane and 4 upper bays | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
26 |  |  | Perform bay by bay catalogue and label Elect | SM | 12 | 1 |  |  |  | 2010-10-01 | 2010-10-01 | 2010-10-17 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [16 empty] | 96
27 |  |  | Perform bay by bay catalogue and label Mech | SM | 12 | 1 |  |  |  | 2010-10-01 | 2010-10-01 | 2010-10-17 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [16 empty] | 96
28 |  |  | Write removal procedures | SM | 60 | 1 | 27 |  |  |  | 2010-10-17 19:12 | 2011-01-09 19:12 | 2010-10-01 | 2010-10-17 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [16 empty] | 480
29 |  |  | Remove RF pipes | Techs RF | 20 | 2.5 |  |  |  | 2011-01-03 | 2011-01-03 | 2011-01-31 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 400
30 |  |  | Write Removal & Installation Procedures | SM | 20 | 1 |  |  |  | 2011-01-03 | 2011-01-03 | 2011-01-31 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [16 empty] | 80
30 |  |  | Safe, remove and store Elect | Techs E | 20 | 2.5 |  |  |  | 2011-01-03 | 2011-01-03 | 2011-01-31 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 400
31 |  |  | Upper Tray remove and store Elect | Techs E | 20 | 2.5 | 30 |  |  |  | 2011-01-31 | 2011-02-28 | 2010-10-01 | 2011-01-31 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 400
32 |  |  | Remove and store Mech | Techs M1 | 30 | 5 |  |  |  | 2011-01-17 | 2011-01-17 | 2011-02-28 | 2011-01-17 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 1200
33 |  |  | Remove section of platform | Techs M2 | 10 | 5 |  |  |  | 2011-01-03 | 2011-01-03 | 2011-01-17 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 400
34 |  |  | Fiducialize Coil and Vacuum vessel | Priniski | 20 | 2.5 | 32 |  |  |  | 2011-02-28 | 2011-03-28 | 2010-10-01 | 2011-02-28 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 400
35 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
36 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
37 |  | EQUIPMENT REMOVALS | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
38 |  |  | Remove insulation | Techs M3 | 15 | 2.5 |  |  |  | 2011-01-03 | 2011-01-03 | 2011-01-24 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 300
39 |  |  | Write removal procedures | Techs M4 | 60 | 1 |  |  |  | 2011-01-03 | 2011-01-03 | 2011-03-28 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [16 empty] | 480
39 |  |  | Gas Injection System | Techs M4 | 15 | 2.5 |  |  |  | 2011-01-03 | 2011-01-03 | 2011-01-24 | 2011-01-03 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 300
40 |  |  | Disconnect trim coil and lock mode coil | Techs M1 | 8 | 2.5 | 32 |  |  |  | 2011-02-28 | 2011-03-11 04:48 | 2010-10-01 | 2011-02-28 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 160
41 |  |  | Remove trim coil and lock mode coil | Techs M2 | 30 | 2.5 | 33 |  |  |  | 2011-01-17 | 2011-02-28 | 2010-10-01 | 2011-01-17 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 600
42 |  |  | Clear platform and area to remove bad TF | Techs M3 | 10 | 2.5 | 38 |  |  |  | 2011-01-24 | 2011-02-07 | 2010-10-01 | 2011-01-24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 200
43 |  |  | Remove bad TF | Techs M4 | 5 | 5 | 39 |  |  |  | 2011-01-24 | 2011-01-31 | 2010-10-01 | 2011-01-24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 200
44 |  |  | Heating Manifolds cut and remove | Techs W1 W2 | 6 | 5 | 39 |  |  |  | 2011-01-24 | 2011-02-01 09:36 | 2010-10-01 | 2011-01-24 | 2010-10-01 | 2010-10-01 | 2010-10-01 |  | 25 | [15 empty] | 240
45 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
46 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
47 |  | UPPER HALF | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
48 |  |  | Umbrella Lid Remove existing | Techs M4 | 1 | 5 | 43 |  |  |  | 2011-01-31 | 2011-02-01 09:36 | 2010-10-01 | 2011-01-31 | 2010-10-01 | 2010-10-01 | 2010-10-01 |  | 2 | [15 empty] | 40
49 |  |  | Umbrella Lid Install New | Techs M4 | 10 | 2.5 | 48 |  |  |  | 2011-02-01 09:36 | 2011-02-15 09:36 | 2010-10-01 | 2011-02-01 09:36 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 200
50 |  |  | TF connection casting (modify) | Techs M3 | 12 | 2.5 | 42 |  |  |  | 2011-02-07 | 2011-02-23 19:12 | 2010-10-01 | 2011-02-07 | 2010-10-01 | 2010-10-01 | 2010-10-01 |  | 5 | [15 empty] | 240
51 |  |  | TF Remove turnbuckles | Techs M4 | 2 | 2.5 | 43 |  |  |  | 2011-01-31 | 2011-02-02 19:12 | 2010-10-01 | 2011-01-31 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 40
52 |  |  | VV Trim existing pads | Techs M1 | 12 | 2.5 | 40 |  |  |  | 2011-03-11 04:48 | 2011-03-28 | 2010-10-01 | 2011-03-11 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 240
53 |  |  | VV Install New pads | Techs W1 | 12 | 2.5 | 52 |  |  |  | 2011-03-28 | 2011-04-13 19:12 | 2010-10-01 | 2011-03-28 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 240
54 |  |  | Design build lifting spiders | Techs W1 W2 | 30 | 3 |  |  |  | 2010-10-01 | 2010-10-01 | 2010-11-12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 |  | 25 | [5 empty] | 480 | [7 empty] | 240 |  | 720
55 |  |  | PF2 lift and support | Techs M4 | 2 | 5 | 51 |  |  |  | 2011-02-02 19:12 | 2011-02-05 14:24 | 2010-10-01 | 2011-02-02 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 80
56 |  |  | PF2 Remove existing hardware (bolted) | Techs M4 | 3 | 2.5 | 55 |  |  |  | 2011-02-05 14:24 | 2011-02-09 19:12 | 2010-10-01 | 2011-02-05 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 60
57 |  |  | PF2 Install New plates (bolted) | Techs M4 | 8 | 2.5 | 56 |  |  |  | 2011-02-09 19:12 | 2011-02-21 | 2010-10-01 | 2011-02-09 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 160
58 |  |  | PF2 weld new ribs | Techs W2 | 18 | 2.5 | 57 |  |  |  | 2011-02-21 | 2011-03-18 04:48 | 2010-10-01 | 2011-02-21 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 360
59 |  |  | PF3 remove bolted support | Techs M2 | 4 | 2.5 | 57 | 41 |  |  | 2011-02-28 | 2011-03-05 14:24 | 2010-10-01 | 2011-02-21 | 2011-02-28 | 2010-10-01 | 2010-10-01 | [17 empty] | 80
60 |  |  | PF3 Install new bolted support | Techs M2 | 12 | 2.5 | 77 |  |  |  | 2011-03-11 04:48 | 2011-03-28 | 2010-10-01 | 2011-03-11 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 240
61 |  |  | PF4, 5 Remove existing midplane columns | Techs M4 | 4 | 2.5 | 75 |  |  |  | 2011-03-11 04:48 | 2011-03-16 19:12 | 2010-10-01 | 2011-03-11 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 |  | 30 | [15 empty] | 80
62 |  |  | PF4, 5 support fixture | Techs W1 W2 | 25 | 2.5 | 54 |  |  |  | 2010-11-12 | 2010-12-17 | 2010-10-01 | 2010-11-12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 500
63 |  |  | PF4, 5 lift and support | Techs M4 | 12 | 5 | 61 |  |  |  | 2011-03-16 19:12 | 2011-04-02 14:24 | 2010-10-01 | 2011-03-16 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 480
64 |  |  | PF4, 5 cut and grind existing ribs | Techs M1 | 20 | 2.5 | 63 | 52 |  |  | 2011-04-02 14:24 | 2011-04-30 14:24 | 2010-10-01 | 2011-04-02 14:24 | 2011-03-28 | 2010-10-01 | 2010-10-01 | [17 empty] | 400
65 |  |  | PF4, 5 Install new bolted support | Techs M1 | 18 | 2.5 | 64 |  |  |  | 2011-04-30 14:24 | 2011-05-25 19:12 | 2010-10-01 | 2011-04-30 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 360
66 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
67 |  | LOWER HALF | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
68 |  |  | Umbrella Lid Remove existing | Techs M4 | 1 | 5 | 49 |  |  |  | 2011-02-15 09:36 | 2011-02-16 19:12 | 2010-10-01 | 2011-02-15 09:36 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 40
69 |  |  | Umbrella Lid Install New | Techs M4 | 10 | 2.5 | 68 |  |  |  | 2011-02-16 19:12 | 2011-03-02 19:12 | 2010-10-01 | 2011-02-16 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 200
70 |  |  | TF connection casting (modify) | Techs M3 | 12 | 2.5 | 50 |  |  |  | 2011-02-23 19:12 | 2011-03-12 14:24 | 2010-10-01 | 2011-02-23 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 240
71 |  |  | VV Trim existing pads | Techs M1 | 12 | 2.5 | 52 |  |  |  | 2011-03-28 | 2011-04-13 19:12 | 2010-10-01 | 2011-03-28 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 240
72 |  |  | VV Install New pads | Techs W1 | 12 | 2.5 | 71 |  |  |  | 2011-04-13 19:12 | 2011-04-30 14:24 | 2010-10-01 | 2011-04-13 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 240
73 |  |  | PF2 lower and support | Techs M4 | 2 | 2.5 | 57 |  |  |  | 2011-02-21 | 2011-02-23 19:12 | 2010-10-01 | 2011-02-21 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 40
74 |  |  | PF2 Remove existing hardware (bolted) | Techs M4 | 3 | 2.5 | 73 |  |  |  | 2011-02-23 19:12 | 2011-02-28 | 2010-10-01 | 2011-02-23 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 60
75 |  |  | PF2 Install New plates (bolted) | Techs M4 | 8 | 2.5 | 74 |  |  |  | 2011-02-28 | 2011-03-11 04:48 | 2010-10-01 | 2011-02-28 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 160
76 |  |  | PF2 weld new ribs | Techs W2 | 18 | 2.5 | 75 | 58 |  |  | 2011-03-18 04:48 | 2011-04-12 09:36 | 2010-10-01 | 2011-03-11 04:48 | 2011-03-18 04:48 | 2010-10-01 | 2010-10-01 | [17 empty] | 360
77 |  |  | PF3 remove bolted support | Techs M2 | 4 | 2.5 | 59 |  |  |  | 2011-03-05 14:24 | 2011-03-11 04:48 | 2010-10-01 | 2011-03-05 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 80
78 |  |  | PF3 Install new bolted support | Techs M2 | 12 | 2.5 | 77 |  |  |  | 2011-03-11 04:48 | 2011-03-28 | 2010-10-01 | 2011-03-11 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 240
79 |  |  | PF4, 5 support fixture | Techs W1 W2 | 12 | 2.5 | 62 |  |  |  | 2010-12-17 | 2011-01-02 19:12 | 2010-10-01 | 2010-12-17 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 240
80 |  |  | PF4, 5 lower and support | Techs M4 | 12 | 2.5 | 63 |  |  |  | 2011-04-02 14:24 | 2011-04-19 09:36 | 2010-10-01 | 2011-04-02 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 |  | 10 | [15 empty] | 240
81 |  |  | PF4, 5 cut and grind existing ribs | Techs M1 | 20 | 2.5 | 80 | 64 |  |  | 2011-04-30 14:24 | 2011-05-28 14:24 | 2010-10-01 | 2011-04-19 09:36 | 2011-04-30 14:24 | 2010-10-01 | 2010-10-01 | [17 empty] | 400
82 |  |  | PF4, 5 Install new bolted support | Techs M1 | 18 | 2.5 | 81 |  |  |  | 2011-05-28 14:24 | 2011-06-22 19:12 | 2010-10-01 | 2011-05-28 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 360
83 |  |  | PF4, 5 Install new midplane columns | Techs M1 | 12 | 2.5 | 82 |  |  |  | 2011-06-22 19:12 | 2011-07-09 14:24 | 2010-10-01 | 2011-06-22 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 |  | 10 | [15 empty] | 240
84 |  |  | TF Install New Coil | Techs M1 | 5 | 5 | 83 | 65 |  |  | 2011-07-09 14:24 | 2011-07-16 14:24 | 2010-10-01 | 2011-07-09 14:24 | 2011-05-25 19:12 | 2010-10-01 | 2010-10-01 |  | 50 | [15 empty] | 200
85 |  |  | Reinstall platform sections | Techs M1 | 8 | 5 | 84 |  |  |  | 2011-07-16 14:24 | 2011-07-27 19:12 | 2010-10-01 | 2011-07-16 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 320
86 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
87 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
88 |  | CAGE SUPPORT | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
89 |  |  | Modify Existing support legs | Techs M2 | 12 | 2.5 | 78 |  |  |  | 2011-03-28 | 2011-04-13 19:12 | 2010-10-01 | 2011-03-28 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 240
90 |  |  | Install new cage legs | Techs M2 | 10 | 2.5 | 89 |  |  |  | 2011-04-13 19:12 | 2011-04-27 19:12 | 2010-10-01 | 2011-04-13 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 200
91 |  |  | Grout (need 4 weeks for curing) | Techs M2 | 5 | 2.5 | 90 |  |  |  | 2011-04-27 19:12 | 2011-05-04 19:12 | 2010-10-01 | 2011-04-27 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 100
92 |  |  | Install TF support ring | Techs M2 | 24 | 2.5 | 91 |  |  |  | 2011-05-04 19:12 | 2011-06-07 09:36 | 2010-10-01 | 2011-05-04 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 480
93 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
94 |  | ALIGNMENT VERIFICATION COIL AND VACUUM VESSEL | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
95 |  |  | Map internal targets to external | Priniski | 20 | 2.5 | 84 |  |  |  | 2011-07-16 14:24 | 2011-08-13 14:24 | 2010-10-01 | 2011-07-16 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 400
96 |  |  | Verify Vessel Alignemnt targets | Priniski | 20 | 2.5 | 95 |  |  |  | 2011-08-13 14:24 | 2011-09-10 14:24 | 2010-10-01 | 2011-08-13 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 400
97 |  |  | Verify Coil Alignment Targets | Priniski | 45 | 2.5 | 96 |  |  |  | 2011-09-10 14:24 | 2011-11-12 14:24 | 2010-10-01 | 2011-09-10 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 900
98 |  |  | Adjust vessel Internals | Priniski | 30 | 2.5 | 97 |  |  |  | 2011-11-12 14:24 | 2011-12-24 14:24 | 2010-10-01 | 2011-11-12 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 600
99 |  |  | Adjust TF Coils | Priniski | 10 | 2.5 | 98 |  |  |  | 2011-12-24 14:24 | 2012-01-07 14:24 | 2010-10-01 | 2011-12-24 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 200
100 |  |  | Adjust PF Coils | Priniski | 30 | 2.5 | 99 |  |  |  | 2012-01-07 14:24 | 2012-02-18 14:24 | 2010-10-01 | 2012-01-07 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 600
101 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
102 |  | CENTER STACK PEDESTAL | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
103 |  |  | Remove center stack | Techs M2 |  |  | 92 | [5 empty] | 2010-10-01 | 2011-06-07 09:36 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
104 |  |  | Pedestal remove existing | Techs M2 |  |  | 103 | [5 empty] | 2010-10-01 |  | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
105 |  |  | Pedestal Install new | Techs M2 |  |  | 104 | [5 empty] | 2010-10-01 |  | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
106 |  |  | Pedestal align | Techs M2 |  |  | 105 | [5 empty] | 2010-10-01 |  | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
107 |  |  | Pedestal grout (need 4 weeks for curing) | Techs M2 |  |  | 106 | [5 empty] | 2010-10-01 |  | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
108 | [8 empty] | see new job 8250 |  |  |  | 2010-10-01 | 2010-10-01 | 2010-10-01 | #N/A | 2010-10-01
109 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
110 |  | INSTALL CENTER STACK REPLACEMENT | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
111 |  |  | Design lift fixture | ENG | 75 |  |  |  |  | 2010-10-01 | 2010-10-01 | 2011-01-14 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [15 empty] | 600
112 |  |  | Lift into place / Install ceramic break | Techs M4 |  |  | 80 | [5 empty] | 2010-10-01 | 2011-04-19 09:36 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
113 |  |  | Install 72 flex bus Assys | Techs M4 |  |  | 112 | [5 empty] | 2010-10-01 |  | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
114 |  |  | Fit and Install PF 1a, 1b, 1c U&L buswork | Techs M4 | 15 | 2.5 | 113 |  |  |  | 2010-10-01 | 2010-10-22 | 2010-10-01 |  | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 300
115 |  |  | Fit and Install OH U&L buswork | Techs M4 | 5 | 2.5 | 114 |  |  |  | 2010-10-22 | 2010-10-29 | 2010-10-01 | 2010-10-22 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 100
116 |  |  | Install CHI & Ring bus | Techs M4 | 8 | 2.5 | 115 |  |  |  | 2010-10-29 | 2010-11-09 04:48 | 2010-10-01 | 2010-10-29 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 160
117 |  |  | Install TF coil cooling system (72) | Techs M3 | 30 | 2.5 | 116 |  |  |  | 2010-11-09 04:48 | 2010-12-21 04:48 | 2010-10-01 | 2010-11-09 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 600
118 |  |  | Install Inboard Divertor heating/cooling system | Techs M3 | 15 | 2.5 | 117 |  |  |  | 2010-12-21 04:48 | 2011-01-11 04:48 | 2010-10-01 | 2010-12-21 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 300
119 |  |  | New TF air cooled bus and support system | Techs M3 | 25 | 2.5 | 118 |  |  |  | 2011-01-11 04:48 | 2011-02-15 04:48 | 2010-10-01 | 2011-01-11 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 500
120 |  |  | Install center stack edge tiles | Techs M3 | 5 | 2.5 | 119 |  |  |  | 2011-02-15 04:48 | 2011-02-22 04:48 | 2010-10-01 | 2011-02-15 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 100
121 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
122 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
123 |  | REINSTALL EQUIPMENT | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
124 |  |  | Reinstall trim coil and lock mode coil | Techs M1 | 30 | 5 | 85 |  |  |  | 2011-07-27 19:12 | 2011-09-07 19:12 | 2010-10-01 | 2011-07-27 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 1200
125 |  |  | Reinstall insulation | Techs M3 | 30 | 2.5 | 124 |  |  |  | 2011-09-07 19:12 | 2011-10-19 19:12 | 2010-10-01 | 2011-09-07 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 600
126 |  |  | Gas Injection System | Techs M4 | 25 | 5 | 125 |  |  |  | 2011-10-19 19:12 | 2011-11-23 19:12 | 2010-10-01 | 2011-10-19 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 1000
127 |  |  | Reconnect trim coil and lock mode coil | Techs M1 | 10 | 5 | 126 |  |  |  | 2011-11-23 19:12 | 2011-12-07 19:12 | 2010-10-01 | 2011-11-23 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 400
128 |  |  | Platform areas reinstall | Techs M2 | 10 | 5 | 107 |  |  |  | 2010-10-01 | 2010-10-15 | 2010-10-01 |  | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 400
129 |  |  | Heating Manifold Reinstall | Techs M2 | 10 | 2.5 | 128 |  |  |  | 2010-10-15 | 2010-10-29 | 2010-10-01 | 2010-10-15 | 2010-10-01 | 2010-10-01 | 2010-10-01 |  | 25 | [15 empty] | 200
130 |  |  | Heating Manifold Weld and reconnect | Techs W1 W2 | 5 | 2.5 | 129 |  |  |  | 2010-10-29 | 2010-11-05 | 2010-10-01 | 2010-10-29 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 100
131 |  |  | Reinstall RF pipes | Techs RF | 48 | 2.5 | 127 |  |  |  | 2011-12-07 19:12 | 2012-02-13 | 2010-10-01 | 2011-12-07 19:12 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 960
132 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
133 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
134 |  | BAY BY BAY DIAGNOSTICS | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
135 |  | Assume 8 lower 8 midplane and 4 upper bays | [10 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
136 |  |  | Perform bay by bay review Elect | SM | 2 | 2.5 | 99 |  |  |  | 2012-01-07 14:24 | 2012-01-10 09:36 | 2010-10-01 | 2012-01-07 14:24 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [16 empty] | 40
137 |  |  | Perform bay by bay review Mech | SM | 2 | 2.5 | 136 |  |  |  | 2012-01-10 09:36 | 2012-01-13 04:48 | 2010-10-01 | 2012-01-10 09:36 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [16 empty] | 40
138 |  |  | Write reinstallation procedures | SM | 10 | 2.5 | 137 |  |  |  | 2012-01-13 04:48 | 2012-01-27 04:48 | 2010-10-01 | 2012-01-13 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [16 empty] | 200
139 |  |  | Reinstall Mech | Techs DIAG | 40 | 4 | 138 |  |  |  | 2012-01-27 04:48 | 2012-03-23 04:48 | 2010-10-01 | 2012-01-27 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 1280
140 |  |  | Reinstall Elect | Techs E | 40 | 2.5 | 139 |  |  |  | 2012-03-23 04:48 | 2012-05-18 04:48 | 2010-10-01 | 2012-03-23 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 800
141 |  |  | Testing | Techs E | 40 | 2.5 | 140 |  |  |  | 2012-05-18 04:48 | 2012-07-13 04:48 | 2010-10-01 | 2012-05-18 04:48 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 800
142 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
143 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
144 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
145 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
146 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
147 | [12 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | [17 empty] | 0
[13 empty] | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01 | 2010-10-01
|  | TOTALS | [16 empty] | 372 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7564 | 1512 | 29480 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL Preliminary Cost Estimate ($k)= |  |  |  | 5467.6844 | [13 empty] | 456.072 | 0 | 0 | 0 | 0 | 0 | 59.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1209.4836 | 228.1608 | 3514.016 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Notes: | [22 empty] | CATEGORIZATION CODES:
|  | (1) Procurement lead time: |  |  | Weeks | [18 empty] | 1 - National Standards
|  |  | Purchase orders-Commercial, off-the-shelf items |  | 3 | [18 empty] | 2 - Engineering Judgement/Experience
|  |  | Purchase orders-Noncommercial items |  | 5 | [18 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
|  |  | Subcontracts (non construction) |  | 8 | [18 empty] | 4 - Previous PPPL/ORNL Experience (e.g., TFTR, NSTX, PLT, etc.)
|  |  | Construction subcontracts |  | 9 | [18 empty] | 5 - Prototype Data/Test Results
6 - Catalogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other

## Tab C Risk and uncertainty
Cost Center: |  | 1170
Job Number: |  | 8200
Job Title: |  | Installation of the Support System
Job Manager: |  | Mike Viola
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X
| Design Complexity |  | X
Residual Impacts
[10 empty] | Cost Impact |  | Schedule Impact
| Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  |  | Basis of estimate | Low ($K) | High ($K) | Low (weeks) | High (Weeks)
1 | Damage to coil insulation during removal - This is in case we accidentally nick or gouge the outer insulation. |  |  |  | UL | repair coil - This will take two machine techs and 2 coil Engineer(s) Meighan and Chrzanowski |  |  | Estimate based on conference with Jim Chrzanowski (coil expert) | 10 | See Plan | 2 | 4
2 | Realign vacuum vessel - This is in case the vessel springs or changes shape after cutting the new port opening. This could affect the algnment of all the vessel internals mounted to the vessel wall. |  |  |  | UL | This will take 2 metrology techs and a metrology engineer; Two Machine techs and an Engineer. Possibly a welder to fabricate bracing. |  |  | Based on the time it takes to remove and reinstall existing wall hardware during maintenance weeks | 30 | See Plan | 4 | 8
3 | Realign Coils - This is in case the coils spring or change shape after releasing them from their existing clamps. This could afect the algnment of all any coil mounted to the vessel wall/ribs. |  |  |  | UL | Metrology - new clamps; This will take 2 metrology techs and a metrology engineer; Two Machine techs and coil Engineer(s) Meighan and Chrzanowski and possibly 2 machinists and 1K materials |  |  | Based on the 6 weeks it took to align the existing coils | 30 | See Plan | 4 | 6
4
5
Notes:
(1) | Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
(2) | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
(3) | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Design Maturity Definition
High
Final design available. All design features/requirements well
known. No further design development or evolution expected that
will impact estimate.
Medium
Preliminary design available. Some additional design evolution
likely. Further developments can be somewhat expected or
anticipated and reflected in estimate.
Low
No better than conceptual design basis currently available. Design
details, procedures, etc. still need much development and
evolution of requirements beyond estimate basis is likely and
expected.
Design Complexity Definition
Low
Work is fairly well understood -- either standard construction or
repetition of activities performed in past. Little likelihood of
estimate not being well understood and requirements not being
well defined.
Medium
More complex work requirements that have potential to impact
cost and schedule estimates. Limited experience performing
similar tasks, so ability to estimate accurately is somewhat suspect
High
Extremely challenging tasks and/or requirements. Unique or firstof-
a-kind assembly or work tasks. No good basis for estimating
work exists so there is a high degree of estimate uncertainty.
Based on standard industry and DOE estimate classifications (Per AACEI Recommended

## Tab D M&S Detail
Cost Center: | 1170
Job Number: | 8200
Job Title: | Installation of the Support System
Job Manager: | Mike Viola
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
Description:
CATEGORIZATION CODES:
1 - National Standards
2 - Engineering Judgement/Experience
3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.)
4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.)
5 - Prototype Data/Test Results
6 - Catelogue Price/Vendor Quote
7 - Placed Contracts
8 - Actual experience for NCSX Work
9 - Other
TOTALS