## Sheet1
NSTXU-ECP- | WBS | Control Account | Description of Change | Approval | Level | In $K | Contract Budget Base (CBB) |  | Contingency |  | Total Project Cost (TPC) |  | Status
Date
[7 empty] | Increase/ | Balance | Increase/ | Balance | Increase/ | Balance | *(A/D/P)
[7 empty] | Decrease |  | Decrease |  | Decrease
1 | 1.7.1.5 | 7700/7710 | Combine CA 7700 & 7710 into one CA (7710) Direct Allocations | 2011-04-25 | 3 | 0 | 0 | 77317 | 0 | 16992 | 0 | 94309 | A
2 | 1.6 | 6100 | Move the Baseline Start date for task 6100-0041 to 12 April 2012 | 2011-06-08 | 3 | 0 | 0 | 77317 | 0 | 16992 | 0 | 94309 | A
3 | 1.6 | 6100 | Reduce man-hours on task 6100-0041. Add this budget as M&S in task 6100-0049D | 2011-09-19 | 3 | 0 | 0 | 77317 | 0 | 16992 | 0 | 94309 | A
4 | 1.1/1.8 | 1304/8200 | CA 1304 change to TF procurement (cost/schedule) and CA 8200 restructured and split into two CA’s 8200 (LOE)/8210 (cost/schedule) |  | 2 | [7 empty] | P
5 | 1.5 | N/A | Update the Work Breakdown Structure/Dictionary in the Project Execution Plan to ensure that a single Control Account does not occur at more than one WBS element | 2011-10-06 | 3 | 0 | 0 | 77317 | 0 | 16992 | 0 | 94309 | A
Codes: A = Approved/D = Disapproved/P = Pending