# Draft Strategy for Management

of the

# National Spherical Torus eXperiment (NSTX)

# Center-Stack Upgrade

# Non-Major System Project

# October 28, 2008

Table of Contents

1	Introduction								  1

2	Mission Need Justification / Project Description			  2

3	Project Description							  2

4 	Management Structure						  4

4.1	Organization and Responsibilities

4.2 	NSTX Management Team

4.3	Integrated Project Team

5	Work Breakdown Structure (WBS)					12

6	Resource Plan 								13

6.1 	NSTX Center-Stack Project Costs

6.2	Funding Profiles

7	Project Baselines 							13

7.1	Project Scope Baseline

7.2	Cost and Schedule Baselines

8	Control of Project Baselines						14

8.1	Configuration Management Approach

8.2 	Change Control Process

8.3	Change Control Levels

8.4	Contingency Management Plan

8.5	Value Management/Engineering

9	Project Management and Control Systems				17

9.1	Project Management Systems Approach

9.2	Project Control System Overview

9.3	Cost and Schedule Reviews

9.4	Reporting

10	Funds Management							18

10.1	Project Funding Mechanisms

10.2	Management Reserve Funds

11	Risk Management 							19

12	Acquisition Strategy 							19

13	Data Management System 						20

14	System Engineering and Technical Management			20

14.1	Systems Engineering

14.2	Quality Assurance

14.3	NEPA Documentation And Safety Assessment

15	Integrated Safety Management Plan 					21

Appendix A:  Application of NCSX Lessons Learned			22

Appendix B:  Brief Background Description of the NSTX CS Project

Engineering Managers					25

# INTRODUCTION

The National Spherical Torus Experiment (NSTX) is the world’s highest performance Spherical Torus (ST) research facility funded by the U.S. Department of Energy (DOE) Office of Fusion Energy Sciences (OFES) and is the centerpiece of the U.S. ST national research program.  Operational at DOE’s Princeton Plasma Physics Laboratory (PPPL) since 2000, NSTX is exploring the attractiveness of low-aspect-ratio tokamak or ST concept characterized by strong intrinsic plasma shaping and enhanced stabilizing magnetic field line curvature.  The NSTX device cross section is shown in Fig. 1.1.

Fig. 1.1  NSTX Device Cross Section and Component Description

The NSTX replaceable Center-Stack (CS) assembly is the central part of the NSTX device as shown within a marked box in Fig. 1.1.  The new CS will greatly expand the NSTX plasma operational regime to help establish the physics basis for the next-step ST facilities. The present draft "Strategy for Management of the NSTX CS Upgrade Project" describes the roles, responsibilities, and management interactions among the DOE Office of Science (SC), the DOE Princeton Site Office (DOE-PSO) and the Princeton Plasma Physics Laboratory and the approach PPPL will take to effectively manage the project. This draft Strategy for Management was prepared to be consistent with the intent of DOE order 413.3A, Program and Project Management for the Acquisition of Capital Assets.

The function of this draft "Strategy for Management of the NSTX CS Upgrade Project" is to describe the management and project execution processes that will be implemented prior to approval of the draft NSTX CS Preliminary PEP, which will occur as an element of Critical Decision 1 (CD-1). The final NSTX CS PEP will be approved as an element of Critical Decision 2 (CD-2).

The DOE has identified the NSTX CS Project as a Major Item of Equipment (MIE) Project as opposed to a Line Item construction project.  The differentiating factor between a MIE and a line item construction designation is that the project can be accomplished with little or no significant construction activities required.  It is not a Major System Project. It has a ROM cost range of $? - ?M, as discussed in the CD-0 document..  Since the new CS is a replacement to the present CS on the existing NSTX device no major building additions are required to accommodate the new CS; while there may be some minor interior changes in configuration, these changes will not affect the structural integrity of the existing facility.  In addition, the existing facility is currently served by most of the utilities necessary to support the CS Project, with only minor additional ancillary equipment needed.

# MISSION NEED JUSTIFICATION/PROJECT DESCRIPTION:

See the CS Project CD-0 document.

# PROJECT DESCRIPTION

The NSTX Center-Stack Project involves the design and fabrication of the NSTX  Center-Stack (CS).  Fig. 3-1shows a cross sectional view of the NSTX device with the present (left) CS and the new (right) CS.  The new CS is a logical step for the NSTX facility, which was designed originally to be able to accommodate a replacement.  The CS can be removed relatively easily by removing the 72 flexible joints (36 top and 36 bottom) of the TF coil as shown in Fig. 3-1.  The removable/replaceable CS design facilitates the maintenance and repair of the CS, which is the most stressed and complex component on NSTX.  During the eight years of operation to date, the CS has been removed three times for maintenance, repair and improvements. The new CS will have the same vacuum sealing surfaces to the flexible elements of the vacuum vessel boundary so that it can be installed during a normal annual outage period (typically a period of few months.)   This new CS is capable of ~ 2( higher toroidal magnetic fields (BTF ~ 1T) for 5( longer pulses (~ 5 sec).  This would raise the magnetic fields in NSTX half-way to those of the next-step devices.  The two designs are similar except that the new CS is about 13 cm larger in major radius.  In addition to the TF and OH coils, the new CS will also include top and bottom PF 1A, 1B and 1C coils to retain divertor and plasma shaping flexibility.   The present CS has symmetric top and bottom PF 1A coils but only a bottom PF 1B without a corresponding top PF 1B coil and PF 1C coils.  Due to larger conductor sizes and larger radial build, the stresses in the upgraded TF and OH magnets are similar to those in the present CS.  Similarly, the TF joint current density and the magnetic field at the joint are similar.  So the overall design and the manufacturing processes for the TF, OH magnets and the TF joints should remain similar to those used for the present CS with some design improvements.  The overall forces (e.g., vertical lifting force at the TF joints and overturning force) will be larger due to the higher toroidal and poloidal fields so appropriate support structure enhancements will be implemented.  Since even at 1T, the NSTX TF magnetic field is still modest compared to that of a tokamak (e.g., the vertical lifting force is an order of magnitude lower compared to a comparable size tokamak with BTF ~ 3T), the support structure enhancement is expected to be modest.  The outer PF coils (PF 2, 3, 4, 5) as well as the outer TF coils are sufficient to support the higher field operation.  The power system for the new CS will require nearly doubling the toroidal field coil current.  This will be done by reconfiguring the available TFTR power supplies.  The effects of disruptions on the PFCs, passive plates and vacuum vessel will be assessed and reflected in the design.  The existing OH and PF power supplies are adequate for the projected plasma current of 2 MA.  The new CS will contain a new set of replacement magnetic sensors and thermo-couples.  The new CS replacement will cause relatively minor changes for the plasma diagnostic systems and they will be covered by the normal NSTX diagnostic upgrades and operations as necessary.

The design of the new CS will be accomplished by engineers with input from the research team.  Manufacture of the TF, OH and PF coils will be done by industry, under contract to PPPL, or by a combination of industry and Laboratory efforts. Laboratory personnel will assemble the new CS.  As part of the project, the D-site power supply equipment will be reconfigured or refurbished as needed to meet NSTX new CS TF coil requirements.

Fig. 3.1 The cross section of the present and second (new) Center-Stack (CS).

# MANAGEMENT STRUCTURE

## Organization and Responsibilities

Authority and responsibility for managing the DOE programs and facilities resides with the Secretary of Energy.  The Office of Science (SC) has been delegated responsibility for fundamental research programs in basic energy sciences, biological and environmental sciences, and computational science.  Specific responsibility for the NSTX CS Project as a part of the on-going NSTX Project/Program is assigned to SC’s Office of Fusion Energy Sciences (OFES).

SC-OFES provides funding for the NSTX CS Project directly to PPPL via approved financial plans within the NSTX Project/Program. The NSTX Project has assigned the Engineering and Infrastructure Department the responsibility to execute the NSTX CS Project as shown in Fig. 4-1. Day-to-day oversight is provided by SC’s Princeton Site Office (DOE-PSO), with PPPL accountable to DOE for carrying out the NSTX CS Project.  An Integrated Project Team (IPT) comprised of DOE and PPPL will accomplish this project. PPPL will establish a NSTX CS Project that will be responsible for all R&D, engineering, design, fabrication and installation of the new CS.  Figure 4-1 shows the NSTX CS Project including the DOE reporting structure and the relationship of the NSTX CS Project to the NSTX Project.  Figure 4-2 depicts a preliminary NSTX CS Project management structure including RLMs (Responsible Line Managers) and project control officer reporting to the NSTX CS Project Manager.

FigFigure 4-1  NSTX  CS Project DOE / OFES Organization Structure

Figure 4-2 NSTX CS Project

The following subsections describe the relationships between the elements of the organization and their responsibilities.

### U.S. Department of Energy (DOE)

Within the DOE, the responsibility for the NSTX Program resides in the Office of Fusion Energy Sciences (OFES).  OFES will also maintain executive level awareness of project progress, and an OFES NSTX Program Manager has been assigned.

The OFES NSTX Program Manager (DOE-OFES) is:

- Responsible for programmatic guidance, including defining project objectives, scope, schedule and cost.

- Responsible for allocating project funding.

- Responsible for coordinating the organization and implementation of major project reviews (e.g. Physics Validation Review, Conceptual Design Review, etc.)

- Responsible for project oversight at an executive level.

The DOE-PSO has been delegated the responsibility of carrying out the NSTX Project and a NSTX Federal Project Director (DOE-PSO) is assigned who is responsible for:

- Planning and implementing, and completing the project using a systems engineering approach.

- Organizing and directing the Integrated Project Team (IPT) that is comprised of both DOE and NSTX CS team personnel to implement and achieve the overall project objectives and goals.

- Overseeing implementation of the project objectives, scope, schedule and cost, including:

  - Overseeing the design, fabrication, environmental, safety, and health efforts, including risk management, performed by the PPPL team and their subcontractors, and other functions enumerated in the Project Execution Plan, in accordance with public law, regulations, and Executive orders.

  - Serving as the point of contact between federal and contractor staff for all matters relating to the NSTX CS Project and its execution.

  - Performing all required project status reporting to DOE HQ organizations and database management systems.

  - Evaluates and verifies reported progress; makes projections of progress and indentifies trends.

  - Serving as the Contracting Officer’s technical representative.

### Performing Organizations

#### Plasma Physics Laboratory (PPPL)

PPPL has overall responsibility for the NSTX CS Project execution, reporting to DOE through the Associate Laboratory Director for Engineering and Infrastructure and the PPPL Laboratory Director. Project support in the areas of Quality Assurance and Environment, Safety and Health (ES&H) are provided by PPPL.  Major hardware procurements will be placed through PPPL’s procurement organization.

4.1.2.2	Princeton University

Princeton University as the managing institution for PPPL will provide a management oversight through the Dean of Research who will receive a monthly summary report by the PPPL Director.  Princeton University will also organize an external review of the NSTX CS project including the cost and schedule prior to the DOE CD1, CD2 and CD3 reviews.  It will also hold external reviews as needed during the construction phase of the project.  Princeton University's Best Practice Office will define the Project Management training through its project management initiative.

## 4.2 	NSTX Management Team

Key project positions and responsibilities are as follows:

### Senior Laboratory Managers

#### PPPL Director's Office

The PPPL Director's Office has overall responsibility to DOE for the execution of the NSTX CS Project.  The PPPL Director is supported by the Deputy Director for Operations in the execution of the NSTX CS Project.

#### Engineering and Infrastructure Department

The Engineering and Infrastructure Department has responsibility for the execution of the project to meet technical performance on cost and schedule, which are determined with input from the NSTX Program and Project Heads. The Associate Laboratory Director for Engineering and Infrastructure is responsible overseeing the performance by the NSTX CS Management Team and coordinating with the NSTX Program and Project Heads.

### NSTX CS Project Management Team

#### NSTX Center-Stack (CS) Project Manager

The NSTX CS Project Manager is responsible for the day-to-day execution of the NSTX CS Project in a safe and cost-effective manner, in accordance with requirements, procedures and standards, as set forth in the PPPL contract with DOE.  This includes executing the technical, cost, schedule, project control, risk management, ES&H, and quality assurance aspects of the project within approved cost, schedule, and scope baselines, as defined in the Project Execution Plan and the contract.  The NSTX CS Project Manager has primary responsibility for communication with the NSTX CS Federal Project Director.  The Project Manager will instill a culture of personal accountability within the project team, focusing on driving schedule, without compromising safety and quality.  The NSTX CS Project Manager will participate in the Princeton University's Project Management Initiative to train project managers and be certified by a third-party organization.

#### 4.2.2.2 Responsible Line Managers

The Responsible Line Managers (RLMs) are responsible for carrying out NSTX-CS  engineering design and fabrication activities in their respective disciplines. There are three RLMs: for Design and Procurement, for Construction (the Construction Manager), and for Electrical Systems.  The Responsible Line Managers (RLMs) report to the NSTX CS Project Manager as shown in Fig. 4.2.

4.2.2.3 WBS Managers

The project engineering work organization is structured according to the work breakdown structure (WBS) utilizing the original NSTX construction WBS structure. A WBS Manager is assigned at the optimal WBS level according to a risk based graded approach.  In some instances, this “optimal” level may be at WBS Level 2 and sometimes at a lower level (job managers or cost account managers). A WBS Manager is responsible for the execution of the work scope consistent with technical, cost, and schedule objectives. The WBS managers report to Responsible Line Managers.

#### NSTX CS Project Control Officer

The NSTX CS Project Control Officer reports to the NSTX CS Project Manager and is responsible for all project control and administrative functions necessary to support NSTX Project activities.

The NSTX CS Project Control Officer’s responsibilities include:

- Coordinating the development of project plans and administering the centralized Work Authorization system;

- Maintaining up-to-date NSTX cost and schedule baselines that are consistent with the technical baseline;

- Coordinating the preparation of statements of work, sole source justifications (as appropriate), the processing of requisitions, and tracking of procurements and subcontracts supporting the project;

Establishing, maintaining, and monitoring project budgets and schedules to ensure consistency with project control milestones and funding;

- Operating the PPPL Project Control System (PCS) as the Project Control System for the NSTX CS Project.

- Assisting the Project Manager in administering the operation of the NSTX documentation, configuration management, requirements definition, and design description systems;

- Serving as the primary point-of-contact to the PPPL Business Operations Department; and

- Performing administrative functions such as space planning, facility maintenance coordination, travel approvals and vouchers, and overall personnel planning.

#### Engineering Support Team

The Engineering Support Team reports to the NSTX CS Project Manager and is responsible for engineering support activities, including:

- Systems Engineering;

- Design Integration;

- Systems Analyses and Technical Assurance;

#### Quality Assurance (QA) and Environment, Safety & Health (ES&H)

##### 4.2.2.6.1Quality Assurance

An NSTX QA Engineer and an NSTX ES&H Engineer are assigned to support the NSTX CS Project Manager.  The NSTX QA Engineer, with the support of the entire QA Division, will assist the project in meeting quality assurance/control objectives. Support tasks include:

- Preparing a project QA plan;

- Assisting in the development of project procedures, policies, and other plans, as requested by project management;

- Providing quality related services such as inspections and support of procurements; and

- Performing both compliance-based and performance-based audits of the project and its associated plans and procedures.

- Coordinate DCMA inspections on project industrial subcontracts. Provide assurance to DOE-PSO of DCMA activity and deliverables.

4.2.3.6.2 ES&H Engineer

ES&H Engineer support responsibilities - The NSTX ES&H Engineer will assist the project in meeting ES&H objectives. These include safe execution of the project and producing a facility that will be safe to operate. The NSTX ES&H Engineer will assist in implementing PPPL ES&H policies and procedures. The NSTX ES&H Engineer will prepare any required National Environmental Policy Act (NEPA) documentation and a Safety Assessment Document (SAD).

While their normal reporting relationship is to the NSTX CS Project Manager, both individuals have a direct line of reporting to the PPPL Head of ES&H and Infrastructure for items involving overall QA and ES&H impact.

## 4.3	Integrated Project Team

The NSTX Integrated Project Team (IPT) is made up of key DOE and NSTX CS Project Team personnel.  The IPT is led by the NSTX Federal Project Director.  While the makeup of the IPT will evolve as the project matures, the initial makeup of this cross-functional team for the project activities includes the following personnel:

- The NSTX Federal Project Director;

- The OFES NSTX CS Program Manager;

- The Associate Laboratory Director for Engineering and Infrastructure

- The NSTX CS Project Manager;

- The NSTX CS Project Engineering Integration Manager.;

- The PPPL Procurement Manager;

- The NSTX Quality Assurance Manager;

- The NSTX ES&H Manager; and

- The NSTX CS Project Control Officer;

Other DOE and NSTX Project Team and PPPL personnel may be added as the need arises in order to accomplish the NSTX CS Project objectives.  For example, as the NSTX CS Project nears ISTP, personnel with ISTP operational experience will be added to the team.

5	WORK BREAKDOWN STRUCTURE (WBS)

The NSTX Center-Stack (CS) Project has been organized into a preliminary Work Breakdown Structure (WBS). The final WBS, which will be developed to support approval of CD-2, will contain a complete definition of the project’s scope and will form the basis for planning, executing and controlling project activities. The WBS is structured to the following level classification:

WBS Level 1 – NSTX CS Project

WBS Level 2 – Major Subsystem

WBS Level 3 – Specific Component of Major Subsystem

The preliminary Level 2 WBS is shown below.

Level 1 Center-Stack Project

Level 2 WBS 1.Center-Stack

Inner TF bundle and joints OH coils PF 1 coils CS casing PFCs Load analyses and support enhancements Ceramatic insulators Support base and structures. Final CS assembly Diagnostics/ sensors Central I&C

Level 2 WBS 2. Power System

TF Coil Power Supply Modification

Level 2 WBS 3. Construction

Old CS Removal and new CS installation Other related NSTX Test Cell activities

Level 2 WBS 4 Project Management and Integration

Project Management Project Control System Engineering Management System analysis Design integration. Environment, Safety, and Health Integrated System Tests

.

# RESOURCE PLAN

## NSTX Center-Stack (CS) Project Costs

As indicated in Section 1 of this draft Strategy for Management of the NSTX CS Project, the NSTX Center-Stack (CS) Project has been designated by the Department of Energy as a Major Item of Equipment (MIE) and will be funded with NSTX Operational Funds as well as Capital Equipment Funds.  As a result of this decision, the overall cost objective that encompasses all project work scope is measured in terms of the Total Estimated Cost (TEC). These TEC cost activities will be used to measure the performance of the NSTX CS Project against its technical, cost, and schedule baselines. CD-0 provides a cost range and funding profile for the NSTX CS Project.

# PROJECT BASELINES

The initial NSTX CS Project scope, schedule, and cost baselines will be developed in the conceptual design phase of the project. The initial performance baseline will be established with the approval of CD-2 in 2010.

## Project Scope Baseline

The configuration or technical baseline is the configuration/technical documentation formally designated at a specific time during the Project.  Configuration baselines, plus approved changes to those baselines, constitute the current configuration documentation.  Configuration baselines will be established at CD-2.

## Cost and Schedule Baselines

The cost and schedule baselines for the NSTX Center-Stack (CS) Project will be established at CD-2.  The NSTX CS Project resource-loaded schedule will provide the schedule and cost details for the Project’s performance measurement baseline. The Primavera Project Planner (P3) commercial scheduling module will be the standard software used for the NSTX CS Project.  Even prior to CD-2, the NSTX CS Project will utilize P3 as a tool to develop an integrated schedule to monitor progress and develop a consistent staffing plan.  There will be a minimum of three levels of detail starting with the Project Summary Schedule (Level 1). This summary level schedule will identify significant DOE and project milestones and summary logic for the entire project.

The other three levels of schedule are as follows and provide increasingly greater level of detail:

- Level II or Intermediate Schedules – will show major milestones and key tasks summarized by WBS, including key interrelationships.

- Level III or Job Level Schedules – will be developed at the time of the project baseline.

- Level IV or Working Level Schedules – depending on the needs of the project, detailed working level schedules are prepared as needed.  As critical tasks occur (e.g., complex hardware procurement, fabrication and installation tasks, etc.), activities that are covered in the Level III job schedules may be broken down into additional detail to allow for coordination of work by the responsible manager.  Level IV schedules may also be developed by cognizant job managers to aid in the performance and control of their jobs.  This level of schedule detail is normally not controlled at the same rigor as higher level schedules, but efforts are made to ensure continuity to established project milestones and Level III schedules.

# CONTROL OF PROJECT BASELINES

## Configuration Management Approach

Changes to the NSTX configuration, cost, and schedule baselines will be controlled using a disciplined, yet flexible configuration management approach. Changes to the baseline are carefully considered and evaluated for impact before proceeding.  Processes for effecting changes to the configuration, cost, and schedule baselines will be described in the Configuration Management Plan to be developed as a part of CD-1.

## Change Control Process

The NSTX change control process will ensure that changes to the NSTX new CS design and requirements are properly identified, screened, evaluated, implemented, and documented. A formal procedure will be fully implemented after CD-2, though it will begin to be used starting at the CD-1 to oversee the change control process.

Once an Engineering Change Proposal (ECP) has been prepared and the impacts fully documented, the ECP will come before a project Change Control Board (CCB) that is comprised of senior members of the NSTX Center-Stack (CS) Project management team.  CCB chaired by the NSTX CS Project Manager or his designate will be established by the integrated project team during the conceptual design phase.  Other members of the CCB will be assigned as appropriate, but may include the following:

- Project Control Officer

- Engineering Integration Manager

- WBS Managers

- ES&H representative

- QA representative

- Other cognizant job managers impacted by the proposed change

The chairperson shall have the ultimate authority to recommend changes for the final approval; other board members act solely as advisors.

Once a proposed change is approved, the project will implement the change in a timely manner. An updated list of approved, disapproved, and pending changes will be maintained electronically by Project Engineering on the NSTX Engineering web site.

## Change Control Levels

Changes to the NSTX configuration, cost, or schedule baselines will be classified according to their impact on the project.  The change approval levels are established consistent with the technical, cost, and schedule risk and are intended to feed into the higher-level DOE configuration change system. Program directed changes will be approved at an appropriate level as determined within the Office of Science. For project baseline deviations, Table 8-1 summarizes the performance baseline change authority for the Associate Director for Fusion Energy Sciences - Office of Science  (Level 1), the NSTX Federal Project Director (Level 2), and the NSTX Laboratory Project Manager (Level 3).

Table 8-1 NSTX CS Project Change Classification Matrix

| Change Level | Approval Level | Technical Scope | Schedule | Cost |
| --- | --- | --- | --- | --- |
| 1 | Associate Director for FES | Changes to technical requirements and parameters that affect safety basis and operation function, but do not affect mission need objectives. | Less than a 6 month increase (cumulative) in the original project completion date. | Increase of the original cost baseline. |
| 2 | NSTX Federal Project Director | Changes with ES&H impacts significant enough to affect the approved NEPA/EA documentation. | <3 month increase (cumulative) in the original project completion date OR Change in DOE level 2 milestone. | Changes requiring the use of contingency funds |
| 3 | NSTX Project Director | Changes not requiring DOE approval. | All other changes to the performance measurement baseline schedules not requiring DOE approval. | All other changes to the performance measurement baseline costs not requiring DOE approval. |

## Contingency Management Plan

The amount of contingency will be established at the beginning of the project based on a risk assessment performed as part of the cost estimating process. This will be done at CD-2. A formal risk-assessment methodology that considers technical, cost, and schedule risks at the subsystem level, is performed, using a high-medium-low risk classification.  The initial project contingency level will be approved by the Associate Director for Fusion Energy Sciences as the Acquisition Executive for NSTX at CD-2 as part of establishing the overall cost and schedule baselines.

Based on experience with similar projects, changes in scope of work and schedule, requiring the application of contingency, typically arise as a project proceeds. Changes involving the application of contingency must be approved by the NSTX DOE Federal Project Manager via the configuration control process. Cost and schedule baselines and remaining contingency will be adjusted upon approval of change proposals.

Each fiscal year, not later than the middle of the year, the NSTX CS Project Manager will assess the status of authorized work, achieved milestones, and current and future risks, to determine how to apply remaining management reserve (See Section 10.2) funds under the CS Project Manager’s control. They can be used to authorize as yet un-funded work planned for the current or future years, to fund approved changes, or a combination of these. This decision will occur early enough in the fiscal year to permit effective use of these funds, and will be presented as part of the annual mid-year project review meeting with DOE.

## Value Management/Engineering

Value Engineering (VE) is the systematic application of recognized techniques by a multi-disciplinary team to identify the function of a product or service, establish a worth for that function, generate alternatives through the use of creative thinking, and provide the needed functions to accomplish the original purpose of the project at the lowest life-cycle cost without sacrificing safety, necessary quality, and or environmental attributes of the project.  The NSTX Project will apply VE methodologies following a tailored approach to the formal elements of VE.  The NSTX approach has included:

- Using a multi-disciplinary team to identify and assess alternates;

- Following a systematic job plan;

- Identifying and evaluating function, cost and worth;

- Developing and evaluating new alternatives for required functions; and

- Developing and implementing recommendations.

The NSTX Project will apply value engineering methods from early in the design process, starting with the pre-conceptual design phase.

# PROJECT MANAGERMENT AND CONTROL SYSTEM

## Project Management Systems Approach

The NSTX Center-Stack (CS) Project Manager will ensure that all project activities are properly controlled using PPPL’s Project Control System (PCS).  This system will be used as a management tool in planning and executing the project work scope and evaluation of schedule and budget performance. The NSTX CS Project Manager will report the status of progress and variance in the WBS elements monthly to the Associate Laboratory Director Engineering and Infrastructure, the NSTX Project Director and the PPPL Director’s Office.

Project Control System Overview

The NSTX CS Project will use the existing PPPL Project Control System (PCS) as described in the PPPL Project Control System Description. This document was reviewed and approved by DOE in 1996.  The PPPL PCS satisfies the principles of project management and control systems outlined in this draft Strategy for Management and DOE Order 413.3A (“Program and Project Management for the Acquisition of Capital Assets”).  It is our understanding that DOE plans on certifying our EVMS in the next year, providing added assurance that the system meets DOE’s expectations.

## Cost and Schedule Reviews

Nominally the Project will schedule quarterly reviews of Project status with the NSTX Federal Project Director and the OFES Management.  These reviews will focus on cost and schedule aspects of the Project.  At these meetings the project will report the status of the project in general and the cost variances that potentially impact the level of contingency in particular.  Progress on detailed planning will also be reported.  Every six months a bottoms-up estimate at completion (EAC) will be performed for the entire project.  This may involve the re-scheduling of work previously scheduled but not completed. This is done in order to ensure that the current performance measurement baseline remains up-to-date and consistent with the approved performance baseline parameters (TEC, completion date, etc.), and remains a reliable basis for budgeting, resource planning, and measurement of future performance.

## Reporting

Quarterly project reports to OFES will be prepared by the NSTX CS Federal Project Director. All monthly PCS status will be provided to the NSTX CS Federal Project Director.  The data should include, but not limited to, the following:

- Actual cost of work performed (ACWP) - cumulative and incremental for overall project and lower tier WBS work packages

- Budgeted cost of work performed (BCWP) - cumulative and incremental for overall project and lower tier WBS work packages

- Budgeted cost of work scheduled (BCWS) - cumulative and incremental for overall project and lower tier WBS work packages

- Schedule variance (SV) and cost variance (CV) with explanation and planned corrective action

- Cost performance indices (CPI) and schedule performance indices (SPI) (cumulative and incremental) for overall project and lower tier 3 active WBS work packages.

- Cost and schedule contingency analysis reconciled against CV and SV with an updated risk registry changes

- Critical path analysis and near term ‘look ahead’

- Status of near term Level 2 milestones

Additionally, the NSTX Federal Project Director, and other members of DOE-PSO, will participate in scheduled status meetings as well as design reviews

The DOE NSTX Federal Project Director is responsible for entering monthly performance data and narrative into the DOE Project Assessment and Reporting System (PARS) database.

# FUNDS MANAGEMENT

## Project Funding Mechanisms

NSTX/PPPL will be funded directly via DOE Budget and Reporting (B&R) line.  DCMA activity will be funded via interagency agreement between DOE-PSO and the DCMA. Funds will be transferred from NSTX’s B&R line to DCMA to be utilized in the execution of subcontract site inspections requested by the NSTX CS Project. Participation of other organizations other than other DOE National Laboratories will be funded by PPPL through subcontracts.  All project work and expenditure of project funds will be centrally authorized and controlled by the project office via the PCS. The annual NSTX funding requirements will be updated each year by PPPL through their respective DOE Field Work Proposal (FWP) processes.

## Management Reserve Funds

All funds authorized for the Project by the DOE Financial Plan will be disbursed to the NSTX Program Fund (PPPL). Management reserve funds are a portion of each year’s approved funding allowance that are set aside at the beginning of each fiscal year instead of being immediately used to authorize work.  Management reserve funds will be held in a unique management reserve account controlled by the NSTX CS-Project Manager. As needs arise, the NSTX CS-Project Manager will authorize the disbursement of the management reserve funds to authorize as yet un-funded work scheduled for the current year or future years, or resolve approved changes arising within the current year’s authorized scope of work. Changes requiring the application of contingency, will be handled via the change control process defined in Section 8 and will, as stated there, require DOE Federal Project Director or higher DOE approval. As part of the reporting process, the NSTX CS-Project Manager will report on management reserve disbursements regularly, and as part of the cost and schedule project review meetings, including the IPT meetings, with DOE, as well as the Associate Laboratory Director for Engineering and Infrastructure and the NSTX Project Director.

# RISK MANAGEMENT

The NSTX Center-Stack (CS) Project will manage risks, where “risk” refers to factors within the Project’s control that both threaten and provide opportunities to improve project cost and schedule performance and the achievement of project technical objectives.  During all phases of the NSTX CS Project, priority is placed on identifying and mitigating risks.  Risk mitigation activities are incorporated into the project’s cost and schedule baselines, as appropriate. Contingency is used to address realized risks.

While any member of the NSTX CS Project Team is expected to identify risks that become apparent, the responsibility for risk management for the NSTX CS Project rests with the NSTX line management.  The NSTX CS Project Risk Management Plan with a risk registry will be developed consistent with the requirements in DOE 413.3a as an appendix to the Project Execution Plan (PEP) during the conceptual design phase of the project.  The risk factors and mitigation plans as necessary will be factored into the baseline cost and schedule.

# ACQUISITION STRATEGY

The NSTX CS Project Acquisition Execution Plan (AEP) will be issued and approved as part of the CD-1 approval process.  The NSTX CS Project will follow the strategies and processes outlined in the AEP.  The key feature of the NSTX CS Project acquisition strategy and planning is the procurement of critical components that comprise the new NSTX CS. Procured components will be assembled by Laboratory labor into the completed new CS assembly. All major procurements will be placed by the PPPL Procurement Department.

Since the majority of the other systems will primarily be upgrades and/or modifications to existing PPPL systems and structures, it is anticipated that simple build-to-print of fixed price procurements based on firm specifications are feasible.

During Final Design, the project, in conjunction with the PPPL Procurement organization, will develop a formal CS Project procurement plan that identifies all planned procurements by type, dollar amount, key dates, and special requirements such as incentive, or shared savings, provisions.

# DATA MANAGEMENT SYSTEM

A system for controlling documents and drawings, adapted from existing PPPL document and drawing control systems using hard copy and electronic media, will be developed to ensure the organized and consistent treatment and format of NSTX documents including procedures, plans, memos, drawings, calculations, requirement documents, design documents, and procurement documents.  This system will utilize web-based file servers for rapid review, authorization, updating, and retrieval of documents and drawings.  The majority of project documents (other than drawings) will be made available from the NSTX web page. Drawings in electronic format will be accessed via the Pro/INTRALINK database. Legacy drawings only in hard copy can be obtained from the PPPL Drafting Center.  The NSTX CS Project will develop a separate Document and Records Plan that identifies documents to be controlled on the project, including the document’s purpose, approval level, format, naming convention, and records retention requirements.  The NSTX Data Management Plan will describe the processes to be used for document and drawing control.  Processes for effecting changes to controlled documents will be described in the Configuration Management Plan.  All participants will be encouraged to use the project standards for documents of either the MAC or PC versions of Microsoft Word, Microsoft Excel, or Microsoft PowerPoint.

# SYSTEM ENGINEERING AND TECHNICAL MANAGEMENT

## Systems Engineering

The Engineering Support organization has responsibility for implementing a systems engineering program on NSTX.  The systems engineering program includes the development and allocation of requirements; system design and verification; risk management; value engineering; configuration management; interface management; data management; and technical reviews.  The systems engineering program will be described in the Systems Engineering Management Plan.

## Quality Assurance

The NSTX Project QA Plan will demonstrate how the existing PPPL Quality Assurance Plans and implementing policies and procedures, in conjunction with additional NSTX specific plans, policies, and procedures will satisfy the requirements of the DOE Order on Quality Assurance, 414.1A, and provide an appropriate level of quality on the project.  The Defense Management Contract Agency (DCMA) will augment the PPPL QA organization by providing written audit reports to PPPL staff on subcontract site visits.

## NEPA Documentation and Safety Assessment

The NSTX Project will comply with the requirements of the National Environmental Policy Act (NEPA) and its implementing regulations prior to taking any action on the proposed project that would have an adverse environmental effect or that would limit the choice of reasonable alternatives. It is noted that the NEPA review process was completed for the original NSTX project without adverse findings and that no major departure from the original project is proposed for the new CS.  It is expected that a Categorical Exclusion (CX) under Appendix B to Subpart D of the DOE NEPA Implementing Procedure Rule (10CFR1021) will be requested from the Princeton Site Office for the CS Project.

# INTEGRATED SAFETY MANAGEMENT PLAN

PPPL follows the institutional Integrated Safety Management Plan (ISM) that has been approved by DOE.  The NSTX Project intends to follow that ISM and to adopt this plan as its own for the conduct of NSTX work performed at PPPL.

ISM at PPPL is comprised of:

- The governing policy that safety be integrated into work management and work practices at all levels.

- The distinct policies, programs, procedures, and cultural beliefs that PPPL has developed as the structure that PPPL workers utilize in fulfilling PPPL’s environmental, safety, and health responsibilities.

The NSTX Project will incorporate ISM into its management approach as follows:

- By accepting responsibility for safety as a line management responsibility. The NSTX CS Project Manager is responsible for safe execution of the project.

- By following PPPL procedures for work planning (e.g., ENG-032, etc.), where applicable. These procedures including the JHA (Job Hazard Analysis) incorporate the ISM core functions of folding safety into the work planning, establishing appropriate controls, operating within established parameters, feedback.  The “core functions” of ISM include the following 5 step process:

- Defining the scope of work;

- Analyzing the hazard;

- Developing and implement hazard controls;

- Performing the work within these controls; and

- Providing feedback and continuous improvement to this process.

Where project-specific procedures must be developed, ISM principles will be incorporated into them.

# NSTX CS Upgrade Project

# Appendix A:

# Application of NCSX Lessons Learned

A Lessons Learned study was conducted by PPPL and Princeton University (PU) to better understand issues that led to cost and schedule variances on the National Compact Stellarator Experiment (NCSX) and to establish corrective actions to prevent reoccurence of similar problems in future projects. This appendix describes how solutions to the the NCSX Lessons Learned will be applied to support the NSTX Upgrade Projects.

# NCSX Lesson Learned

1. Complete requisite R&D and designs prior to establishing a baseline.

# NSTX solution:

The complex geometry and tight fabrication tolerances of NCSX created unique engineering and assembly challenges. It was found that R&D and design needs to be sufficiently completed to establish a sound technical basis for the cost and schedule estimates.  The NSTX new center-stack on the other hand can be considered as a variant (or an upgrade) to the existing center-stack where the NSTX team has ten years of design, fabrication, and operational experience.  In addition, the geometry and configuration for the center-stack is far simpler compared, for example, to the NCSX modular coils.  The anticipated R&D needs for the center-stack are relatively well defined and modest, mainly in the TF joint and the OH conductor joint areas.   Neverthelss, the NSTX CS project will perform the necessary design and R&D prior to CD-2 to indentify any potential issues and make sure that tolerance requirements are well defined prior to defining the cost and schedule baseline.

# NCSX Lesson Learned

2. Implement rigorous, disciplined, and realistic cost estimating techniques early on.

# NSTX solution:

The formality of estimating cost and schedule was insufficient during the early years of the NCSX project.  For the NSTX Center-Stack (CS) project,  the cost and schedule baseline will be defined at Critical Decsion 2 (CD-2).  Prior to NSTX requesting CD-2 approval  a WBS defining all the elements of the upgrade project will have been established.  Preliminary design reviews (PDRs) for all WBS elements of the upgrade project will be held.  These PDRs will take place after all design issues have been addressed, including any necessary research and development or prototyping, and the design has matured enough to allow sufficient information for the development of the Performance Baseline.  The Performance Baseline will include cost and schedule estimates for the full scope of the project using standardized cost and schedule methodologies which will include the basis for all estimates.  Risks will be identified and classified with appropriate contingencies applied.  These preliminary designs will be reviewed by both internal and external experts and their comments will be addressed prior to review of the proposed Performance Baseline by the DOE Office of Project Assessment (OPA) in preparation for submittal of CD-2.  During the conceptual design process and prior to CD-1 cost estimates will be developed for all WBS elements and reviewed both internally and by an expert external review team to insure that the cost basis for the estimates is sound.

# NCSX Lesson Learned

3. Conduct regular bottoms-up estimates to complete (ETC) to identify and address cost and schedule issues.

# NSTX solution:

# After the approval to start construction, the NCSX Project did not perform thorough ETC updates on a regular basis causing inability to recognize and resolve cost and schedule issues in a timely fashion.   As part of the monthly statusing process the NSTX CS Project Cost Account Managers/PPPL Job Managers will be required to validate their EACs.  In addition a comprehensive bottoms-up estimate by the Cost Account Manager will be performed each 6 months to insure that ramifications of future work are scrutinized.

# NCSX Lesson Learned

4. Develop and execute an effective risk management plan early on.

# NSTX solution:

The late introduction of a rigorous risk analysis on the NCSX Project was identified as a root cause for a significant increase in cost and schedule late in the project cycle.  The use of formal risk and opportunity assessment techniques, based on a risk register and analysis of the tasks at the appropriate WBS level will be introduced early in the NSTX CS project cycle to establish cost and schedule contingency requirements.  During all phases of the NSTX CS Project, priority will be placed on identifying and mitigating risks.  Risk mitigation activities will be incorporated into the project’s cost and schedule baselines, as appropriate and contingency is used to address realized risks.  While any member of the NSTX CS Project Team is expected to identify risks that become apparent, the responsibility for risk management for the NSTX CS Project rests with the NSTX line management.  The NSTX CS Project Risk Management Plan with a risk registry will be developed consistent as an appendix to the Project Execution Plan (PEP) during the conceptual design phase of the project.  The risk factors and mitigation plans as necessary will be factored into the baseline cost and schedule.

# NCSX Lesson Learned

5. Develop, maintain, and execute a staffing plan.

NSTX solution:

# The NCSX Project was delayed due to inadequate staffing level due to several interconnected factors.  Accordingly, the NSTX CS Projcet will develop and maintain a staffing plan early in the project identifying the specific individual’s name, where appropriate, to insure that adequate resources are identified and assigned to support the tasks on the projects resource loaded schedule.

# NCSX Lesson Learned

6. Recognize the cost and schedule implications of using high technology tools at or near their capability limits.

# NSTX solution:

# The NCSX device represented a one of the kind experimental facility with unprecedented complexity and tolerance requirements ever undertaken by the US fusion facility project team.  Accordingly, many high technology tools were utilized at or near their capability limits.  In comparison, the NSTX new center-stack geometry and configuration for the center-stack is much simpler compared to NCSX.  The NSTX CS TF coil bundle is circlar and straight where as the NCSX modular coils are intricatedly curved in complex 3-D patterns.  The NSTX CS OH coils are solenoidal and its winding geometry is conventional and will not present any new manufacturing issues.  Similarly the NSTX CS Poloidal Field coils and the CS casing are comprised of a simple cylindical geometry.  The NSTX CS Project therefore will largely utilize well tested conventional technology and tools for its project needs.  Nevertheless, the NSTX CS project will be open minded in considering utilization of new technology tools if they will lead to an improved cost and schedule and/or an improved product quality.  In that event, the project will consult/recruit more experienced users of the technology and all tools be validated before their utilization.  Such capabilities if selected will be confirmed prior to its implementation.

# NCSX Lesson Learned

7. Develop strong ties with external resources in key technology areas, including those outside of your area of expertise.

# NSTX solution:

The conceptual, preliminary, and final design team members and respective review team members will include experts in key techonology areas from universities, industry and DOE national laboratories.  The comments from the review team will be addressed prior to the DOE-OPA reviews of the NSTX Project. In addition, Princeton University will provide technical and project management oversight throughout the project’s history. This will insure that the outside independent expert comments and recommendations are addressed and resolved.

In addition, Don Rej, who has completed his assignment on NCSX and has returned to LANL, will provide valuable expertise and mentoring to both the NSTX-
CS and NSTX-2nd NBI Project Managers as well as the PPPL management by helping PPPL management ensure that we have the mechanisms and the management commitment to meet cost and schedule targets, have the necessary expertise assigned to the project to succeed; and have the disciplined, rigorous implementation of project management policies through processes that focus on results. He will advise us on our processes to evaluate and confirm cost estimates, including the estimates' basis and level of detail, associated risks, and contingency planning in the event of unexpected events; planned schedules and how schedules could affect cost estimates; the appropriateness of the project's business management, including organization, project controls, staffing, risk mitigation, quality issues, and environmental and safety compliance issues; and the actions taken to address previous issues or recommendations from past reviews. We anticipate that Don Rej will participate in the monthly project reviews and spend up to 0.10-FTE in this role.

# NCSX Lesson Learned

# 8. Build a strong, effective project management organization early.

# NSTX solution:

The NSTX CS Upgrade Project is assemblying a strong, effective project management organization at the early stage of this project at the time of the CD-0 approval.  NSTX CS Upgrade Project Manager has decades of engineering management experience and he has been working on the fabrication upgrades project on NSTX since the construction of NSTX facilities in 1997.  The NSTX CS Integration Engineering Manager is also the NSTX Project Engineer and he has been organizing the engineering effort on NSTX since inception of the NSTX Project in 1996.  The vitae of the project manager, the RLMs and the project control officer for the project are listed in Appendix B.  In addition The NSTX CS Project Manager will participate in Princeton University’s Project Management Initiative, which will provide additional training  and he will be certified as a Project Manager by a third-party organization.

# NCSX Lesson Learned

9. Communicate and act.

# NSTX solution:

The NSTX Project will schedule quarterly reviews with the NSTX DOE-PG Federal Project Director and the OFES Management.  At these meetings the project will report the status of the project. Every six months a bottoms-up estimate at completion (EAC) will be performed for the entire project.  This is done in order to ensure that the current performance measurement baseline remains up-to-date and consistent with the approved performance baseline parameters (TEC, completion date, etc.), and remains a reliable basis for budgeting, resource planning, and measurement of future performance. The NSTX Center-Stack Federal Project Director will prepare formal quarterly project reports to OFES with input from the PPPL NSTX CS Project Manager. Monthly Project Control System (PCS) status will be provided to the NSTX Federal Project Director, which will include all standard Earned Value Management System (EVMS) indices as well as critical path analysis. The NSTX CS-Project Manager is responsible for briefing the Associate Director for Laboratory Engineering and Infrastructure, the PPPL Director, the PPPL Deputy Director of Operations.  The PPPL Director is responsible for briefing the Princeton University Dean for Research.

In addition the NSTX Project plans on assembling an Integrated Project Team, led by the Federal Project Director, comprised of members of both DOE and key members of the NSTX CS upgrade project organization that will report progress and issues on a monthly basis to the DOE Associate Director of Science for Fusion Energy Sciences (FES).

Appendix B:

Brief Background Description of the NSTX CS Project Engineering Managers

NSTX CS Upgrade Project Management Team is shown in the figure above.  The Project engineering management team members have decades of engineering and engieering management experience.  They are also the engineering managers and RLMs for the successful NSTX facility construction team.  They have beem also actively working on various fabrication upgrades project on NSTX since the construction of NSTX facilities in 1999.  A brief background of the NSTX Project Director, the CS Project Manager, Integration Engineering Manager and the Responsible Line Managers (RLMs) are provided below.

Associate Laboratory Director for Engineering and Infrastructure: Michael Williams – Mr. Michael Williams has 32 years of engineering and management experience at PPPL, with specific expertise in the design, construction and operation of world-class experimental fusion devices. Highlights of his career include the management of the NSTX engineering and construction, which was completed on budget and six weeks ahead of schedule. More recently, he oversaw the dismantlement and decontamination of the Tokamak Fusion Test Reactor (TFTR), which was completed on schedule and $3M under budget. Following recent project management deficiencies, Mr. Williams has been instrumental in developing methodical project management and risk management processes and tools to improve oversight of complex projects. He will leverage this experience and lessons learned to ensure all projects at PPPL are managed in a disciplined fashion to rigorous standards. His experience includes 10 years working on neutral beams, including development and operation of the TFTR Neutral Beam facility, which is still the largest neutral beam heating system (40 Million Watts). Invented “decel conditioning” for low power discharge cleaning of ion source accelerators. Discovered the need for capacitive compensation of resistive gradient grid networks, thus eliminating the requirement for arc modulators. Oversaw Radio Frequency (RF) heating and magnetic power systems at PPPL for 20 years, which support all the experiments. In 1991, became Head of the Engineering Department, responsible for all engineering functions at PPPL. Received multiple awards including: Outstanding Accomplishment Award from the American Nuclear Society Fusion Energy Division in 2000 and a DOE Certificate of Appreciation in 1999. His responsibilities were broadened to include facilities/infrastructure. From 1997, Mr. Williams was Deputy Division Head for NSTX, responsible for construction of the NSTX project on budget and 6 weeks ahead of schedule. Oversaw D&D of TFTR on time and $3M under budget. Received certificate of recognition for ISMS in 1999. Received award from the Institute of Electrical and Electronic Engineers Fusion Technology in 1993. Received Kaul Foundation Prize for Excellence in Plasma Physics Research and Technology Development from Princeton University, and the Excellence in Fusion Engineering Award from Fusion Power Associates in 1999.  Mr. Williams completed courses in project management in 1989 and 2004 and participated in a DOE Workshop on Project Management in 2006.

CS Project Manager:  Lawrence E. Dudek - Mr. Larry Dudek has over 25 years engineering experience in magnetic fusion energy research at Princeton Plasma Physics Laboratory (PPPL) and is currently Division Head of the Fabrication, Operations, and Maintenance Division in the Engineering and Infrastructure Department. While at PPPL, he made major contributions to the fabrication and assembly, and to engineering for neutral-beam heating, diagnostics, and deuterium-tritium (D-T) systems.  Mr. Dudek was assigned as National Compact Stellarator Experiment (NCSX) Construction Manager to oversee the component fabrication, Modular Coil Assembly, and Field Period Assembly.  As Construction Manager for the National Spherical Torus Experiment (NSTX) in 2001-02, he managed resources to successfully complete the planned maintenance and system upgrades (OH Coil Repair, Center-stack Divertor modification, Passive Plate modifications, Thomson Scattering installation and Center-stack Ceramic Break Upgrade) on schedule and within budget. He also developed a plan to modify the center-stack divertor flange without disassembly using in-situ machining techniques.  Mr. Dudek managed and supervised fabrication and installation of the tritium purification system for the Tokamak Fusion Test Reactor (TFTR). This cryogenic distillation system was built by the Canadian Fusion Fuels Technology Project and was the first major installation of a PPPL tritium system. It was also the first closed-cycle tritium fuel system used in a fusion reactor.  Mr. Dudek saved the project substantial disposal costs by redesigning the Laboratory's tritium shipping containers. The design was so well received that several other national laboratories have asked PPPL to fabricate the containers for them.  He designed, fabricated, and installed the Poloidal Rotation Diagnostic on TFTR. Specifications called for optical alignments greater than 1 part per 1000 in several degrees of freedom. When installed, the diagnostic exceeded these alignment and performance requirements and set state-of-the-art standards for this measurement. Mr. Dudek completed the installation of tritium-compatible HVAC modifications for TFTR. He developed methods to reduce modification costs by 20%. Mr. Dudek is author or co-author of over 30 published papers dealing with fusion process systems, diagnostics, operations, and fabrication methods. He received an MBA from Rider University in 1979 and a BSME from Lafayette College in 1975. He is a licensed Professional Engineer in the State of New Jersey. Mr. Dudek completed courses in project management in 1989 and 2004.

Engineering Integration Manager: Charles Neumeyer - Mr. Charles Neumeyer is a Registered Professional Engineer with 30 years of experience in advanced technology engineering and project management.  For the ITER Project Mr. Neumeyer is the WBS Manager for the Steady State Electric Power Network (SSEPN) and consultant to the ITER International Organization on the electrical power systems.  Since 1997 he has been serving as the Project Engineer for NSTX where he successfully managed the facility design and commissioning efforts.  Mr. Neumeyer started his fusion career at PPPL on TFTR in 1976, with the design, procurement, and commissioning of the AC/DC converter systems, and was eventually responsible for the operation of all power systems.  He was a member of the CIT/BPX design team.  He was manager of the Power Systems, Neutral Beams, and Central I&C Systems for the TPX Project.  During the ITER EDA he was the US Home Team Representative for the ITER Power Systems and a working member of the EDA team.  While at Raytheon Engineers & Constructors Mr. Neumeyer was involved in several projects including SSC.   In 2000 he received the PPPL Distinguished Engineering Fellow Award and in 2001 the New Jersey Society of Professional Engineers award for Engineer of the Year.  He is an elected member of the IEEE Nuclear Plasma Sciences Society AdCom and a member of the IEEE/USA Energy Policy Committee.  Mr. Neumeyer has been an invited participant in numerous high-level technical reviews worldwide. Mr. Neumeyer received BS in Electrical Engineering BS from University of Virginia and he is the author of numerous technical papers in the fields of fusion engineering.

Design RLM: Phil Heitzenroeder, Mr. Phil Heitzenroeder heads the Mechanical Engineering Division, which is part of the Engineering and Infrastructure Department and was the Engineering Manager and the Stellarator Design and Engineering Manager for the National Compact Stellarator experiment.  Prior to his current NCSX appointment, Mr. Heitzenroeder was the Deputy Project Engineering Manager for NCSX and the Technical Representative for the modular coil prototypes and the (18) “production” modular coil winding forms.  Mr. Heitzenroeder has held a variety of other managerial and technical positions during his 34 year career at PPPL including Acting Project Engineering Manager for the US ITER Project from July ’04- February ’06, FIRE Engineering Coordinator, TPX Vacuum Systems Manager, Project Engineer for TFTR Internal Support Structure/PF assembly, BPX Coil Design Coordinator, PBX-M PF Coil System Coordinator: Head of the PBX-M Engineering Branch, the Vacuum Branch, and the Coil Development Branch.  Mr. Heitzenroeder’s industrial experience includes 3 years at IBM and 1 year at Ingersoll-Rand Research.  Mr. Heitzenroeder received a BS degree in Mechanical Engineering from the New Jersey Institute of Technology. He also completed 23 credit hours of graduate courses in engineering at NJIT and Syracuse University.  He has authored or co-authored numerous papers on fusion technology, is a member and former Chair of the IEEE/NPSS Standing Committee on Fusion Technology, and an associate member of ASME.   Phil is a PPPL Distinguished Engineering Fellow, and the 2006 recipient of the Kaul Award.

CS Fabrication RLM: James H. Chrzanowski, - In his current position, Mr. Jim Chrzanowski is responsible for managing PPPL’s Central CADD Design Group and mechanical engineers involved with the hardware design of systems and components for fusion experiments. He was the job manager for the manufacturing of the NCSX Modular Coils and the Poloidal Field Coils. Jim also serves as Cognizant Torus Systems Engineer for the National Spherical Torus Experiment (NSTX). Prior to his NCSX assignment he served as Engineering Manager for the Decommissioning and Decontamination of the Tokamak Fusion Test Reactor (TFTR), completed on schedule and under budget in September 2002. From 1997 until 1999, Mr. Chrzanowski oversaw the design, cost/schedule, and fabrication of the tokamak components for NSTX. This included the coil systems, the vacuum vessel, and in-vessel plasma facing components.  In 1997-98, Mr. Chrzanowski supported the ITER vacuum-pressure impregnation (VPI) program by providing applicable TFTR VPI information and procedures, reviewing and participating in the preparation of ITER VPI procedures, taking part in technical planning meetings, and providing on-site support for the actual vacuum-pressure impregnation process. Mr. Chrzanowski has 33 years of engineering experience in magnetic fusion energy research. He worked on the design and fabrication of coils and bus systems for such machines as the NSTX, the Advanced Toroidal Facility (ATF) at the Oak Ridge National Laboratory (ORNL), TFTR, the S-1 Spheromak, the Princeton Beta Experiment, the Poloidal Divertor Experiment (PDX), and the Princeton Large Torus (PLT).  Mr. Chrzanowski received an AAS degree in Engineering Technology from Mercer Community College in 1969. In 1971 he was granted a BS degree in Industrial Engineering Technology from Southern Illinois University. He is the author or co-author of 16 papers relating to magnetic fusion engineering.

Construction RLM: Erik Perry - Mr. Erik Perry, who was the project manager for the very successful TFTR D&D Projectat PPPL (Princeton University Plasma Physics Laboratory), is the Construction Branch Head at PPPL.  After working at Lockheed Missiles and Space Company, he joined the staff at PPPL in 1977.  He has more than 33 years' experience in the design, fabrication, installation, and testing of large, one-of-a-kind, high-technology devices. This experience includes analytical and hands-on work, as well as management from the design through installation phases of a project. Mr. Perry was the Construction RLM for the NSTX facility project which was completed successfully on schedule and on budget in 1999.  He also managed the construction aspect of the subsequent NSTX upgrade projects. He made major contributions in the construction activities leading to deuterium-tritium operation on TFTR.  In 20002, Mr. Perry received the Kaul Award for "managing the Tokamak Fusion Test Reactor Decommissioning and Decontamination (D&D) Project, which was completed on schedule and under budget, as well as demonstrating that a large and complex fusion facility can be safety dismantled without significant radiological exposure to workers or harm to the environment."  Mr. Perry is a member of the American Society of Mechanical Engineers and of the American Nuclear Society, and a former member of the American Institute of Aeronautics and Astronautics.  He received a bachelor's degree in mechanical engineering from Cornell University in 1974, a master's degree in aerospace structures from the University of Michigan in 1975, and a certificate in management from Mercer County Community College in 1982.

Power Systems RLM: Raki Ramakrishnan - Mr. Raki Ramakrishnan is a Principal Engineer at PPPL.  Mr. Ramakrishnan has been working in the design of fission plants and fusion devices over the last 35 years and has extensive experience in the design, installation, testing and operation of these devices.  Mr. Ramakrishnan has been instrumental in designing and implementing several important improvements and upgrades in PPPL.  Mr. Ramakrishnan was the Electrical Power Systems Manager & NB Power System manager for NSTX for the design and construction phases, and the tasks were completed on schedule and within budget.  Mr. Ramakrishnan was the WBS4 (Electrical Power System) Manager for the design of National Compact Stellarator Experiment.  He came to PPPL to design the electrical system of TFTR as a consulting engineer with Ebasco Services, and performed the design of the AC system and part of the DC system of TFTR.  Prior to his joining the TFTR team, Mr. Ramakrishnan was an electrical engineer with Ebasco Services, and worked on the St. Lucie Nuclear Power Plant.  Mr. Ramakrishnan received his MSEE from Indian Institute of Technology at Roorkee (India). He also received the Certificate in Fusion Reactor Technology from Princeton University, and Master’s Degree in Engineering Management from NJIT.  He is a licensed Professional Engineer in New Jersey.  He is a member of IEEE, member of IEEE Power Conversion Committee, and Sigma Xi.  Mr. Ramakrishnan has published several papers on the electrical power systems of Fusion devices in SOFE.

Project Control Officer: Tom Egebo - Mr. Tom Egebo has over thirty years experience in project environment.  As NSTX Planning and Control Officer since 1996, he reports to the NSTX Project Director responsible for provision and coordination of administration and project support activities across the project.  Specific responsibilities include planning, budgeting, scheduling, cost control, project reporting and administration services required to accomplish NSTX project commitments while ensuring that project financial and budget practices are consistent in compliance with laboratory practices and procedures.  Mr. Egebo is experienced in all aspects of PPPL Business Operations and the requirements set forth in DOE O 413.3A with particular emphasis on Project Control aspects.  He has a hands on familiarity with industry scheduling software (PRIMAVERA) with proficiency in Earned Value Management Systems.  At PPPL (1984-present), Mr. Egebo has worked in a Project Control capacity on multiple projects from project initiation to closeout, ranging from scheduling/earned value trainee to project controls manager including NSTX, TPX, TFTR D-T Preparation, BPX, CIT, and TFTR Tokamak Flexibility Modifications. He has also participated as preparer and presenter in multiple DOE-SC Office of Project Assessment reviews, as well as supported Key Decision and ESAAB approval process. As an EBASCO Services Inc. Project Control Support Engineer (1978-1984), Mr. Egebo participated and supported the development and deployment of the companies first integrated computerized earned value system on the Limestone Electric Generating Station Project.  He has also worked on Shearon Harris Nuclear Facility and Washington Public Power Supply System Units 3&5 nuclear plants.  Mr. Egebo received the Bachelor of Engineering- Civil Engineering degree from City College of the City University of New York in 1978.

# Text boxes

Center-Stack

EF/RWM

Coils