WBS Element:  1						WBS Level 1

WBS Title:     NSTX Upgrade Project

Definition: 	An improved understanding of the Spherical Torus (ST) magnetic confinement configuration is needed to establish the physics basis for next-step ST facilities, broaden the scientific understanding of plasma confinement for ITER, and maintain U.S. world leadership in ST research capabilities. In particular, operation at higher magnetic field with reduced plasma collisionality is needed to extend the plasma physics understanding of the ST toward next-step ST facilities and ITER. Controllable fully-non-inductive current-drive will also contribute to assessing the ST as a  potentially cost-effective path to fusion energy.

The proposed upgrade capabilities entail a new center-stack and a second neutral beam heating system.  The purpose of these upgrades will be to expand the NSTX operational space and thereby the physics basis for the next-step ST facilities.

WBS Element:	1.1					WBS Level: 2

WBS Title:	Torus Systems

Definition:	The torus systems include all the systems and related elements within the boundary of the NSTX  support structure.  This WBS element includes the Plasma Facing Components (WBS 1.1), Vacuum Vessel & Support Structure (WBS 1.2), and Magnet Systems (WBS 1.3). The scope of the work contains engineering design, R&D, mockups, procurement activities, and component fabrication.

What is not included in this WBS element: All site preparation and assembly of the Torus Systems is included in WBS 8.1. All integrated system testing is included in WBS 7.3. The following third and fourth level WBS descriptions detail the areas not included.

Key interfaces with other systems are described in the third level WBS descriptions below.

WBS Element:	1.1.0				WBS Level: 3

WBS Title:	PROJECT INTEGRATED MODEL

Definition:	This WBS element includes development of a project integrated model and the associated analysis support of the overall NSTX Upgrade Project.

As a result of the NSTX upgrades, the NSTX global models and analyses will need to be updated. The updated global model will provide the basis for updating the analysis to qualify components and identify areas of the tokamak requiring further analysis. Identified plasma scenarios and power supply current limit analyses will be run in the global model and current sets that require further analysis will be identified. These analysis also serve to check the results of more detailed analyses.

The following is not included in this WBS:  With the exception of the modifications identified above, no additional modifications to the PFCs are anticipated.

Key interfaces are included between the Vacuum Vessel and  Support Structure (WBS 1.1.2), the Magnet Systems (WBS 1.1.2), the Neutral Beam Injection System (WBS 1.2.4), the Glow Discharge Cleaning System (WBS 1.3.5), Plasma Diagnostics (WBS 1.4.1), and the Central I&C Systems (WBS 1.6.1 and WBS 1.6.2)

WBS Element:	1.1.0.1				WBS Level: 4

WBS Title:	Overall NSTX Upgrade Project Analytical Support (Job 1000)

Definition:	This job provides analytical support for global models and analysis not presently identified. The global model analysis will be used to qualify components and identify areas of the tokamak requiring further analysis. Identified plasma scenarios and power supply current limit analyses will be run in the global model and current sets that require further analysis will be identified. These analysis also serve to check the results of more  detailed analyses.

WBS Element:	1.1.1				WBS Level: 3

WBS Title:	Plasma Facing Components

Definition:	The plasma facing components (PFCs) include all the systems and related elements that serve to protect the vacuum vessel from the charged particles and radiation flux from the plasma. These include the plasma facing tiles and mounting components, passive stabilizers, inner wall protection, divertor area strike plates, and local I&C. This element consists of the engineering design, analysis, procurement activities and component fabrication.

As a result of the NSTX upgrades, the PFCs will need to be redesigned in order to accommodate the higher heat loads due to the addition of the 2nd NBI.  The existing PFC structural design will also need to be modified to  accommodate the added wall and divertor armor, and the new center stack assembly.

The following is not included in this WBS:  With the exception of the modifications identified above, no additional modifications to the PFCs are anticipated.

Key interfaces are included between the Vacuum Vessel and  Support Structure (WBS 1.1.2), the Magnet Systems (WBS 1.1.2), the Neutral Beam Injection System (WBS 1.2.4), the Glow Discharge Cleaning System (WBS 1.3.5), Plasma Diagnostics (WBS 1.4.1), and the Central I&C Systems (WBS 1.6.1 and WBS 1.6.2)

WBS Element:	1.1.1.1				WBS Level: 4

WBS Title:	Center Stack – Plasma Facing Components (Job 1001)

Definition:	This job provides design and analyses to ensure that there is adequate thermal  coverage for the center stack via tiles. Design diagnostic housing and tile mounting schemes. The results of this design and analyses will be documented in reports, drawings, and/or a Sytems Design Description (SDD).

WBS Element:	1.1.1.2				WBS Level: 4

WBS Title:	Passive Plate Analyses and Upgrade Activities (Job 1002)

Definition:	This job continues analysis of the passive plates for disruption and thermal loads. CDR level calculations addressed in one of five disruptions. The remaining identified disruptions are to be completed during Preliminary Design. During  Final design, analysis updates are expected as a result of preliminary design evolution. Modest hardware upgrades are anticipated are anticipated as part of this task. Additions of accelerometers or other diagnostics to benchmark calculations with actual performance in NSTX are also anticipated.

WBS Element:	1.1.2				WBS Level: 3

WBS Title:	VACUUM VESSEL & SUPPORT STRUCTURE

Definition:	The vacuum vessel & support structure (VVSS) consists of the modified vacuum chamber that utilizes the upper and lower dome from the S-1 vacuum vessel, a new straight cylindrical section between the two domes, and ceramic insulator rings with bellows.  This WBS element also includes all ports and vacuum boundary closures and the torus support structure which provides the overall supporting mechanism for the torus components to the test cell floor.  This WBS element includes the engineering design, analysis, procurement activities and component fabrication.

The existing VVSS will need to be modified to accommodate the new center stack structure, including the umbrella structure and the new center stack support structure.

What is not included:  With the exception of the modifications identified above, no additional modifications to the outer PF coils are anticipated.

Key interfaces are included between the Plasma Facing Components (WBS 1.1), the Magnet Systems (WBS 1.3), the Vacuum Pumping System (WBS 3.1), Coolant Systems (WBS 3.2), Bakeout Heating System (WBS 3.3), Gas Delivery System (WBS 3.4), Glow Discharge Cleaning System (WBS 3.5),  and the Plasma Diagnostics (WBS 4.1).

WBS Element:	1.1.2.1				WBS Level: 4

WBS Title:	Center Stack Upgrade Structural Supports (Job 1200)

Definition:	This job includes the analytical  and Cad design of the support structures associated with the Magnet upgrade activities.  The scope includes the Outer TF supports; Outer PF supports; Centerstack support structure and the Umbrella structural modifications.  It also includes the procurement and fabrication of these structures, but does not include installation costs.

WBS Element:	1.1.3					WBS Level: 3

WBS Title:	Magnet Systems

Definition:	The magnet system consists of the outer Poloidal Field coils (PF#2-4), the outer TF coil legs, and the center stack The center stack contains the inner TF coil legs, the OH solenoid, the shaping coils, and the center stack casing. This WBS element includes the design, analysis, prototypes (as required), procurement activities and fabrication up to and including the coil leads.

The existing magnet systems will need to be modified to accommodate the new center stack structure, including modifications to the TF cooling systems; update of the center stack gas system; support modifications to the outer PF coils, outer TF coils, center stack shaping coils, the center stack casing; and the development of new TF inner leg interfaces to the center stack.

What is not included: With the exception of the modifications identified in the following fourth level WBS descriptions, no additional modifications to the magnet systems are anticipated.

Key interfaces with other systems are described in the fourth level WBS descriptions below.

WBS Element:	1.1.3.0				WBS Level: 4

WBS Title:	Center Stack Upgrade Project Design Support (Job 1300)

Definition:	This job provides CAD design support for the overall assembly drawings associated with the CS upgrades.  CAD design support for individual components is included in the specific component jobs.

It also includes some time for space allocation studies associated with the magnet upgrades.

WBS Element:	1.1.3.1				WBS Level: 4

WBS Title:	Outer Poloidal Field Coils (PF #3-5)

Definition:	The outer Poloidal Field coils (PF 3-5) are not being upgraded as part of the NSTX Upgrade Project scope.

WBS Element:	1.1.3.2				WBS Level: 4

WBS Title:	Outer Toroidal Field Coils

Definition:	The outer Toroidal Field coils subsystem consists of the coil sections that make up the TF outer legs. For the NSTX Upgrade Project, modifications will be needed to the TF outer leg support structure and outer TF cooling tube routings will be needed to accommodate the new center stack. This WBS elements includes the design, analysis, prototypes (as required), procurement activities and fabrication.

What is not included: With the exception of the modifications identified above, no additional modifications to the outer TF coils are anticipated.

Key interfaces with other systems:  For the NSTX Upgrade Project, as a result of the redesigned TF outer leg support structure and TF cooling tube routings, interfaces with the VV umbrella structure (WBS 1.1.2), the interfacing bus work with the Outer TF coils (WBS 1.1.3.3.1), and the routing of the cooling tubes (WBS 1.3.2) will need to be defined.

WBS Element:	1.1.3.2.1				WBS Level: 5

WBS Title:	Outer Toroidal Field Coils (Job 1301)

Definition:	This job includes the fabrication of (2) new Outer TF coils (OTF) to replace the existing [leaking] OTF#7 and #11 in NSTX.  The scope includes the procurement of conductor, insulations, aluminum castings and supports necessary to fabricate a new OTF coil.  Coil fabrication will be performed in-house.  This scope does not include costs associated with installation into NSTX (Covered in WBS 1.8.2 – Job 8200).

WBS Element:	1.1.3.3				WBS Level: 4

WBS Title:	Center Stack Assembly (PF1/PF2 Upper and Lower)

Definition:	The entire Center Stack Assembly (CSA) shall be removed from the existing NSTX device and replaced with a new design as part of the NSTX Upgrade Project.  The following other components will need to be removed to provide access and/or replaced:

- Toroidal Field (TF) inner leg bundle will design new TF inner leg bundle and busswork – the interfaces with the new Center Stack will have to be replaced with new designs.

- Ohmic Heating (OH) solenoid – a new design will replace the existing coil.

- Center Stack Sensors, including the Rogowski Coils, the Mirnov Coils, the Flux Loops, the Langmuir Probes, and the Thermocouples. Will need to re-install new center stack sensors.

- Poloidal Field (PF) coils PF1A Upper, PF1A Lower, and PF1B – will need to be removed new designs of the PF1A and PF1B coils will be installed.

- Microtherm insulation and the Center Stack Casing (CSC) – will need to re-designed and installed.

- Plasma Facing Components (PFC) associated with CSC including the Inboard Divertor (IBD) – will need to removed from the old center stack and then re-installed with new PFC tiles.

- Pedestal which supports Center Stack Assembly from floor – will need a new design to accommodate the larger center stack.

This WBS elements includes the design, analysis, prototypes (as required), procurement activities and fabrication.

What is not included: As a result of the entirely new center stack assembly and associated supports, there is nothing that is excluded.

Key interfaces with other systems:  For the NSTX Upgrade Project, as a result of the entirely new center stack assembly, interfaces with the surrounding other magnet system WBS elements are anticipated and will need to be defined. In addition, there may also be interfaces with the following other WBS elements:  Plasma Facing Components (WBS 1.1.1.1), the Auxiliary Systems (WBS 1.3), Plasma Diagnostics (WBS 1.4), and the  Power Systems (WBS 1.5. More detailed identification of specific interfaces is described in the following WBS Level 5 elements.

WBS Element:	1.1.3.3.0				WBS Level: 5

WBS Title:	Center Stack Assembly (Job 1302)

Definition:	This job includes the activities associated with the assembly of the new centerstack.  It does not include the mounting of the first wall tiles (Covered in WBS 1.1.1 – Job 1001), installation of the new diagnostics [covered in WBS -  Job 4100], or  the installation of the CS into the NSTX (Covered in WBS 1.8.2 – Job 8200).

Details include the:

- Set up and tear down of  CS assembly area in the NCSX Test Cell;

- Design modifications and upgrade of coil assembly stand. [Note: CS lift fixture covered in WBS 1.8.2 – Job 8200;

- Assembly of CS components including OH/TF coils and supports, mounting of OH surface diagnostic and thermal blanket; Inconel casing and inner PF1A and 1B coils; and.

- Generating the  procedures for assembly of Center Stack and for installation into NSTX.

WBS Element:	1.1.3.3.1				WBS Level: 5

WBS Title:	Center Stack - TF Inner Legs

Definition:	The TF inner leg subsystem consists of the new coil sections that will make up the TF inner bore and bundle.  For the NSTX Upgrade Project, a new TF inner bundle  and the CS-TF joint and supporting details (e.g., insulation, cooling, etc) will be to be designed, fabricated, and installed. As a result, revised interfacing busswork between the inner and outer FT coils will have to be designed and fabricated.  Additionally, the inner TF coils cooling tubes will need to be rerouted.  This WBS elements includes the design, analysis, prototypes (as required), procurement activities and fabrication.

What is not included: As a result of the entirely new TF bundle assembly and associated supports, there is nothing that is excluded.

Key interfaces with other systems:  For the NSTX Upgrade Project, new interfaces with the VV umbrella (WBS 1.1.2), the interface busswork between this WBS element and the Outer TF Coils (WBS 1.1.3.2), and the Cooling System (WBS 1.3.2).

WBS Element:	1.1.3.3.1.1				WBS Level: 6

WBS Title:	Outer TF Joint Test Stand & Performance of Test (Job 1303)

Definition:	This job includes design and fabrication of a test stand to measure the required performance parameters on the new NSTX TF joint design.  It also include performing test parameter measurements and cyclic lifetime tests as required.  Testing data will be compiles and reported.  The test stand configuration will be modified as needed for revised design configurations and the tests will be repeated as needed.  A comprehensive final test report will be developed that includes all test data.

WBS Element:	1.1.3.3.1.2				WBS Level: 6

WBS Title:	InnerTF Bundle – Design and Fabrication (Job 1304)

Definition:	This job includes the design of the TF bundle, TF flex bus, and flex bus supports – including all analytical & CAD design efforts for these components and the the early procurement of the TF conductor [80 lengths].  The procurement of the  procurement of the TF flex bus and supports.   The scope does not include the procurement of the Inner TF bundle (Covered in WBS 1.1.3.3.2 – Job 1305).  This is included as part of the OH procurement in Job 1305.

WBS Element:	1.1.3.3.2				WBS Level: 5

WBS Title:	Center Stack - Ohmic Heating Solenoid (Job 1305)

Definition:	For the NSTX Upgrade project, an entirely new OH solenoid will be designed, fabricated, and installed. It is anticipated that a new cooling system will be required as a result of this new design as well as an upgraded cooling system.  This WBS elements includes the design, analysis, prototypes (as required), procurement activities and fabrication.

This job includes the design & fabricate a new OH solenoid and associated components including a belleville washer spring assy. and support structures for the NSTX upgrades.  Estimate includes all analytical & Cad design efforts. Includes advance procurement of the copper conductor and co-wound [glass/Kapton] insulation.  Also includes the procurement of the Micro-therm insulation, conductive paint.

Includes the procurement and engineering oversite for the combined OH and TF bundle assembly.  Single vendor shall fabricate both components.    Does not include any installation or assembly tasks.

What is not included: The installation and assembly tasks into NSTX are not included (Covered in WBS 1.8.2 – Job 8200).

Key interfaces with other systems:  For the NSTX Upgrade Project, the new OH solenoid will have new interfaces with other center stack assembly WBS elements, the Cooling System (WBS 1.3.2), and the Power Systems (WBS 1.5.0).

WBS Element:	1.1.3.3.3				WBS Level: 5

WBS Title:	Shaping Coils/Inner PF Coils Design and Fabrication (Job 1306)

Definition:	The NSTX Upgrade Project requires  new shaping coils (PF1A and PF1B). This WBS element includes the design, analysis, prototypes (as required), procurement activities and fabrication.

This job includes the design and procurement of the Inner poloidal field coils and supports [PF1A and PF1B].  Includes all analytical & CAD design efforts for these components.   The scope includes the early procurement of the PF conductor and Co-wound [Glass/Kapton] insulation,  the procurement of the PF support mandrels that the PF1A and 1B coils will be wound onto, and the fabrication of three new upper and lower sets of inner PF coils (PF1A, 1B and 1C).

What is not included: The installation and assembly tasks into NSTX are not included (Covered in WBS 1.8.2 – Job 8200).

.

Key interfaces with other systems:  For the NSTX Upgrade Project, the new shaping coils will have new interfaces with other center stack assembly WBS elements, the Cooling System (WBS 1.3.2), and the Power Systems (WBS 1.5.0).

WBS Element:	1.1.3.3.4				WBS Level: 5

WBS Title:	Center Stack Casing Design and Fabrication (Job 1307)

Definition:	The NSTX Upgrade Project will require an entirely new center stack casing assembly.  This WBS element includes the design, analysis, prototypes (as required), procurement activities and fabrication.

This job includes the design and fabrication of the Center Stack casing and ceramic break assembly for the upgraded NSTX Center Stack Upgrade Project.   Scope includes:

- All analysis and CAD design for these components;

- Procurement of the Inconel tubing, forgings, bellows and organ pipes;

- Thee fabrication of CS support legs;

- The procurement/fabrication of a new ceramic break assembly;

- The in-house assembly of the casing components; and

- The mounting of the PF1A and PF1B structure/coils to the casing.

What is not included: The installation and assembly tasks into NSTX are not included (Covered in WBS 1.8.2 – Job 8200).

Key interfaces with other systems:  For the NSTX Upgrade Project, the new new center stack casing assembly will have new interfaces with other center stack assembly WBS elements, the PFCs (WBS 1.1.1.1), the Diagnostic Systems  (WBS 1.4.1), and the Gas Delivery System (WBS 1.3.4).

WBS Element:	1.2					WBS Level: 2

WBS Title:	Plasma Heating And Current Drive Systems

Definition:	The heating and current drive systems include all the auxiliary plasma heating and current drive systems required for first day operation. This WBS element includes the High Harmonic Fast Wave (HHFW) Current Drive System, the Coaxial Helicity Injection (CHI) Current Drive System, the Electron Cyclotron Heating (ECH) System, and the Neutral Beam Injection (NBI) System.  Of all of these, only the ECH (WBS 1.2.3) and Neutral Beam Injection (WBS 1.2.4) are needed for day one operation – all others are exclude from the NSTX Upgrade Project.  The scope of the work contains engineering design, R&D, mockups, procurement activities, component fabrication, installation, and System Testing.  Installation of the WBS 2 systems is included in the individual WBS 2, level 3 elements.

WBS Element:	1.2.1				WBS Level: 3

WBS Title:	High Harmonic Fast Wave/HHFW

Definition:	The High Harmonic Fast Wave System provides radio frequency (rf) energy to the plasma for the purpose of plasma heating and current drive.  The components of such a system include generators, transmission lines, tuning systems, antennas and their associated diagnostic and control systems.  The system includes components inside the vacuum vessel (antennas and feed-throughs) in the test cell (transmission and tuning components) and in the RF power rooms (AC/DC power conversion system, RF generators, switches and loads).

The HHFW System is not included in the scope of the NSTX Upgrade Project.

WBS Element:	1.2.2				WBS Level: 3

WBS Title:	Coaxial Helicity Injection/CHI Current Drive

Definition:	The Coaxial Helicity Injection System is to provide helicity injection to aid startup and provide edge current profile control.  The main hardware elements required fall under other WBS's.  These include a ceramic break in the vacuum vessel (WBS 12), the poloidal coil system (WBS 13) and a power supply (WBS 54).  In this WBS element the task is to assure that the various components of the system are compatible with helicity injection and that the Central I&C required is provided.

The CHI System is not included in the scope of the NSTX Upgrade Project.

WBS Element:	1.2.3				WBS Level: 3

WBS Title:	Electron  Cyclotron Heating/ECH (Job 2300)

Definition:	The Electron Cyclotron Heating System provides breakdown and startup assist through an electron cyclotron heating system.  The system will be composed of an AC/DC power conversion system, gyrotron source, transmission system, vacuum window and launcher.  Any ECH specific diagnostics will be included and interfaced to Central I&C.

This job includes This Task covers the ECH and other antenna systems, and miscellaneous diagnostics and components attached to the vessel which will be effected by the increases in EM and thermal loading. Disruption loads on the ECH waveguide will be evaluated for the Center Stack Upgrade Fields and field transients. Discussions with heating system experts regarding the performance of the ECH system for the higher CSU fields indicate that no modification to the resonant frequency or other operational characteristic for the system will require upgrade. Only disruption qualification is planned.  No previous qualification has been identified, so the resources include creation of a new calculation is required.

WBS Element:	1.2.4				WBS Level: 3

WBS Title:	Neutral Beam Injection/NBI

Definition:	The Neutral Beam Injection System Upgrade provides a second Neutral Beam as part of the NSTX Upgrade Project.  The second NBI is identical to the one already installed on NSTX.  An existing TFTR beam will be decontaminated, refurbished, and installed on NSTX.

The NSTX Upgrade Project shall include the following jobs:

- NBI Project Support and Administration (Job 2410)

- Upgrading Sources (Job 2420)

- Decontamination of a TFTR Beam (Job 2430)

- Refurbishment of the TFTR Beamline (Job 2440)

- Relocation of the Refurbished Beamline (Job 2450)

- Associated Support Services (Job 2460)

- NBI Upgrade Power Systems (Job 2470)

- NBI Upgrade Controls (Job 2475)

- NBI Upgrade Nozzle and Ducts (Job 2480)

- NBI Relocations (Job 2490)

WBS Element:	1.2.4.1				WBS Level: 4

WBS Title:	NBI Project Support & Integration

Definition:	This work scope is  included in WBS 1.7.3 (Job 7300).

WBS Element:	1.2.4.2				WBS Level: 4

WBS Title:	NBI Sources Refurbishment (Job 2420)

Definition:	This job includes the activities to  refurbish three neutral beam ion sources for BL2 just as we currently do for the installed BL1. The refurbishment tasks will follow established procedures that have been utilized for both TFTR and NSTX.

WBS Element:	1.2.4.3				WBS Level: 4

WBS Title:	NBI Beamline 2 Decontamination (Job 2430)

Definition:	This job includes the disassembly and decontamination activities of a TFTR Neutral Beam beamline in preparation for beamline refurbishment and reuse as an NSTX upgrade.

WBS Element:	1.2.4.4				WBS Level: 4

WBS Title:	NBI Beamline Refurbishment and Relocation

Definition:	This WBS element includes refurbishment of a TFTR NBI and its relocation to the NSTX test cell.

WBS Element:	1.2.4.4.1				WBS Level: 5

WBS Title:	NBI Beamline 2 Refurbishment (Job 2440)

Definition:	This job includes the activities necessary to refurbish a TFTR Neutral Beam beamline for use on NSTX. This scope includes replacing copper impinged parts as required and refurbishment of the seals, Theremocouple wiring, and bellows (cal and spool) as needed.

WBS Element:	1.2.4.4.2				WBS Level: 5

WBS Title:	NBI Beamline 2 Relocation (Job 2425)

Definition:	This job includes the efforts to relocate the  neutral beam beam line and ancillary equipment into NSTX test cell.  This includes HVEs and complete beam box.

WBS Element:	1.2.4.5				WBS Level: 4

WBS Title:	NBI Beamline 2 Services (Job 2450)

Definition:	This job includes the efforts to provide services to the new neutral beam beamline and ancillary equipment in NSTX test cell. These services  include cooling water, cryogenic systems, gas supplies, and vacuum lines.

WBS Element:	1.2.4.6				WBS Level: 4

WBS Title:	NBI Armor/Protective Plate  Upgrade (Job 2460)

Definition:	This job includes the design, fabrication, and installation of upgraded and relocated neutral beam armor including cooling and instrumentation work.

WBS Element:	1.2.4.7				WBS Level: 4

WBS Title:	NBI Beamline 2 Power and Controls

Definition:	This work scope includes providing power and controls for the NBI beamline 2.

WBS Element:	1.2.4.7.1				WBS Level: 5

WBS Title:	NBI Beamline 2 Power Upgrade (Job 2470)

Definition:	This job includes providing power for the NBI beamline 2. NB2 is planned to be powered from the TFTR NB4 A,B, & C line ups.  The electrical equipment in these line ups will be reactivated. The TFTR NB4 HVEs will be relocated to the NSTX Test Cell. New triax cables will be installed with terminations from the Modregs to the HVEs. New  Decel coaxial cables will be installed from the Decel supplies to the Sources. The Arc, Filament,  Magnet , and the 208 feeds, to HVEs cables, will be spliced in the TFTR Test Cell basement to new cabling designed and installed from the TFTR Basement to the NSTX Test Cell. The fiber cables also will be spliced with additional lengths recovered from other TFTR line ups. The AC auxiliaries and Grounding for the NB2 will be designed and installed.

WBS Element:	1.2.4.7.2				WBS Level: 5

WBS Title:	NBI Beamline 2 Controls Upgrade (Job 2475)

Definition:	This job includes upgrade of  the controls and instrumentation for the NB2. The work covers PLC, programming, control racks, new thermocouples, TC scanner, miscellaneous controls, and control cabling. The work also includes the gradient grid upgrade. System integration and testing will be performed.

WBS Element:	1.2.4.8				WBS Level: 4

WBS Title:	NBI Beamline 2 Duct and Vacuum Vessel Modifications (Job 2480)

Definition:	This job includes the design, and fabrication of all components connecting NB Box to NSTX, the connecting ductwork and modifications to NSTX Vacuum Vessel to accommodate the second beamline.

WBS Element:	1.2.4.9				WBS Level: 4

WBS Title:	NBI Beamline 2 Equipment Relocations (Job 2490)

Definition:	This job covers the move of racks and diagnostics to clear space in the NSTX Test Cell for the second Neutral Beamline.  The racks to be removed and re-installed in a new location are #419, 431-435, 440-445, 447-449, 488.  Racks 456 and 489 will be removed and excessed.  This scope also includes the fabrication and installation of five sections of platform at elevation 118' on the west side of the NTC to accommodate the racks being re-installed in the Test Cell.  Racks #441-445 will be relocated to the Gallery east of the NTC.  Diagnostics to be removed are those from the midplanes of Bay J and Bay K as well as those on the present pump duct.  The diagnostics from Bay J will be re-installed ~5" outboard of their present position.  IR windows and the Transmission Grating Spectrometer will be relocated to the new NB duct.  Ion gages, filaments and the RGA will be relocated to the new pump duct under the NB2 duct.  SPRED and LOWEUS will be relocated to Bay L.  The Thompson Scattering Beam Dump Window will be relocated to between Bays K and L.

WBS Element:	1.3					WBS Level: 2

WBS Title:	Auxiliary Systems

Definition:	The auxiliary systems include all the mechanical non-torus support systems for NSTX.  This WBS  element includes the Vacuum Pumping System, the Coolant Systems, the Bakeout Heating System, Gas Delivery System and the Glow Discharge Cleaning System. The scope of the work contains engineering design, R&D, mockups, procurement activities, component fabrication, and  System Testing.  Installation of the WBS 3 systems is included in the individual WBS 3, level 3 elements.

WBS Element:	1.3.1				WBS Level: 3

WBS Title:	Vacuum Pumping System (Job 2485)

Definition:	The Vacuum Pumping System provides the source and distribution of all vacuum pumping to NSTX.  This includes the roughing pumps as well as the turbo pumps and any backing pumps to:

- Provide the initial high vacuum environment with minimum impurities for plasma formation;

- Evacuate the spent plasma constituents at the end of each pulse prior to the next plasma pulse;

- Remove impurities liberated during bakeout and/or discharge cleaning of the vacuum vessel interior; and

- Provide instrumentation and a Residual Gas Analyzer.

This WBS element also includes the controllers for all pumps and any baffles for backstreaming.  This job includes the design, fabrication, and installation of a new Vessel Pumping System.  The job scope includes new pump ducts off of NB2 duct, mechanical and electrical isolation of the system, vacuum diagnostic relocation, magnetic shielding and support of TVPS TMPs, and TMP service connections.

WBS Element:	1.3.2				WBS Level: 3

WBS Title:	Water Coolant Systems Modifications for CSU(Job 3200)

Definition:	The NSTX Upgrade project will provide water cooling services to the new center stack and ancillary equipment in NSTX test cell.

WBS Element:	1.3.3				WBS Level: 3

WBS Title:	Bakeout Heating System Modifications for CSU

Definition:	This job includes purchase of a new power supply for the bakeout heating system that will be  used for the electrical heating of the vessel. It is proposed to buy a 0-8V, 8000 amps for the application.  Suitable cable leads will be fabricated and necessary interlocks will be incorporated.

WBS Element:	1.3.4			WBS Level: 3

WBS Title:	Gas Delivery Systems Modifications for CSU (Job 3400)

Definition:	This job includes the Design, fabricate, install and test two center stack fueling lines and modify gas delivery assemblies.

WBS Element:	1.3.5				WBS Level: 3

WBS Title:	Glow Discharge Cleaning System Modifications

Definition:	GDC CHI System is not included in the scope of the NSTX Upgrade Project.

WBS Element:	1.4					WBS Level: 2

WBS Title:	Plasma Diagnostics

Definition:	The Plasma Diagnostics provide information on discharge parameters to characterize NSTX plasmas and guide its operation for optimized performance.  The near term emphasis will be on detailed measurements of plasma profiles, using equipment presently available at PPPL. The long term objective will be to provide input for advanced plasma control systems, using new concepts and systems developed by the national NSTX team. Installation of the WBS 4 systems is included in the individual WBS 4, level 3 elements.

WBS Element:	1.4.1				WBS Level: 3

WBS Title:	Center Stack Diagnostics  Upgrades for CSU (Job 4100)

Definition:	For the NSTX Upgrade Project only the diagnostics associated with the Center Stack Upgrade will be upgraded. The scope includes the design and fabrications of CS magnetics diagnostics to replace units removed with old center stack.

The current NSTX diagnostic suite is adequate to accommodate and monitor the NSTX beamline 2.

WBS Element:	1.5					WBS Level: 2

WBS Title:	Power Systems

Definition:	The Power Systems include all the systems and related elements that provide conditioned electrical power and energy to the NSTX systems.  This WBS element consists of the AC Power Systems, the TF Power Conversion System, the PF/OH Power Conversion System, the CHI Power Conversion System, the General Power Systems and Integration activities, and the Coil Bus Runs.  All equipment, including local  instrumentation and control, is included. Installation of the WBS 1.5 systems is included in the individual WBS 1.5, level 3 elements.

WBS Element:	1.5.0				WBS Level: 3

WBS Title:	Center Stack Upgrade Power Supplies (Job 5500)

Definition:	This job includes  The Center stack upgrade entails the TF feed to be 1kV, 129.8kA for 7.45 seconds every 2400 seconds. Design shall be such that the pulse period can be reduced to 1200 seconds. This requires complete redesign of the TF power system. Replacement of the fault detector (FD) and the Firing generator (FG) is required for fast and reliable response to fault conditions. The HCS will be upgraded with a PLC. The OH power supply will be also redesigned to have the capabiity of 8kV, +/-24kA; the FD and FG of the OH system will also be changed. OH CLRs will be replaced with calculated optimum requirements.

WBS Element:	1.5.1				WBS Level: 3

WBS Title:	AC Power Systems

Definition:	This scope is covered in WBS 1.5.0 (Job 5500).

WBS Element:	1.5.2				WBS Level: 3

WBS Title:	TF Power Conversion System

Definition:	This scope is covered in WBS 1.5.0 (Job 5500).

WBS Element:	1.5.3				WBS Level: 3

WBS Title:	PF/OH Power Conversion System (Job 5300)

Definition:	This scope is covered in WBS 1.5.0 (Job 5500).

WBS Element:	1.5.4				WBS Level: 3

WBS Title:	CHI Power Conversion System

Definition:	There are no modifications to this system resulting from the Center Stack Upgrade.

WBS Element:	1.5.5				WBS Level: 3

WBS Title: 	General Power Systems and Integration

Definition:	There are no modifications to this system resulting from the Center Stack Upgrade.

WBS Element:	1.5.6				WBS Level: 3

WBS Title: 	Coil Bus Runs (Job 5501)

Definition:	This job includes design and fabrication of bus runs/supports between the NSTX coils and the FCPC cable terminations located in the NSTX test cell west side.  The scope includes new air-cooled TF bus; relocation of OH cable bus from top to bottom of machine; new CHI ring bus and bus links to lower VV; and new bus for the inner PF coils.  The scope does not include installation costs (Covered in WBS 1.8.2 – Job 8200).

WBS Element:	1.6					WBS Level: 2

WBS Title:	NSTX Central Instrumentation and Control 		(I&C)

Definition:	The scope of this WBS element is to develop a Central Instrumentation and Control (I&C) System that will provide remote control, monitoring, data acquisition and data management for the NSTX subsystems during machine operation.  The Central I&C System will be developed, to varying degrees, in conjunction with all other WBS elements and will consist of two major elements: the Control System and the Data Acquisition System.  Local I&C system controllers, field instrumentation and wiring are included in the individual subsystems.

WBS Element:	1.6.0				WBS Level: 3

WBS Title:	Control  and Data Acquisition Upgrade Systems (Job 6100)

Definition:	This upgrade will be capable of producing plasmas on the order of 10 seconds; to-date they are less than two seconds. For dozens of CAMAC and PC-based data acquisition systems this will require an upgrade, and in some cases replacement.  The real-time plasma control system may require an upgrade to accommodate additional input/output signals, control loops, and a longer control period.   The networks,  back-end compute servers, and data storage systems will need be upgraded to achieve reasonable performance for time-sensitive functions. Some test cell racks will be relocated; there will be a modest effort required to route the control, timing, and communication cabling and qualify the systems.

WBS Element:	1.6.1				WBS Level: 3

WBS Title:	Control Systems)

Definition:	The scope of the upgrades are covered in WBS 1.6.0 (Job 6100).

WBS Element:	1.6.2				WBS Level: 3

WBS Title:	Data Acquistion Systems)

Definition:	The scope of the upgrades are covered in WBS 1.6.0 (Job 6100).

WBS Element:	1.7					WBS Level: 2

WBS Title:	Project Support And Integration

Definition:	Project support and integration includes the non-hardware related subsystems such as overall Project Management and Administration, Center Stack Upgrade and NBI Upgrade management, Health Physics Support, Direct Allocations, and Integrated Systems Testing.

WBS Element:	1.7.1				WBS Level: 3

WBS Title:	Project Management And Integration (Job 7100)

Definition:	The project management and integration WBS element consists of all the activities necessary to plan, monitor, integrate and control, and report on the progress of the NSTX Upgrade Project for the addition of a second neutral beam on NSTX and the design, fabrication and installation of a new centerstack as well as upgrades to coil structures to support the new loads.  Also included is the updating of the General Arrangement Drawings for the NSTX Test Cell and funds for independent reviewers.

This WBS includes technical, business, and administrative planning and support; organizing, directing, coordinating, controlling, reviewing and approving project actions; implementation and operation of the Project Control System (PCS); data and information collection, reproduction, distribution, and storage; reports; and all of the activities associated with integrating the design of the various subsystems, including plasma position control that involves several subsystems.

WBS Element:	1.7.2				WBS Level: 3

WBS Title:	Center Stack Upgrade Management (Job 7200)

Definition:	Primarily LOE job to cover the oversight of CSU work and to cover engineers time for project cost and schedule reviews.

WBS Element:	1.7.3				WBS Level: 3

WBS Title:	Neutral Beam Upgrade Management (Job 7300)

Definition:	Management and engineering oversight of NBI upgrade through FY2013. Job includes engineer preparation for reviews every 6 months.

WBS Element:	1.7.4				WBS Level: 3

WBS Title:	Health Physics Support (Job 7400)

Definition:	This job includes continuous health physics support of the beamline decontamination, refurbishment, and relocation. require continuous HP support. This job covers time for two HPs, overtime, and minor sundries for HP ops for FY 10,11,12. Two HPs are required to cover surveys, regulatory compliance documentation, procedures, and RWPs. Two HPs are required during every decontamintation evolution where one individual is suited up in PCs inside the RWP area and one is outside providing support and running smears. HP is also required to process cleaned items for release. FY09 Decon Ops experience has demonstrated the need for 2 HPs.

In addition, equipment Removal/Relocation (WBS 1.2.4.5 - Job 2425) requires one HP support during the removal of equipment.

WBS Element:	1.7.5				WBS Level: 3

WBS Title:	Allocations

Definition:	This WBS element includes the direct allocations and the upgrade allocations.  PPPL collects direct allocation costs charged to the NSTX Upgrade Project and Program.  These include Job 7700 and 7710. There are two components associated with the Direct Allocation charges:

- Health physics sampling, data analysis and maintenance of the PPPL Environmental, Analytical, and Radiological Laboratory (PEARL); and

- Direct allocation charges are to cover the allocated charges for the Computer Division's support and maintenance of the Laboratory computer systems, desktop computer support at PPPL, diagnostic and RF development activities at PPPL.

The portion of the direct allocation budget applied to the NSTX Up project is calculated and controlled by the PPPL budget office as a function of the research, analyst, and health physics personnel budgeted to the project.

WBS Element:	1.7.1.1				WBS Level: 4

WBS Title:	Health Physics Direct Allocations (Job 7700)

Definition:	These are the direct allocation charges associated with health physics sampling, data analysis and maintenance of the PPPL Environmental, Analytical, and Radiological Laboratory (PEARL).

WBS Element:	1.7.1.2				WBS Level: 4

WBS Title:	Other Direct Allocations (Job 7710)

Definition:	These are the direct allocations charges associated with the allocated charges for the Computer Division's support and maintenance of the Laboratory computer systems, desktop computer support at PPPL, diagnostic and RF development activities at PPPL.

WBS Element:	1.7.6				WBS Level: 3

WBS Title:	Integrated Systems Tests

Definition:	This element includes all of the activities associated with the support of development of all necessary procedures and documents to support the integrated tests, and to support performance of the pre-operational integrated system tests culminating in first plasma.

Major activities will include:

- Convening the NSTX Activity Certification Committee (ACC) for comprehensive review of NBI-2 and the new Center Stack upgrade. Prepare and make presentation to the PPPL ES&H Executive Safety Board for issuance of appropriate Safety Certificate parameters for operation of NSTX with new enhanced operating capabilities.

- Preparation of documentation (procedures)  for safely integrating NBI-2 and the new center stack for operations within NSTX safe operating parameters.

- Working with NSTX Operations Group for the successful intergration of NBI-2 and new CS sub-systems.

- Participate in cost & schedueling reviews. Report on progress as required.

WBS Element:	1.8					WBS Level: 2

WBS Title:	Site Preparation and Torus Installation

Definition:	Site preparation and torus assembly includes modifications to the existing D-site Hot-Cell components and subsystems and the assembly and installation of all Torus Systems (WBS 1.1).  Modifications to other PPPL facilities, components, and subsystems outside the D-site Hot-Cell and the assembly and installation of non-torus components and subsystems are included in the individual  components and subsystems.

WBS Element:	1.8.1				WBS Level: 3

WBS Title:	Site Preparation (Job 8100)

Definition:	General site preparation activities are not included in the scope of the NSTX Upgrade Project.  Whatever site preparation activities are covered in WBS 1.8.2 (Jobs 8200 and 8250)

WBS Element:	1.8.2				WBS Level: 3

WBS Title:	Center Stack and Coil Structure Installation

Definition:	This WBS element includes the removing the  old centerstack and installing new one, including any coil support modifications.  Other activities will include closing the vacuum vessel, conducting pumpdown and leakchecks, and bakeout and scrub to ensure  that NSTX is ready to start ISTPs. It also includes the Construction Management oversight activities.

Installation of the new control room components is included in Central I&C (WBS 61).  Subsystem testing and integrated system testing are covered in other WBS elements.

WBS Element:	1.8.2.1				WBS Level: 4

WBS Title:	Installation of Center Stack and Coil Support System (Job 8200)

Definition:	This job includes The scope of this job includes the PF and TF support upgrade.  This involves removing diagnostic equipement for clearance and accessibility, moving the existing PF coils, cutting off existing supports mounted on the vessel and installing a new external cage support system.

WBS Element:	1.8.2.2				WBS Level: 4

WBS Title:	Center Stack Removal & RE-Installation, Pumpdown, and Bakeout

(Job 8250

Definition:	The job includes the removal of the existing centerstack and installation of the upgraded centerstack.  This also includes the vessel closing, pumpdown and leak check, bakeout and scrub so that NSTX is ready to start ISTPs.