## Sheet1
NSTX Calculation Log
Line # |  | Calc Title | Preparer | COG | Preparation % Complete | Schedule Date (COG) | Forecast Date (Preparer) | Calc # | Bob S. Comments on Calc | Preparer Sign date | Reviewer | Review % Complete | Reviewer Sign date | WBS | Job # (WAF) | Act ID | Comments
WBS 10 - Torus Systems
1 |  | Global Model | P. Titus | Titus | 60 | 2011-01-17 |  | NSTXU-CALC-10-01-02 |  |  | Group |  |  | 1.1.1 | 1000 | 0011 | Replaces Calc-13-01-01
2 |  | Torques to Lids and TF Teeth | P. Titus | Smith | 75 | 2011-03-08 |  | Will be part of Rev 3 to the above calc |  |  | A.Zolfaghari |  |  | 1.1.2 | 1201 | 0031
3 |  | Leg and Brace Hiltis | P. Titus | Smith | 5 | 2011-03-08 |  | Will be part of Rev 3 to the above calc |  |  | M.Smith |  |  | 1.1.2 | 1207 | 0032
4 |  | Full Load Inventory | P. Titus | P. Titus | 30 | 2010-12-15 | 2011-01-15 | Will be part of Rev 3 to the above calc | [5 empty] | 1.1.1 | 1000 | 0016 | Per M Smith email
5 |  | Pedestal Loads | P. Titus | Smith | 10 | 2011-03-08 |  | Will be part of Rev 3 to the above calc |  |  | M.Smith |  |  | 1.1.2 | 1206 | 0029, 0032
6 |  | VV Leg | Titus | Smith |  | 2010-11-30 | [7 empty] | 1.1.2 | 1207 | 0032 | Per M Smith email
7 |  | VV Interface Welds | Titus | Smith |  | 2010-11-30 | [7 empty] | 1.1.2 | 1207 | 0032
WBS 11- Plasma Facing Components
8 |  | Heat Balance | A.Brooks |  | 100 |  |  | NSTXU-CALC-11-01-00 | Tentative Calc # |  | H.Zhang |  |  | 1.1.1 | 1000 | 0011
9 |  | Sizing of Coolant Capabilities | A.Brooks | Chrzanowski | 100 | 2010-06-01 |  | Will be part of the above calc | [5 empty] | 1.3.2 | 3200 | 0023
10 |  | Divertor Tile Thermal Stress (CFC Tiles) | A.Brooks | Tresemer | 100 |  |  | Will be part of the above calc | [5 empty] | 1.1.1 | 1001
11 |  | General Tile Program | J. Boales | Tresemer | 100 |  |  | NSTXU-CALC-11-02-00 | Tentative Calc # | 2010-10-01 | A. Brooks | A.Brooks |  | 1.1.1 | 1001 | 0040
12 |  | Inner CS Casing Tile Stress | J. Boales | Tresemer | 100 |  |  | Will be part of the above calc |  | 2010-10-01 | A. Brooks |  |  | 1.1.1 | 1001
13 |  | Final Tile Stress Analysis (ATJ Tiles) | A.Brooks | Tressemer | 50 | 2010-11-19 | 2010-12-20 | NSTXU-CALC-11-03-00 | Tentative Calc # |  |  |  |  | 1.1.1 | 1001 | 0040
14 |  | Fastener Analysis | A.Brooks | Tressemer | 10 | 2011-01-10 |  | NSTXU-CALC-11-04-00 | Tentative Calc # |  |  |  |  | 1.1.1 | 1001 | 0041
WBS 12 - Vacuum Vessel
|  | Disruption Analysis of Vacuum Vessel and Passive Plates | S.Avasarala | Titus | 100 |  |  | NSTXU-CALC-12-01-00 | Existing Calc |  |  |  |  | 1.1.1 | 1002 | 0016
|  | Update of Analysis of Vacuum Vessel & Passive Plates | P. Titus | Titus | 65 | 2011-01-05 | 2011-01-20 | Will be part of Rev 1 to the above calc | [5 empty] | 1.1.1 | 1002 | 0019
15 |  | Dome/PF Rib Stresses | P.Titus | Smith | 50 | 2011-02-01 |  | NSTXU-CALC-12-02-00 | Tentative Calc # |  | M.Smith |  |  | 1.1.2 | 1220 | 0016
16 |  | OPERA 2D Disruption Analyses | Hatcher/Titus | Titus | 90 | 2011-01-17 |  | NSTXU-CALC-12-03-00 | Tentative Calc # |  | A.Brooks |  |  | 1.1.1 | 1002 | 0014
28 |  | PF2 Bolting and Bracket Stress | P. Titus | Smith | 75 | 2011-02-01 |  | NSTXU-CALC-12-03-00 | Tentative Calc # |  | M.Smith |  |  | 1.1.2 | 1202 | 0032
29 |  | PF3 Bolting, Bracket, and weld Stress | P. Titus | Smith | 75 | 2011-02-01 |  | NSTXU-CALC-12-04-00 | Tentative Calc # |  | M.Smith |  |  | 1.1.2 | 1203 | 0032
30 |  | PF4 and 5 Support Analysis | P. Titus | Smith | 65 | 2011-03-22 |  | NSTXU-CALC-12-05-00 | Tentative Calc # |  | M.Smith |  |  | 1.1.2 | 1208 | 0029-0032
31 |  | PF4 and 5 Radial Support (Incorporate into Calc 05) | P. Titus | Smith | 60 | 3/9-3/22 |  | NSTXU-CALC-12-06-00 | Tentative Calc # |  | M.Smith |  |  | 1.1.2 | 1204 | 0032
52 |  | Alunimum Block | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 | Tentative calc # - Assume this is part of the structure |  | M.Smith |  |  | 1.1.2 | 1205 | 0029, 0037 | Per M Smith email
53 |  | TFO Leg | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | Will be part of the above calc | [5 empty] | 1.1.2 | 1205 | 0029, 0037 | Moments Loads
54 |  | Bolt details | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | Will be part of the above calc | [5 empty] | 1.1.2 | 1205 | 0029, 0037 | Moments Loads
69 |  | Umbrella Reinforcement Details | Han Zhang | Smith | 20 | 2011-02-22 |  | NSTXU-CALC-12-07-00 | Tentative Calc # |  | P.Titus / H.Zhang |  |  | 1.1.2 | 1205 | 0029-0090
70 |  | Lid/Spoke Assembly, Upper and Lower | P.Titus/Smith | Smith | 50 | 2011-02-22 |  | NSTXU-CALC-12-08-00 | Tentative Calc # |  |  |  |  | 1.1.2 | 1205 | 31 & 89
71 |  | Pedestal Analysis | P.Titus/Smith | Smith | 50 | 2011-03-08 |  | NSTXU-CALC-12-09-00 | Tentative Calc # |  |  |  |  | 1.1.2 | 1206 | 0029-0032
WBS 13 - Magnet Systems
WBS 130 - General
1 |  | Global Model | P. Titus | Titus |  | N/A |  | NSTX-CALC-13-01-01 | SUPERCEDED - Now CALC-10-01-02
79 |  | Maximum and Minimum Loads on the NSTX OH and PF Coils, and Coil Groupings | Titus | Titus | 100 | N/A |  | NSTX-CALC-13-02-00 | Existing Calc - SUPERCEDED by Charlie's Design Point
80 |  | NSTX Influence Matrix | R.Hatcher | Titus | 100 |  |  | NSTXU-CALC-13-03-00 | Existing Calc |  |  |  |  | 1.1.3 | 1300 | 0010
|  | DCPS Force Influence Coefficients | R.Hatcher | R.Hatcher | 100 | 2010-11-24 |  | Will be part of Rev 1 to the above calc | [5 empty] | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
36 |  | DCPS TF Inner Leg Torsional Shear Stress | Wooley/Titus | R.Hatcher | 50 | 2010-10-27 | 2010-12-15 | NSTXU-CALC-13-04-00 | [5 empty] | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
39 |  | DCPS Moment Influence Coefficients | Wooley/Titus | R.Hatcher | 50 | 2010-12-15 |  | NSTXU-CALC-13-05-00 | Will this be a separate calc or part of one of the above? (separate) |  |  |  |  | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
WBS 131 - Polodal Field Coils
|  | Analysis of CSU Poloidal Field Coils | Woolley | Chrzanowski | 100 |  |  | NSTXU-CALC 131-01-00 | Existing Calc |  |  |  |  | 1.1.3 | 1306 | 1020
|  | Poloidal Magnetic Quantites for the Feb 2010 Provisional Design | Woolley | Chrzanowski | 100 |  |  | NSTXU-CALC 131-02-00 | Existing Calc |  |  |  |  | 1.1.3 | 1306 | 1020
WBS 132 - Toroidal Field Coils
32 |  | Coupled EM-Thermal Diffusion Analysis(to be superceded by #48) | P.Titus | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-01-00 | Existing Calc |  |  |  |  | 1.1.3 | 1304
33 |  | Coupled EM-Thermal Analysis (to be superceded by #48) | P.Titus | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-02-00 | Existing Calc - SHOULD THIS HAVE BEEN AN UPDATE TO CALC-132-01?:Superseded by Item #48 |  |  |  |  | 1.1.3 | 1304
34 |  | OOP PF/TF Torques on TF | Wooley | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-03-00 | Existing Calc |  |  |  |  | 1.1.3 | 1304 | 0220
35 |  | Torque Egns for Design Point | Wooley | Titus | 50 | 2011-01-17 |  | Will be part of the above calc | [5 empty] | 1.1.0 | 1000 | 0011
40 |  | Analysis of TF Outer Leg | Han Zhang | Smith | 50 | 2010-10-27 | 2011-01-31 | NSTXU-CALC-132-04-00 | Existing Calc |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
41 |  | Loads at Knuckle Clevis | Han Zhang | Smith | 50 | 2011-03-08 |  | Will be part of Rev 1 to the above calc | [5 empty] | 1.1.2 | 1201 | 0031, 0032
42 |  | Loads and Moments on Ring | Han Zhang | Smith | 50 | 2011-03-08 |  | Will be part of Rev 1 to the above calc | [5 empty] | 1.1.2 | 1201 | 0031, 0032
43 |  | Outer Leg Insulation Bond Shear Stress | Han Zhang | Chrzanowski | 50 | 2011-03-01 |  | Will be part of Rev 1 to the above calc | [5 empty] | 1.1.3 | 1304 | 0210
44 |  | Umbrella Rinforcement | Han Zhang | Smith | 50 | 2011-03-08 |  | Will be part of Rev 1 to the above calc | [5 empty] | 1.1.2 | 1205 | 0029, 0037
48 |  | Coupled EM-Thermal Analysis | Han Zhang | Chrzanowski | 50 | 2010-12-01 | 2011-01-31 | NSTXU-CALC-132-05-00 | Existing Calc, but how differ from 132-01 or 132-02 above? Perhaps this should be a rev?? |  |  |  |  | 1.1.3 | 1304 | 0220
49 |  | Cooldown of Flex | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | Will be part of Rev 1 to the above calc | [5 empty] | 1.1.3 | 1304 | 0220
50 |  | Benchmarh I^2 t Calcs | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | Will be part of Rev 1 to the above calc | [5 empty] | 1.1.3 | 1304 | 0220
51 |  | TF Peak Temps at Corner | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | Will be part of Rev 1 to the above calc | [5 empty] | 1.1.3 | 1304 | 0220
55 |  | TF Flex Joint and Bundle Stub | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 | Existing Calc |  | A.Zolfaghari? |  |  | 1.1.3 | 1304 | 0230
56 |  | Joint Electrical Contact Resistance | T.Willard | Chrzanowski | 100 |  |  | Will be part of the above calc | [5 empty] | 1.1.3 | 1304 | 0220
57 |  | Flex Stress for Inplane and OOP Loads | T.Willard | Chrzanowski | 100 |  |  | Will be part of the above calc | [5 empty] | 1.1.3 | 1304 | 1030
58 |  | DLF for Disruption | T.Willard | Chrzanowski |  | 2010-12-15 | 2011-01-15 | Will be part of Rev 1 to the above calc | [5 empty] | 1.1.3 | 1304 | 0230
59 |  | Maximum Torsional Shear Stress | P. Titus | Chrzanowski | 75 | 2010-12-15 | 2011-01-15 | NSTXU-CALC-132-07-00 | Existing Calc |  |  |  |  | 1.1.3 | 1304 | 0230
77 |  | Determination of shear Forces Between the TF conductors and Insulation and the G-10 Insulating Crown. | A. Zolfaghari | Chrzanowski | 100 |  |  | NSTXU-CALC-132-08-00 | [5 empty] | 1.1.3 | 1304 | 0230
68 |  | TF Flag Key | A. Zolfaghari | Chrzanowski | 90 | 2011-01-05 |  | Will be part of Rev 1 to the above calc |  |  | T.Willard |  |  | 1.1.3 | 1304 | 0190 & 0210
45 |  | Analysis of Knuckle Clevis | P. Titus | Smith | 50 | 2011-03-08 |  | NSTXU-CALC-132-09-00 | Tentative Calc # |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
46 |  | Ring Bolted Joint | Peter Rogoff | Smith | 50 | 2011-03-08 |  | NSTXU-CALC-132-10-00 | Tentative Calc # |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
47 |  | TF Cooldown using FCOOL | A. Zolfaghari | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-11-00 | Tentative Calc # |  | M.Kalish? |  |  | 1.1.3 | 1304 | 0230
WBS 133 - Center Stack
27 |  | Structural Analysis of the PF1 Coils, leads and Supports | L.Myatt/ A. Khodak | Chrzanowski | 100 | 2010-08-19 | 2010-12-07 | NSTXU-CALC-133-01-00 | Existing Calc - Should this be in WBS 131 and not 133? |  | A.Khodak? |  |  | 1.1.3 | 1306 | 1020
|  | Revision to 133-01 | L.Myatt/ A. Khodak | Chrzanowski |  |  | 2011-03-01
61 |  | Thermal Stresses on OH-TF Coils | S.Avasarala | Chrzanowski | 100 |  |  | NSTXU-CALC-133-02-00 | Existing Calc |  |  |  |  | 1.1.3 | 1307 | 1050
62 |  | Center Stack Casing Disruption Inductive and Halo Current Loads | P.Titus | Chrzanowski | 100 | 2010-08-12 |  | NSTXU-CALC-133-03-00 | Existing Calc | 2010-04-13 | P.Titus |  |  | 1.1.3 | 1307 | 1030
64 |  | OH Preload System and Belleville Spring Design | Peter Rogoff | Chrzanowski | 100 |  |  | NSTXU-CALC-133-04-00 | Existing Calc |  | T.Kozub/Test |  |  | 1.1.3 | 1302
19 |  | Halo Current Analysis of Center Stack Casing | A.Brooks | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-133-05-00 | Tentative Calc # |  |  |  |  | 1.1.3 | 1307 | 1050
65 |  | OH Coolant Hole Optimization | A. Zolfaghari | Chrzanowski | 100 |  |  | NSTXU-CALC-133-06-00 |  |  | M.Mardenfeld |  |  | 1.1.3 | 1305 | 100
63 |  | OH Coax Lead Analysis | M. Mardenfeld | Chrzanowski | 10 | 2010-09-10 | 2011-02-15 | NSTXU-CALC-133-07-00 | Tentative Calc # |  |  |  |  | 1.1.3 | 1305 | 120
66 |  | OH Stress Analyses | A. Zolfaghari | Chrzanowski | 100 | 2010-07-29 |  | NSTXU-CALC-133-08-00 | COMPLETE? WHERE IS IT? PLEASE PROVIDE |  |  |  |  | 1.1.3 | 1305 | 100
67 |  | OH Fatigue and Fracture Mechanics | J. Feng/P. Titus | Chrzanowski | 75 | 2010-09-10 | 2011-01-15 | NSTXU-CALC-133-09-00 | COMPLETE? WHERE IS IT? PLEASE PROVIDE |  |  |  |  | 1.1.3 | 1305 | 140
20 |  | Center Stack Casing Bellows | Peter Rogoff | Chrzanowski | 50 |  | 2011-01-15 | NSTXU-CALC-133-10-00 | [5 empty] | 1.1.3 | 1307 | 1050
21 |  | CS Casing Halo Ind and Res Cur | A.Brooks | Chrzanowski | 100 | 2010-12-01 | 2010-12-15 | [6 empty] | 1.1.3 | 1307 | 1050
22 |  | CS Casing Static and Dynamic | A.Brooks | Chrzanowski | 100 | 2010-12-01 | 2010-12-15 | [6 empty] | 1.1.3 | 1307 | 1050
WBS 24 - NBI
23 |  | Vessel Port Re-Work for NB and Thompson Scattering Port | T. Willard | Priniski / Labik | 75 | 2011-01-05 |  | NSTXU-CALC-24-01-00 | Tentative Calc # |  | A.Zolfaghari |  |  | 1.2.4 | 2480 | 0035
24 |  | NB Reinforcement | T. Willard | Priniski | 75 | 2011-02-25 |  | Will be part of the above calc | [5 empty] | 1.2.4 | 2480 | 0037
25 |  | Thompson Scattering Port | T. Willard | Labik | 75 | 2011-01-05 |  | Will be part of the above calc | [5 empty] | 1.4.5 | 4500 | 0009
72 |  | Armor Plate Backing Plate | L. Bryant | Priniski | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00 | Tentative Calc # |  |  |  |  | 1.2.4 | 2460 | 0026
73 |  | Disruption Loading | L. Bryant | Priniski | 100 | 2011-02-21 |  | Will be part of the above calc | [5 empty] | 1.2.4 | 2460 | 0026
74 |  | Thermal Stress Analysis(Not Req per Craig P.) | L. Bryant | Priniski |  | 2011-02-21 |  | Will be part of the above calc |  |  | I. Zatz |  |  | 1.2.4 | 2460 | 0026 | Not Req per Craig P.
new |  | Magnetic Shielding Calculation | L. Bryant | Priniski | 60 | 2010-11-24 | 2011-03-30 | Initial calc complete and will be filed, 3D calc to be performed. Needs Calc # |  |  | A. Brooks |  |  | 1.2.4 | 2485 | 0016A
75 |  | HHFW Antenna (needs to be modified for upgrade loads) | Han Zhang | Bob Ellis | 80 | 2011-01-15 |  | NSTXU-CALC-24-03-00 | Tentative Calc # (Bob:Check Han's Existing Calc) |  | R.Hatcher |  |  | 1.2.4
WBS 41 - Diagnostics
76 |  | Diagnostics Review and Database | J. Boales | Titus | 100 | 09/01/10 |  | NSTXU-CALC-40-01-00 | Tentative calc #. WBS Number incorrect! Diagnostics should be 1.4.0 NOT 1.2.3.. Should be Kaita as the COG. |  | Bob Kiata to assign? |  |  | 1.2.3 | 2300 | 0015
78 |  | Thomson Scattering Port | Labik | Kaita |  |  |  | NSTXU-CALC-40-02-00 | Not on your spreadsheet, but was on an earlier version.(See line #23 - Huh??? line 23 totally unrelated!) |  |  |  |  | 1.4.0 | 4500 |  | Covered under Vessel Port Re-Work for NB and Thompson Scattering Port #23
WBS 55 - General Power Systems
60 |  | Bus Bar Analysis | A. Khodak | Smith | 30 | 2011-02-08 |  | NSTXU-CALC-55-01-00 | Tentative Calc # |  | H.Zhang? |  |  | 1.5.5 | 5501 | 0049-0076