## 413.3A Reqmnts
DOE O 413.3A Requirement | Applicability | Lead | Strategy
Conceptual Design Report | Applicable. | Perry Strykowsky | Use NCSX Conceptual Design Report as an example.
Acquisition Strategy | Applicable. | Perry | Use NCSX Acquisition Strategy as a template.
One-for-One Replacement Strategy (space banking) | Not applicable. NSTX is not real property nor is there any change in overall square footage within the NSTX Test Cell. (Project is an major item of equipment (MIE)). | n/a | No further action.
Preliminary Project Execution Plan Includes: (a) Risk Management Plan (b) Risk Assessment | Applicable. | Perry | Use NCSX's most recent draft PEP (for 2008 rebaseline) as a template
Approve a Federal Project Director | Already designated via email from Dan Lehman (dated: 2/17/2009) | n/a | No further action.
Establish Itegrated Project Team & charter | FPD will establish IPT and charter 60 days prior to CDR | Makiel | 1. FPD will solicit members and prepare a charter similar to NCSX. The membership and charter will be posted on the NSTX Upgrade website. 2. Around August, the IPT will begin meetings.
Conduct Design Review (a) Drawings, analysis & specs (b) Tech Independent Project Review (see row 9) | Applicable. | Makiel | 1. Confirm Lehman Review date with Kin Chao. 2. Draft charge letter for OFES to Lehman's office.
Technical Independent Project Review for high risk, high hazard, and Category 1, 2 and 3 nuclear facilities | Yes. NSTX is currently considered a 'high hazard' facility. | Makiel Perry Levine | Charge the NSTX ACC to review the PHAR table. See row 18 below.
Prepare Project Data Sheet for PED funds for line item projects | Not required. MIE projects can use operating funds to support conceptual design (pre CD-1) | n/a | No further action.
Approve long lead materials | The CDR will identify long lead materials???? | Dudek von Halle Makiel | The CD-1 approval report/memo (prepared by FPD/OFES) for AE signature will identify long lead procurements and therefore be the approval mechanism.
Implement Integrated Safety Management into management and work process planning at all levels | Applicable. | Levine | 1. Prepare document similar to "ES&H Aspects of NCSX". 2. Prepare slide for CDR review. 3. Incorporate appropriate ISM terminology into: (a) Prelim PEP; (b) IPT Charter; (c) Conceptual Design Report; (d) PHAR
Prepare NEPA and any other permits | A NEPA CX was approved. No other external permits identified. | n/a | No further action.
High Performance Sustainable Building (450.1 chg 2) documented in the CDR and Acquisition Strategy. | NSTX is not real property (i.e., building). It is a major item of equipment upgrade. | n/a | No further action.
Preliminary Security Vulnerability Assessment Report | As per Kin, this report is required for all projects regardless of hazard or risk. | Makiel Samtmann | 1. DOE FPD will request via letter to PPPL Site Protection to review/update the Security Assessment Report (dtd 4/28/08) to see if Upgrade Project has any physical security impact. 2. Response memo from Site Protection to DOE-FPD be provided outlining whether modification are required or not.
Initial Cyber Security Plan for IT projects | Not applicable. NSTX is not an IT project. | n/a | No further action.
Conceptual Safety Design Report for category 1, 2 and 3 nuclear facilities | Not likely applicable. NSTX is currently below category 3. However, 'below cat 3' status after upgrades should be validated. See row 19 below. | Levine | See row 19 below
Preliminary Hazard Analysis Report for below Hazard Category 3 | Applicable. | Perry Gentile | 1. Draft a Preliminary Hazard Analysis Report using the table in the existing NSTX SAD. Also, use the NCSX PHAR table for further support. 2. Charge the NSTX ACC (C. Gentile) as the Technical Independent Project Review team to review the table with presentations from NSTX job managers. 3. Post the PHAR on the NSTX Upgrade website (CD-1).
Preliminary Safety Validation Report of the CSDR for Cat 1, 2 and 3 nuclear facilities | Not likely applicable. NSTX is currently below category 3. However, 'below cat 3' status after upgrades should be validated | Makiel Levine | 1. Verify that NSTX will continue to be 'below cat 3' via calculation. 2. Prepare a paper that describes: a. Why NSTX is currently a 'high hazard' facility / What does 'high hazard' mean? b. Document calculations resulting from the Upgrades (more neutron activitation?) c. Report findings (remains a 'below Nuclear Cat 3' facility?). Post on website. 3. If 'below Cat 3', then no CSDR or PSVR is required...no further action.
Quality Assurance Program is acceptable and continues to apply | Applicable. | Makiel Malsbury | 1. Charge Judy to provide 1 or 2 overview slides of PPPL's QA Program. (a) Organizational structure (b) Services provided (incl DCMA) 2. Have Judy present info at the Lehman (CD-1) Review.

## List of Deliverables
NSTX CD-2 Preparation
Requirement | Due Date | Owner | Status/Remarks
Integrated Project Team
Continue meetings every 3 weeks |  | Makiel
CD-1
Submit CD-1 Package to DOE/PSO | Done | Strykowsky
Schedule ESSAB | Done | OFES
CD-1 Approval | DONE | OFES
Advisory Committee
Establish Approach | Done | Williams/Prager
Create Advisory committee(s), charter and members | n/a | Williams/Prager | n/a PU Advisory committee and independent design reviews
Initial Advisory committee review | n/a | Williams/Prager | PDR june and PU Advisory committee May
Technical Peer Reviews
NBI
Duct/port/armor/beamline services/power/controls review | DONE | Stevenson
Decon review | DONE | Stevenson
CSU
Establish review team & schedule | DONE | Dudek
CSU review | DONE | Dudek
Preliminary Design
FMEA CSU Draft | 2010-04-02 | Dudek | Kalish and Chrzanowski still due
FMEA CSU Final | ? | Dudek
CSU SRD's Draft (for selective systems) | 2010-06-23 | Dudek
NBI SDD Draft | 2010-06-23 | Stevenson
CSU updated GRD | Done | Dudek | Updated 2/9/10
NBI updated GRD | Done | Stevenson
Performance Baseline Documentation
WAF's
CSU - Submit WAF's | Done | Dudek
CSU internal reviews (completed) | 2010-05-17 | Williams | in progress (7xxx remaining)
CSU Update and post | wo/5/24 | Strykowsky
NBI - Submit WAF's | Done | Stevenson
NBI internal reviews (completed) | Done | Williams
NBI update re-Posted | wo/5/24 | Strykowsky
Obtain Rates from Budget Office | Done | Iseicz
Update P3 Rates | Done | Guzman
Resource Loaded Schedule | 2010-05-30 | Guzman
Determine Contingency methodologies | Done | Strykowsky
Establish DOE Funding Proifile Basis | 2010-05-15 | Synakowski | use CD-1 profile
Basis of cost & schedule | 2010-06-01 | Strykowsky
Critical path | 2010-06-01 | Strykowsky
Level 2 & 3 milestones | 2010-06-01 | Strykowsky
Contingency estimate (cost and schedule) | 2010-06-01 | Strykowsky
Breakdown by FY | 2010-06-01 | Strykowsky
Breakdown by WBS | 2010-06-01 | Strykowsky
Staffing Plan | 2010-06-01 | Strykowsky
Cost by WBS (CS, 2nd NBI & Mngmnt) | 2010-06-01 | Strykowsky
Budget profile | 2010-06-01 | Strykowsky
Project Execution Plan (updated) | 2010-06-09
2.2.5 Update project schedule | 2010-06-09 | Strykowsky | marked-up awaiting cost and schedule
6.2 Update funding profile | 2010-06-09 | Strykowsky
7.2 Update cost & schedule | 2010-06-09 | Strykowsky
7.2 Add level 2 and 3 milestones | 2010-06-09 | Strykowsky
Appendix 1 Update WBS Dictionary & Structure | 2010-06-09 | Strykowsky
NEPA Process | Done | Levine | CX approved prior CD-1 - no further work req'd
Preliminary Hazard Analysis Plan (updated) |  | Gentile | ACC Review post-PDR design
ACC Review post-PDR design |  | Gentile
Update Security Vulnerability Analysis (updated) |  |  | Likely not necessary
Recommendations Log | 2010-06-10 | Strykowsky
Identify Long Lead Procurements
I.D items (what, why & how much) | 2010-06-01 | Strykowsky | Prepare a slide
Risk Registry (updated)
PDR risks have been added | 2010-06-01 | Perry
Ensure all fields been filled-out | 2010-06-01 | Perry
Davis-Bacon Determination | 2010-04-01 | Makiel | Required by CD-3
NSTX Upgrade Website
Establish Website for CD-2 | 2010-06-10 | Simmons | ready for postings
Preliminary Design AND CD-2 Readiness Review PU/PPPL
Assemble PDR team members and establish date | Done | Williams | Members identified and contacted
Draft Charge & Agenda | Done | Williams | Draft issued for comment
PU/PPPL PDR Dry Run | 2010-06-08 | Williams
Post Materials for PU/PPPL PDR | 2010-06-11 | Strykowsky
PU/PPPL PDR | 2010-06-23 | Strykowsky | Wed 6/23 thru Fri 6/25
Issue report | 2010-07-14 | Review Team
Disposition Chits | 2010-07-07 | Strykowsky
CD-2 OFES Review (Lehman Review)
Assemble team members and establish date | 2010-06-15 | Makiel | Date established
Draft Charge & Agenda | 2010-06-15 | Makiel | Draft letter for OFES AD signature
Modify/adjuist/revise documentation from the PDR | 2010-06-30
PU/PPPL PDR and CD-2 readiness dryruns | 2010-07-27 | Williams
Post materials for Lehman Review | 2010-07-31 | Strykowsky
CD-2 Lehman Review | 2010-08-10 | Strykowsky
Issue report | 2010-08-31 | Lehman
Prepare and Submit CD-2 package | 2010-08-17 | Makiel
CD-2 Approval | 2010-09-14 | Synakowski | Assumed delegated by SC-1
Formulas:
Due Date = +[Due Date, row below]
Due Date = +[Due Date, row above]

## Sheet3
[6 empty] | FEBRUARY | [19 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE | [21 empty] | JULY
 | time axis 2010-01-28 to 2010-08-05
 | time axis 2010-01-28 to 2010-08-05
x | PF 4/5 Support Basic Concept | 2010-01-29 | Mangra
| PF 4/5 Links to VV Capacity | 2010-01-29 | Titus
| Outer TF Supports Basic Concept | 2010-01-29 | Mangra
| VV Kegs Validation | 2010-01-29 | Titus
| TC Clamp Aluminum Block Reaction to Ground Capacity | 2010-01-29 | Titus
| FMEA CSU | 2010-02-08 | Dudek
| CSU updated GRD | 2010-02-08 | Dudek
| FMEA NBI | 2010-02-08 | Stevenson
| PF 4/5 Support Validation | 2010-02-19 | Titus
| Outer TF Supports Evaluation | 2010-02-19 | Titus
| Umbrella Reinforcement and Attachment Design | 2010-02-26 | Mangra
x | NBI peer review | 2010-02-26 | Stevenson
| Pedestal and Lids Design | 2010-04-01 | Mangra
| Umbrella Reinforcement Evaluation | 2010-04-02 | Titus
x | NBI Decon peer review | 2010-04-15 | Stevenson
| NBI SDDs | 2010-04-15 | Stevenson
| PF 2/3 Capacity | 2010-04-16 | Titus
x | NBI- Submit WAF's | 2010-04-26 | Stevenson
| CSU SDDs | 2010-04-29 | Dudek
x | CSU Peer review | 2010-04-29 | Dudek
x | CSU - Submit WAF's | 2010-05-03 | Dudek
| NBI internal WAF reviews (completed) | 2010-05-03 | strykowsky
| CSU internal reviews (completed) | 2010-05-17 | Strykowsky
| Outer TF supports Validation | 2010-05-21 | Titus
| Umbrella Reinforcement Validation | 2010-05-21 | Titus
| Pedestal and lids validation | 2010-05-21 | Titus
| PU/PPPL PDR Dry Run | 2010-06-08 | Strykowsky
x | PU/PPPL PDR | 2010-06-23 | Strykowsky
| Lehman dry runs | 2010-07-07 | Strykowsky
x | Lehman Review | 2010-07-21 | Strykowsky