## Sheet1
Line # | Job # (WAF) | Act ID | COG | Preparer |  | Calc Title | % Complete | Comments | Schedule Date | Forecast | Calc # | Status | Preparer Sign date | Reviewer | Reviewer Sign date
1 | 1000 |  | Titus | P. Titus |  | Global Model |  |  |  |  | NSTX-CALC-13-01-00 |  |  | Group
2 |  |  | Smith |  |  | Torques to Lids and TF Teeth | [7 empty] | A.Zolfaghari
3 |  |  | Smith |  |  | Leg and Brace Hiltis | [7 empty] | M.Smith
4 | 1206 | 0029, 0032 | Smith |  |  | Pedistal Loads |  |  | 2011-02-14 |  |  |  |  | M.Smith
5 |  |  |  | A.Brooks | First Wall | Heat Balance |  |  |  |  | Need Calc # |  |  | H.Zhang
6 | 3200 |  | Chrzanowski |  |  | Sizing of Coolant Capabilities |  |  |  |  | Need Calc #
7 |  |  | Tresemer |  |  | Divertor Tile Thermal Stress |  |  |  |  | Need Calc #
8 |  |  | Tresemer | J. Boales |  | General Tile Program |  |  |  |  | Need Calc # |  | 2010-10-01 | A. Brooks
9 | 1001 |  | Tresemer |  |  | Inner CS Casing Tile Stress |  |  |  |  | Need Calc #
10 | 1001 |  | Tressemer | K. Tresemer |  | Final Tile Stress Analysis |  |  |  |  | Need Calc #
11 |  |  |  |  | Vacuum Vessel | [5 empty] | Need Calc #
12 | 1200 |  | Smith | P.Titus |  | Dome/PF Rib Stresses |  |  |  |  | Need Calc # |  |  | M.Smith
13 | 1002 |  | Titus | R. Hatcher |  | OPERA 2D Disruption Analyses |  |  |  |  | Need Calc # |  |  | A.Brooks
14 | 1002 | 0016 | Titus | S. Avasarala |  | Disruption Analysis of Vacuum Vessel and Passive Plates |  |  | 2011-03-22 |  | Need Calc #
15 | 1002 | 0016 | Titus | Titus |  | Disruption Analysis of Vacuum Vessel and Passive Plates |  |  | 2011-03-22 |  | Need Calc #
16 | 1307 | 1050 | Chrzanowski | Brooks |  | Halo Current Analysis of Center Stack Casing |  |  | 2010-10-08 |  | Need Calc #
17 | 1307 | 1050 | Chrzanowski |  |  | CS Casing Halo Ind and Res Cur |  |  | 2010-10-08 |  | Need Calc #
18 | 1307 | 1050 | Chrzanowski |  |  | CS Casing Static and Dynamic |  |  | 2010-10-08 |  | Need Calc #
19 | 2480 |  | Priniski / Labik | T. Willard |  | Vessel Port Re-Work for NB and Thompson Scattering Port |  |  |  |  | Need Calc # |  |  | A.Zolfaghari
20 | 2480 | 0037 | Priniski | T. Willard |  | NB Reinforcement |  |  | 2011-02-25
21 | 4500 |  | Labik | T. Willard |  | Thompson Scattering Port |  |  | ??
22 | 1306 |  | Chrzanowski | Woolley | Poloidal Field Coils | [5 empty] | NSTX-CALC 131-01-00
23 | 1306 | 1306-1020 | Chrzanowski | L.Myatt/ A. Khodak |  | Structural Analysis of the PF1 Coils, leads and Supports |  |  | 2010-08-19 | 2010-12-07 | NSTX-CALC-133-01-00 |  |  | A.Khodak?
24 |  |  |  |  | Toroidal Field Coils
25 |  |  | Chrzanowski | Titus |  | Couplel EM-Thermal Analysis |  | Not in Smith Job scope | 2010-10-27 |  | NSTX-CALC-132-01-00
26 |  |  | Chrzanowski | Titus |  | Couplel EM-Thermal Analysis |  |  | 2010-10-27 |  | NSTX-CALC-132-02-00
27 |  |  | Chrzanowski | Wooley |  | OOP PF/TF Torques on TF |  |  | 2010-10-27 |  | NSTX-CALC-132-03-00
28 | 1000 |  | Titus | Wooley |  | Torque Egns for Design Point |  |  | 2010-10-27
29 |  |  | R.Hatcher | Wooley/Titus |  | DCPS TF Inner Leg Torsional Shear Stress |  |  | 2010-10-27
30 |  |  | R.Hatcher | R.Hatcher |  | DCPS Force Influence Coefficients
31 |  |  | R.Hatcher | Wooley/Titus |  | DCPS Moment Influence Coefficients
32 |  |  |  | Han Zhang |  | Analysis of TF Outer Leg |  |  | 2010-10-27 |  | NSTX-CALC-132-04-00
33 | 1201 | 0031, 0032 | Smith |  |  | Loads at Knuckle Clevis |  |  | 2010-10-27
34 | 1201 | 0031, 0032 | Smith |  |  | Loads and Moments on Ring |  |  | 2010-10-27
35 |  |  | Chrzanowski |  |  | Outer Leg Insulation Bond Shear Stress |  | Not in Smith/Chrz. Job scope | 2010-10-27
36 |  |  | Smith |  |  | Umbrella Rinforcement |  |  | 2010-10-27
37 | 1201 | 0031, 0032 | Smith | P. Titus |  | Analysis of Knuckle Clevis |  | Not in Smith/Chrz. Job scope | 2010-10-27
38 | 1201 | 0031, 0032 | Smith | Peter Rogoff |  | Ring Bolted Joint |  | Not in Smith/Chrz. Job scope | 2010-10-27
39 |  |  | Chrzanowski | A. Zolfaghari |  | TF Cooldown using FCOOL |  | Not in Smith/Chrz. Job scope | 2010-10-27 |  |  |  |  | M.Kalish?
40 |  |  | Chrzanowski | Han Zhang |  | Couplel EM-Thermal Analysis |  | Not in Smith/Chrz. Job scope | 2010-10-27 |  | NSTX-CALC-132-05-00
41 |  |  | Chrzanowski |  |  | Cooldown of Flex |  | Not in Smith/Chrz. Job scope | 2010-10-27
42 |  |  | Chrzanowski |  |  | Benchmarh I^2 t Calcs |  | Not in Smith/Chrz. Job scope | 2010-10-27
43 |  |  | Chrzanowski |  |  | TF Peak Temps at Corner |  | Not in Smith/Chrz. Job scope | 2010-10-27
44
45 | 1304 |  | Chrzanowski | Tom Willard |  | TF Flex Joint and Bundle Stub |  |  |  |  | NSTX-CALC-132-06-00 |  |  | A.Zolfaghari?
46 | 1304 | ? | Chrzanowski |  |  | Joint Electrical Contact Resistance | complete
47 | 1304 | 1304-1030 | Chrzanowski |  |  | Flex Stress for Inplane and OOP Loads | complete
48 | 1304 | ? | Chrzanowski |  |  | DLF for Disruption
49 | 1304 | ? | Chrzanowski | P. Titus |  | Maximum Torsional Shear Stress | 75 |  |  |  | NSTX-CALC-132-07-00
50 | [10 empty] | NSTX-CALC-132-08-00
51 | [10 empty] | NSTX-CALC-132-09-00
52 | [10 empty] | NSTX-CALC-132-01-00
53 | [10 empty] | NSTX-CALC-132-01-00
54 | 5501 | 0049-0076 | Smith | A. Khodak |  | Bus Bar Analysis |  |  | 2010-12-07 |  |  |  |  | H.Zhang?
55 |  | ? | Chrzanowski | S.Avasarala |  | Thermal Stresses on OH-TF Coils | complete |  |  |  | NSTX-CALC-133-02-00
56 | 1307 | 1307-1030 | Chrzanowski | P.Titus |  | Center Stack Casing Disruption Inductive and Halo Current Loads | Complete |  | 2010-08-12 |  | NSTX-CALC-133-03-00 |  | 2010-04-13 | P.Titus
57 | 1305 | 1305-0120 | Chrzanowski | A. Khodak |  | OH Lead Analysis |  |  | 2010-09-02
58 | 1305 | ? | Chrzanowski | Peter Rogoff |  | OH Preload System and Belleville Spring Design | complete |  |  |  | NSTX-CALC-133-04-00 |  |  | T.Kozub/Test
59 | 1305 | 1305-0100 | Chrzanowski | A. Zolfaghari |  | OH Coolant Hole Optimization | complete | [6 empty] | M.Mardenfeld
60 | 1305 | 1305-0100 | Chrzanowski | A. Zolfaghari |  | OH Stress Analyses | complete |  | 2010-07-29
61 | 1305 | 1305-0140 | Chrzanowski | J. Feng/P. Titus |  | OH Fatigue and Fracture Mechanics | complete |  | 2010-09-10
62 | 1304 | 1304-0190 and 1304-0210 | Chrzanowski | A. Zolfaghari |  | TF Teeth/ Collar Stress |  |  | 2011-01-05 |  | NSTX-CALC-132-08-00 |  |  | T.Willard
63
64 | 1202 | 32 | Smith | P. Titus |  | PF2 Bolting and Bracket Stress |  |  | 2011-01-06 |  |  |  |  | M.Smith
65 | 1203 | 32 | Smith | P. Titus |  | PF3 Bolting, Bracket, and weld Stress |  |  | 2011-02-28 |  |  |  |  | M.Smith
66 | 1208 | 0029-0032 | Smith | P. Titus |  | PF4 and 5 Support Analysis |  |  | 2011-02-14 |  |  |  |  | M.Smith
67 | 1205 | 0029-0090 | Smith | Mark Smith |  | Umbrella Reinforcement Details |  |  | ??? |  |  |  |  | P.Titus/H.Zhang
68 | 1205 | 31 & 89 | Smith | Titus/Mark Smith |  | Lid/Spoke Assembly, Upper and Lower |  |  | 2011-03-01
69
70 | 1206 | 0029-0032 | Smith | Titus/Mark Smith |  | Pedestal Analysis |  |  | 2011-02-11
71 | 2460 | 0026 | Priniski | L. Bryant |  | Armor Plate Backing Plate |  |  | 2011-02-21
72 |  | 0026 | Priniski | L. Bryant |  | Disruption Loading |  |  | 2011-02-21
73 |  | 0026 |  |  |  | Thermal Stress Analysis |  |  | 2011-02-21
74 |  |  | Bob Ellis | Han Zhang |  | HHFW Antenna | [7 empty] | R.Hatcher
75 | 2300 |  | Titus | J. Boales |  | Diagnostics Review and Database | [7 empty] | Bob Kiata to assign?