## Status
Title | Calc # | Current Status | Responsibility | Comments
Global Model (Update) | 10-01-02 | Updated Draft Needed | Titus | By June 6th
Seismic Analysis | 10-02-00 | In Final Review | Dahlgren | Copy incorporating Fred's comments sent out 6/8
Design Point | 10-03-00 | In Final Review | Neumeyer | Only Ali has provided conferences.
Heat Balance | 11-01-00 | In Final Review | Brooks | Completion Date???6/24
Final Tile Stresse (ATJ Tiles) | 11-03-00 | Draft Overdue | Brooks | New date for when CALC will be done?
Fastener Analysis | 11-04-00 | Draft Overdue | Brooks | New date for when CALC will be done?
Disruption Analysis of VV & Passive Plates | 12-01-00 | In Final Review | Zhai | By June 6th - WHEN?
Dome/PF Rib Stresses | 12-02-00 |  |  | Merged with CALC-12-07
Opera 2D Analysis | 12-03-00 | In Final Review | Brooks | Some Confusion as to who would review - confirmed that Art will do so.
PF2 & PF3 Bolting , Bracket & weld Stresses | 12-04-00 | Incorporating Review Comments | Titus | By June 24th???
PF 4 & PF5 Support Analysis | 12-05-00 | In Final Review | Zatz | By June 24th???
Al Block Analyses | 12-06-00 | Final Review Completed? | Smith | Ready to Sign??
Umbrella Reinf. Details | 12-07-00 | In Final Review | Zatz | By June 24th???
Lid/Spoke Assy, U & L | 12-08-00 | In Final Review | Zatz | By June 24th???
Pedistal Analysis | 12-09-00 | Final Review Completed? | Zolfaghari | By June 10th???
DCPS Force Influence Coefficients | 13-03-00 | In Final Review | Titus | Completion Date???
DCPS Moment Influence Coefficients | 13-05-00 | Final Review Completed? | Woolley | Completion Date???
Calculated Poloidal Magnets Quanties (May 2010 Design) | 131-03-00 | Final Review Completed? | Titus | Ready to Sign??
Title | Calc # | Current Status | Responsibility | Comments
OOP PF/TF Torques on TF | 132-03-01 | Final Review Completed? | Titus | Ready to Sign??
Analysis of TF Outer Leg | 132-04-00 | Final Review Completed? | Zhai | Ready to Sign??
Max Torsional Shear Stress | 132-07-00 | Final Review Completed? | Woolley | Ready to Sign??
Analysis of Knuckle Clevis | 132-09-00 | Final Review Completed? | Zhang | Ready to Sign??
OH Coolant Hole Optimization | 133-06-00 | In Final Review | Mardenfeld | By June 12th???
OH Coax Lead Analysis | 133-07-00 | Draft Overdue | Mardenfeld | By June 17th??
OH Stress Analysis | 133-08-00 | In Final Review | Dahlgren or HM Fan??? | ?????
OH & PF1 Electromagnet Stability Analysis | 133-11-00 | In Final Review | Zatz | Completion Date???
Center Stack Manufacturing Fixture | 133-12-00 | Draft Not Due Until August 2011 | Zolfaghari | Not required for FDR. Raftopoulos will do this work.
Modal Analysis and Normal Operation Transient Load Effects | 133-13 | Out for Final Review | Dahlgren | Just sent out for review to F. Dahlgren (6/8)
Diagnostic Review & Database | 40-01-00 | In Final Review | Zhai | By June 6th -- NEED COPY OF CALC
Bus Bar Analysis | 55-01-00 | In Final Review | Zhang | Review due June 12th???