## Sheet1
NSTX Calculation Log - Week of February 28, 2011 (32 open items)
Line # | WBS Name | WBS | Calc Title | Preparer | COG | Preparation % Complete | Schedule Date (COG) | Forecast Date (Preparer) | Calc # | Preparer Sign date | Reviewer | Review % Complete | Reviewer Sign date | WP Form | WBS | Job # (WAF) | Act ID | Comments
31 | Vacuum Vessel | WBS 12 | Lid/Spoke Assembly, Upper and Lower | P.Titus/Smith | Smith | 80 | 2011-02-22 | 2011-03-04 | NSTXU-CALC-12-08-00 |  |  |  |  | 1677 | 1.1.2 | 1205 | 31 & 89
49 | Toroidal Field Coils | WBS 132 | Analysis of TF Outer Leg | Han Zhang | Smith | 80 | 2010-10-27 | 2011-03-04 | NSTXU-CALC-132-04-00 |  |  |  |  | 1677 | 1.1.2 | 1201 | 0031, 0032
22 | Vacuum Vessel | WBS 12 | OPERA 2D Disruption Analyses (Just needs writeup) | Hatcher | Titus | 90 | 2011-01-17 | 2011-03-04 | NSTXU-CALC-12-03-00 |  | A.Brooks |  |  | 1511 | 1.1.1 | 1002 | 0014
8 | Torus Systems | WBS 10 | VV Leg | P.Titus | Smith | 50 | 2010-11-30 | 2011-03-08 | NSTXU-CALC-10-02-00 |  |  |  |  | 1677 | 1.1.2 | 1207 | 0032 | Per M Smith email
30 | Vacuum Vessel | WBS 12 | Umbrella Reinforcement Details | P. Titus | Smith | 60 | 2011-02-22 | 2011-03-08 | NSTXU-CALC-12-07-00 |  | Han Zhang |  |  | 1677 | 1.1.2 | 1205 | 0029 0090
23 | Vacuum Vessel | WBS 12 | PF2 Bolting and Bracket Stress | P. Titus | Smith | 80 | 2011-02-01 | 2011-03-08 | NSTXU-CALC-12-03-00 |  | M.Smith |  |  | 1677 | 1.1.2 | 1202 | 0032
24 | Vacuum Vessel | WBS 12 | PF3 Bolting, Bracket, and weld Stress | P. Titus | Smith | 80 | 2011-02-01 | 2011-03-08 | NSTXU-CALC-12-04-00 |  | M.Smith |  |  | 1677 | 1.1.2 | 1203 | 0032
70 | Center Stack | WBS 133 | Structural Analysis of the PF1 Coils, leads and Supports, Rev 1 | L.Myatt | Chrzanowski | 10 |  | 2011-03-08 | NSTXU-CALC-133-01-01 |  | A.Khodak? |  |  | 1672
5 | Torus Systems | WBS 10 | Full Load Inventory | P.Titus | Titus | 40 | 2010-12-15 | 2011-03-08 | NSTXU-CALC-10-01-02 |  |  |  |  | 1511 | 1.1.1 | 1000 | 0016 | Per M Smith email
4 | Torus Systems | WBS 10 | Leg and Brace Hiltis | P. Titus | Smith | 50 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-10-01-02 |  | M.Smith |  |  | 1677 | 1.1.2 | 1207 | 0032
32 | Vacuum Vessel | WBS 12 | Pedestal Analysis | P.Titus/Smith | Smith | 50 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-12-09-00 |  |  |  |  | 1677 | 1.1.2 | 1206 | 0029 0032
97 | General Power Systems | WBS 55 | Bus Bar Analysis ?????? | A. Khodak | Smith | 60 | 2011-02-08 | 2011-03-08 | NSTXU-CALC-55-01-00 |  | H.Zhang? |  |  | 1672 | 1.5.5 | 5501 | 0049-0076
20 | Vacuum Vessel | WBS 12 | Update of Analysis of Vacuum Vessel & Passive Plates | P.Titus | Titus | 65 | 2011-01-05 | 2011-03-08 | NSTXU-CALC-12-01-01 |  |  |  |  | 1511 | 1.1.1 | 1002 | 0019
3 | Torus Systems | WBS 10 | Torques to Lids and TF Teeth | P. Titus | Smith | 75 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-10-01-02 |  | A.Zolfaghari |  |  | 1677 | 1.1.2 | 1201 | 0031
9 | Torus Systems | WBS 10 | VV Interface Welds | P.Titus | Smith | 75 | 2010-11-30 | 2011-03-08 | NSTXU-CALC-10-02-00 |  |  |  |  | 1677 | 1.1.2 | 1207 | 0032
21 | Vacuum Vessel | WBS 12 | Dome/PF Rib Stresses | P.Titus | Smith | 75 | 2011-02-01 | 2011-03-08 | NSTXU-CALC-12-02-00 |  | M.Smith |  |  | 1677 | 1.1.2 | 1220 | 0016
65 | Toroidal Field Coils | WBS 132 | Analysis of Knuckle Clevis | P. Titus | Smith | 75 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-09-00 |  |  |  |  | 1677 | 1.1.2 | 1201 | 0031, 0032
50 | Toroidal Field Coils | WBS 132 | Loads at Knuckle Clevis | Han Zhang | Smith | 80 | 2011-03-08 | 2011-03-11 | NSTXU-CALC-132-04-00 |  |  |  |  | 1677 | 1.1.2 | 1201 | 0031, 0032
51 | Toroidal Field Coils | WBS 132 | Loads and Moments on Ring | Han Zhang | Smith | 80 | 2011-03-08 | 2011-03-11 | NSTXU-CALC-132-04-00 |  |  |  |  | 1677 | 1.1.2 | 1201 | 0031, 0032
52 | Toroidal Field Coils | WBS 132 | Outer Leg Insulation Bond Shear Stress | Han Zhang | Chrzanowski | 80 | 2011-03-01 | 2011-03-11 | NSTXU-CALC-132-04-00 |  |  |  |  | 1672 | 1.1.3 | 1304 | 0210
53 | Toroidal Field Coils | WBS 132 | Umbrella Rinforcement | Han Zhang | Smith | 80 | 2011-03-08 | 2011-03-11 | NSTXU-CALC-132-04-00 |  |  |  |  | 1677 | 1.1.2 | 1205 | 0029 0037
76 | Center Stack | WBS 133 | OH Coax Lead Analysis | M. Mardenfeld | Chrzanowski | 15 | 2010-09-10 | 2011-03-15 | NSTXU-CALC-133-07-00 |  |  |  |  | 1677 | 1.1.3 | 1305 | 120
17 | Plasma Facing Components | WBS 11 | Fastener Analysis | A.Brooks | Tresemer | 60 | 2011-01-10 | 2011-03-15 | NSTXU-CALC-11-04-00 |  |  |  |  | 1707 | 1.1.1 | 1001 | 0041
16 | Plasma Facing Components | WBS 11 | Final Tile Stress Analysis (ATJ Tiles) | A.Brooks | Tresemer | 90 | 2010-11-19 | 2011-03-15 | NSTXU-CALC-11-03-00 |  |  |  |  | 1707 | 1.1.1 | 1001 | 0040
54 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Analysis ????? | Han Zhang | Chrzanowski | 90 | 2010-12-01 | 2011-03-18 | NSTXU-CALC-132-05-00 |  |  |  |  | 1672 | 1.1.3 | 1304 | 0220
81 | Center Stack | WBS 133 | OH & PF1 Electromagnectic Stability Analysis | P. Titus/Zolfaghari | Chrzanowski | 50 |  | 2011-03-21 | NSTXU-CALC-133-11-00 |  |  |  |  | 1672 | 1.1.3 | 1307 | 1050
2 | Torus Systems | WBS 10 | Global Model | P.Titus | Titus | 80 | 2011-01-17 | 2011-03-21 | NSTXU-CALC-10-01-02 |  | Group |  |  | 1511 | 1.1.1 | 1000 | 0011 | Replaces Calc-13-01-01
67 | Toroidal Field Coils | WBS 132 | Ring Bolted Joint | Peter Rogoff | Smith | 75 | 2011-03-08 | 2011-03-22 | NSTXU-CALC-132-11-00 |  |  |  |  | 1677 | 1.1.2 | 1201 | 0031, 0032
25 | Vacuum Vessel | WBS 12 | PF4 and 5 Support Analysis | P. Titus | Smith | 80 | 2011-03-22 | 2011-03-22 | NSTXU-CALC-12-05-00 |  | M.Smith |  |  | 1677 | 1.1.2 | 1208 | 0029-0032
26 | Vacuum Vessel | WBS 12 | PF4 and 5 Lead Support Analysis | P. Titus | Smith | 80 | 2011-03-22 | 2011-03-22 | NSTXU-CALC-12-05-00 |  | M.Smith |  |  | 1677 | 1.1.2 | 1204 | 0032
91 | NBI | WBS 24 | Magnetic Shielding Calculation | L. Bryant | Priniski | 60 | 2010-11-24 | 2011-04-08 | NSTXU-CALC-24-04-00 |  | A. Brooks |  |  |  | 1.2.4 | 2485 | 0016A
79 | CentStack | WBS 133 | Centerstack Manufacturing Fixtures |  | Chrzanowski | 0 | 2011-08-15 | 2011-12-01 | NSTXU-CALC-133-12-00 |  |  |  |  | 1672 | 1.1.4 | 1302 | 140
69 | Center Stack | WBS 133 | Structural Analysis of the PF1 Coils, leads and Supports | L.Myatt | Chrzanowski | 100 | 2010-08-19 | 2010-12-07 | NSTXU-CALC-133-01-00 |  |  |  |  | 1672 | 1.1.3 | 1306 | 1020
27 | Vacuum Vessel | WBS 12 | Alunimum Block | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 | 2011-02-10 | M.Smith | 20 |  | 1677 | 1.1.2 | 1205 | 0029 0037 | Per M Smith email
28 | Vacuum Vessel | WBS 12 | TFO Leg | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 |  |  |  |  | 1677 | 1.1.2 | 1205 | 0029, 0037 | Moments Loads
29 | Vacuum Vessel | WBS 12 | Bolt details | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 |  |  |  |  | 1677 | 1.1.2 | 1205 | 0029, 0037 | Moments Loads
82 | Center Stack | WBS 133 | CS Casing Halo Ind and Res Cur | A.Brooks | Chrzanowski | 100 | 2010-12-01 | 2010-12-15 | [5 empty] | 1672 | 1.1.3 | 1307 | 1050
78 | Center Stack | WBS 133 | OH Fatigue and Fracture Mechanics | P. Titus | Chrzanowski | 100 | 2010-09-10 | 2011-01-15 | NSTXU-CALC-133-09-00 | 2011-02-04 | I. Zatz | 100 | 2011-02-28 | 1672 | 1.1.3 | 1302 | 140
61 | Toroidal Field Coils | WBS 132 | DLF for Disruption | T.Willard | Chrzanowski | 100 | 2010-12-15 | 2011-01-24 | NSTXU-CALC-132-06-01 | 2011-02-03 | A.Zolfaghari? | 100 | 2011-02-03 | 1672 | 1.1.3 | 1304 | 0230
85 | NBI | WBS 24 | Vessel Port Re-Work for NB and Thompson Scattering Port | T. Willard | Priniski / Labik | 100 | 2011-01-05 | 2011-01-24 | NSTXU-CALC-24-01-00 |  | A.Zolfaghari | 100 | 2011-02-03 | 1627/1506 | 1.2.4 | 2480 | 0035
86 | NBI | WBS 24 | NB Reinforcement | T. Willard | Priniski | 100 | 2011-02-25 | 2011-01-24 | NSTXU-CALC-24-01-00 |  |  |  |  | 1506 | 1.2.4 | 2480 | 0037
87 | NBI | WBS 24 | Thompson Scattering Port | T. Willard | Labik | 100 | 2011-01-05 | 2011-01-24 | NSTXU-CALC-24-01-00 |  |  |  |  | 1627 | 1.4.5 | 4500 | 0009
39 | Magnet Systems | WBS 13 | DCPS Moment Influence Coefficients | Wooley/Titus | R.Hatcher | 100 | 2010-12-15 | 2011-01-30 | NSTXU-CALC-13-05-00 | 2011-02-10 | Woolley |  |  | 1511 | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
43 | Polodal Field Coils | WBS 131 | Poloidal Magnetic Quantites for the May 2010 Design Point | Woolley | Chrzanowski | 100 |  | 2011-01-30 | NSTXU-CALC 131-03-00 | 2011-02-10 | P.Titus |  |  | 1672
48 | Toroidal Field Coils | WBS 132 | Torque Egns for Design Point | Wooley | Titus | 100 | 2011-01-17 | 2011-01-31 | NSTXU-CALC-132-03-00 |  |  |  |  | 1511 | 1.1.0 | 1000 | 0011
80 | Center Stack | WBS 133 | Center Stack Casing Bellows | Peter Rogoff | Chrzanowski | 100 |  | 2011-01-31 | NSTXU-CALC-133-10-00 | 2011-02-17 |  |  |  | 1672 | 1.1.3 | 1307 | 1050
62 | Toroidal Field Coils | WBS 132 | Maximum Torsional Shear Stress | P. Titus | Chrzanowski | 100 | 2010-12-15 | 2011-02-01 | NSTXU-CALC-132-07-00 | 2011-02-11 |  |  |  | 1672 | 1.1.3 | 1304 | 0230
7 | Torus Systems | WBS 10 | Seismic Analysis | P.Titus | Titus | 100 | 2011-01-17 | 2011-02-10 | NSTXU-CALC-10-02-00 | 2011-02-10 | F. Dahlgren |  |  | 1511 | 1.1.1 | 1000 | 0011
11 | Plasma Facing Components | WBS 11 | Heat Balance | A.Brooks | Chrzanowski | 100 |  |  | NSTXU-CALC-11-01-00 | 2011-02-21 | H.Zhang |  |  | 1672 | 1.1.1 | 1307 | 0011
12 | Plasma Facing Components | WBS 11 | Sizing of Coolant Capabilities | A.Brooks | Chrzanowski | 100 | 2010-06-01 |  | NSTXU-CALC-11-01-00 |  |  |  |  | 1672 | 1.3.2 | 3200 | 0023
13 | Plasma Facing Components | WBS 11 | Divertor Tile Thermal Stress (CFC Tiles) | A.Brooks | Tresemer | 100 |  |  | NSTXU-CALC-11-01-00 |  |  |  |  | 1707 | 1.1.1 | 1001
14 | Plasma Facing Components | WBS 11 | General Tile Program | J. Boales | Tresemer | 100 |  |  | NSTXU-CALC-11-02-00 |  | A. Brooks |  |  | 1707 | 1.1.1 | 1001 | 0040
15 | Plasma Facing Components | WBS 11 | Inner CS Casing Tile Stress | J. Boales | Tresemer | 100 |  |  | NSTXU-CALC-11-02-00 |  |  |  |  | 1707 | 1.1.1 | 1001
19 | Vacuum Vessel | WBS 12 | Disruption Analysis of Vacuum Vessel and Passive Plates | P.Titus | Titus | 100 |  |  | NSTXU-CALC-12-01-00 |  |  |  |  | 1511 | 1.1.1 | 1002 | 0016
36 | Magnet Systems | WBS 13 | NSTX Influence Matrix | Hatcher | Titus | 100 |  |  | NSTXU-CALC-13-03-00 | 2011-02-11 | P.Titus |  |  | 1511 | 1.1.3 | 1300 | 0010
37 | Magnet Systems | WBS 13 | DCPS Force Influence Coefficients | Hatcher | R.Hatcher | 100 | 2010-11-24 |  | NSTXU-CALC-13-03-01 |  |  |  |  | 1511 | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
41 | Polodal Field Coils | WBS 131 | Analysis of CSU Poloidal Field Coils | Woolley | Chrzanowski | 100 |  |  | NSTXU-CALC 131-01-00 |  |  |  |  | 1672 | 1.1.3 | 1306 | 1020
42 | Polodal Field Coils | WBS 131 | Poloidal Magnetic Quantites for the Feb 2010 Provisional Design | Woolley | Chrzanowski | 100 |  |  | NSTXU-CALC 131-02-00 | 2011-02-10 | P.Titus |  |  | 1672 | 1.1.3 | 1306 | 1020
47 | Toroidal Field Coils | WBS 132 | OOP PF/TF Torques on TF | Wooley | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-03-00 |  |  |  |  | 1672 | 1.1.3 | 1304 | 0220
55 | Toroidal Field Coils | WBS 132 | Cooldown of Flex | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | 1672 | 1.1.3 | 1304 | 0220
56 | Toroidal Field Coils | WBS 132 | Benchmarh I^2 t Calcs | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | 1672 | 1.1.3 | 1304 | 0220
57 | Toroidal Field Coils | WBS 132 | TF Peak Temps at Corner | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | 1672 | 1.1.3 | 1304 | 0220
58 | Toroidal Field Coils | WBS 132 | TF Flex Joint and Bundle Stub | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  |  |  |  | 1672 | 1.1.3 | 1304 | 0230
59 | Toroidal Field Coils | WBS 132 | Joint Electrical Contact Resistance | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  |  |  |  | 1672 | 1.1.3 | 1304 | 0220
60 | Toroidal Field Coils | WBS 132 | Flex Stress for Inplane and OOP Loads | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  |  |  |  | 1672 | 1.1.3 | 1304 | 1030
63 | Toroidal Field Coils | WBS 132 | Determination of shear Forces Between the TF conductors and Insulation and the G-10 Insulating Crown. | A. Zolfaghari | Chrzanowski | 100 |  |  | NSTXU-CALC-132-08-00 | 2011-02-11 | T.Willard | 100 | 2011-02-10 | 1672 | 1.1.3 | 1304 | 0230
64 | Toroidal Field Coils | WBS 132 | TF Flag Key | A. Zolfaghari | Chrzanowski | 100 | 2011-01-05 |  | NSTXU-CALC-132-08-00 |  |  |  |  | 1672 | 1.1.3 | 1304 | 0190 & 0210
66 | Toroidal Field Coils | WBS 132 | TF Cooldown using FCOOL | A. Zolfaghari | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-10-00 | 2011-02-10 | M.Kalish? | 100 |  | 1672 | 1.1.3 | 1304 | 0230
71 | Center Stack | WBS 133 | Thermal Stresses on OH-TF Coils | S.Avasarala | Chrzanowski | 100 |  |  | NSTXU-CALC-133-02-00 | 2011-02-10 | Han Zhang |  |  | 1672 | 1.1.3 | 1307 | 1050
72 | Center Stack | WBS 133 | Center Stack Casing Disruption Inductive and Halo Current Loads | P.Titus | Chrzanowski | 100 | 2010-08-12 |  | NSTXU-CALC-133-03-00 | 2011-02-10 | P.Titus |  |  | 1672 | 1.1.3 | 1307 | 1030
73 | Center Stack | WBS 133 | OH Preload System and Belleville Spring Design | Peter Rogoff | Chrzanowski | 100 |  |  | NSTXU-CALC-133-04-00 | 2011-02-11 | T.Kozub/Test |  |  | 1672 | 1.1.3 | 1302
74 | Center Stack | WBS 133 | Halo Current Analysis of Center Stack Casing | A.Brooks | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-133-05-00 | 2011-02-21 |  |  |  | 1672 | 1.1.3 | 1307 | 1050
75 | Center Stack | WBS 133 | OH Coolant Hole Optimization | A. Zolfaghari | Chrzanowski | 100 |  |  | NSTXU-CALC-133-06-00 | 2011-02-11 | M.Mardenfeld |  |  | 1672 | 1.1.3 | 1305 | 100
77 | Center Stack | WBS 133 | OH Stress Analyses | A. Zolfaghari | Chrzanowski | 100 | 2010-07-29 |  | NSTXU-CALC-133-08-00 | 2011-02-11 | F. Dahlgren |  |  | 1672 | 1.1.3 | 1305 | 100
88 | NBI | WBS 24 | Armor Plate Backing Plate | L. Bryant | Priniski | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00 | 2011-02-28 | I. Zatz |  |  | 1508 | 1.2.4 | 2460 | 0026
89 | NBI | WBS 24 | Disruption Loading | L. Bryant | Priniski | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00 |  |  |  |  | 1508 | 1.2.4 | 2460 | 0026
92 | NBI | WBS 24 | HHFW Antenna (needs to be modified for upgrade loads) | Han Zhang/Ellis | Bob Ellis | 100 | 2011-01-15 |  | NSTXU-CALC-24-03-00 |  | R.Hatcher |  |  | 1511 | 1.2.4
94 | Diagnostics | WBS 41 | Diagnostics Review and Database | J. Boales | Titus | 100 | 09/01/10 |  | NSTXU-CALC-40-01-00 |  | Bob Kiata to assign? |  |  | 1511 | 1.2.3 | 2300 | 0015
83 | Center Stack | WBS 133 | CS Casing Static and Dynamic | A.Brooks | Chrzanowski | Duplicate | 2010-12-01 | 2010-12-15 | [5 empty] | 1672 | 1.1.3 | 1307 | 1050
38 | Magnet Systems | WBS 13 | DCPS TF Inner Leg Torsional Shear Stress | P. Titus | R.Hatcher | N/A | 2010-10-27 | 2011-01-28 | NSTXU-CALC-13-04-00 |  |  |  |  | 1511 | 1.5.2 | 5200 | R.Hatcher | Incorp into Calc NSTXU-CALC-132-07-00
6 | Torus Systems | WBS 10 | Pedestal Loads | P. Titus | Smith | N/A | 2011-03-08 |  | NSTXU-CALC-10-01-02 |  | M.Smith |  |  | 1677 | 1.1.2 | 1206 | 0029 0032 | See Calc NSTXU-CALC-12-09-00
34 | Magnet Systems | WBS 13 | Global Model | P. Titus | Titus | N/A | N/A |  | NSTX-CALC-13-01-01 |  |  |  |  | 1511
35 | Magnet Systems | WBS 13 | Maximum & Minimum Loads on the NSTX OH & PF Coils, & Coil Groupings | P.Titus | Titus | N/A | N/A |  | NSTX-CALC-13-02-00 |  |  |  |  | 1511
45 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Diffusion Analysis(to be superceded by #48) | P.Titus | Chrzanowski | N/A | 2010-12-01 |  | NSTXU-CALC-132-01-00 |  |  |  |  | 1672 | 1.1.3 | 1304
46 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Analysis (to be superceded by #48) | P.Titus | Chrzanowski | N/A | 2010-12-01 |  | NSTXU-CALC-132-02-00 |  |  |  |  | 1672 | 1.1.3 | 1304
90 | NBI | WBS 24 | Thermal Stress Analysis(Not Req per Craig P.) | L. Bryant | Priniski | N/R | 2011-02-21 |  | NSTXU-CALC-24-02-00 |  |  |  |  | 1508 | 1.2.4 | 2460 | 0026 | Not Req per Craig P.
95 | Diagnostics | WBS 41 | Thomson Scattering Port | Labik | Kaita | N/R |  |  | NSTXU-CALC-40-02-00 |  |  |  |  | 1627 | 1.4.0 | 4500 |  | Covered under Vessel Port Re-Work for NB and Thompson Scattering Port #23
1 | Torus Systems | WBS 10
10 | Plasma Facing Components | WBS 11
18 | Vacuum Vessel | WBS 12
33 | Magnet Systems | WBS 13
40 | Polodal Field Coils | WBS 131
44 | Toroidal Field Coils | WBS 132
68 | Center Stack | WBS 133
84 | NBI | WBS 24
93 | Diagnostics | WBS 41
96 | General Power Systems | WBS 55
1672
[6 empty] | 2010-12-13 | 2010-12-20 | 2010-12-27 | 2011-01-03 | 2011-01-10 | 2011-01-17 | 2011-01-24 | 2011-01-31 |  | 2011-02-07 | 2011-02-14 | 2011-02-21 | 2011-02-28 | 2011-03-07 | 2011-03-14 | 2011-03-21 | 2011-03-28 | 2011-04-04 | 2011-04-11 | 2011-04-18 | 2011-04-25 | 2011-05-02
[5 empty] | Avg PCT | 70% | 70% | 70% | 72% | 74% | 78%
[5 empty] | at100% and forecast | 31 | 31 | 31 | 32 | 32 | 40 | 45 | 50 |  | 53 | 54 | 55 | 57 | 59 | 69 | 69 | 70 | 72
[5 empty] | Plan completion (1/1/2011) | 31 | 31 | 31 | 32 | 36 | 44 | 49 | 54 |  | 57 | 58 | 59 | 61 | 72 | 72 | 72 | 72
[5 empty] | # checked | 0 | 0 | 0 | 0
[5 empty] | Forecast completion by month | [5 empty] | 8 | 5 | 5 |  | 3 | 1 | 1 | 2 | 2 | 10 | 0 | 1 | 2
20110105 NSTX UPGRADE Calculations-RTS_11112010.xls

## Sheet2
Line # | Preparation % Complete | Schedule Date (COG) | Forecast Date (Preparer) | Calc #
88 | N/R | 2011-02-21 |  | NSTXU-CALC-24-02-00
33 | N/A | N/A |  | NSTX-CALC-13-01-01
93 | N/A |  |  | NSTXU-CALC-40-02-00
10 | 100 |  |  | NSTXU-CALC-11-01-00
11 | 100 | 2010-06-01 |  | NSTXU-CALC-11-01-00
12 | 100 |  |  | NSTXU-CALC-11-01-00
13 | 100 |  |  | NSTXU-CALC-11-02-00
14 | 100 |  |  | Will be part of the above calc
18 | 100 |  |  | NSTXU-CALC-12-01-00
26 | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00
27 | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00
28 | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00
34 | 100 | N/A |  | NSTX-CALC-13-02-00
35 | 100 |  |  | NSTXU-CALC-13-03-00
36 | 100 | 2010-11-24 |  | NSTXU-CALC-13-03-01
40 | 100 |  |  | NSTXU-CALC 131-01-00
41 | 100 |  |  | NSTXU-CALC 131-02-00
44 | 100 | 2010-12-01 |  | NSTXU-CALC-132-01-00
45 | 100 | 2010-12-01 |  | NSTXU-CALC-132-02-00
46 | 100 | 2010-12-01 |  | NSTXU-CALC-132-03-00
54 | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00
55 | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00
56 | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00
57 | 100 |  |  | NSTXU-CALC-132-06-00
58 | 100 |  |  | NSTXU-CALC-132-06-00
59 | 100 |  |  | NSTXU-CALC-132-06-00
62 | 100 |  |  | NSTXU-CALC-132-08-00
66 | 100 | 2010-12-01 |  | NSTXU-CALC-132-11-00
68 | 100 | 2010-08-19 | 2010-12-07 | NSTXU-CALC-133-01-00
70 | 100 |  |  | NSTXU-CALC-133-02-00
71 | 100 | 2010-08-12 |  | NSTXU-CALC-133-03-00
72 | 100 |  |  | NSTXU-CALC-133-04-00
73 | 100 | 2010-12-01 |  | NSTXU-CALC-133-05-00
74 | 100 |  |  | NSTXU-CALC-133-06-00
76 | 100 | 2010-07-29 |  | NSTXU-CALC-133-08-00
77 | 100 | 2010-09-10 | 2011-01-15 | NSTXU-CALC-133-09-00
80 | 100 | 2010-12-01 | 2010-12-15
81 | 100 | 2010-12-01 | 2010-12-15
86 | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00
87 | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00
92 | 100 | 09/01/10 |  | NSTXU-CALC-40-01-00 | 41
8 | 50 | 2010-11-30 | 2010-11-30
7 |  | 2010-11-30 | 2010-11-30
63 | 90 | 2011-01-05 | 2011-01-05 | NSTXU-CALC-132-08-00
16 | 29 | 2011-01-10 | 2011-01-10 | NSTXU-CALC-11-04-00
61 | 75 | 2010-12-15 | 2011-01-15 | NSTXU-CALC-132-07-00
60 |  | 2010-12-15 | 2011-01-15 | NSTXU-CALC-132-06-01
90 | 90 | 2011-01-15 | 2011-01-15 | NSTXU-CALC-24-03-00
79 | 90 |  | 2011-01-15 | NSTXU-CALC-133-10-00
21 | 90 | 2011-01-17 | 2011-01-17 | NSTXU-CALC-12-03-00
2 | 60 | 2011-01-17 | 2011-01-17 | NSTXU-CALC-10-01-02
83 | 90 | 2011-01-05 | 2011-01-19 | NSTXU-CALC-24-01-00
85 | 90 | 2011-01-05 | 2011-01-19 | NSTXU-CALC-24-01-00
84 | 90 | 2011-02-25 | 2011-01-19 | NSTXU-CALC-24-01-00
15 | 80 | 2010-11-19 | 2011-01-20 | NSTXU-CALC-11-03-00
19 | 65 | 2011-01-05 | 2011-01-20 | NSTXU-CALC-12-01-01 | 15
37 | 50 | 2010-10-27 | 2011-01-28 | NSTXU-CALC-13-04-00 | 1
38 | 95 | 2010-12-15 | 2011-01-31 | NSTXU-CALC-13-05-00
42 | 95 |  | 2011-01-31 | NSTXU-CALC 131-03-00
48 | 60 | 2010-10-27 | 2011-01-31 | NSTXU-CALC-132-04-00
53 | 50 | 2010-12-01 | 2011-01-31 | NSTXU-CALC-132-05-00
47 | 95 | 2011-01-17 | 2011-01-31 | Will be part of the above calc
20 | 75 | 2011-02-01 | 2011-02-01 | NSTXU-CALC-12-02-00
22 | 75 | 2011-02-01 | 2011-02-01 | NSTXU-CALC-12-03-00
23 | 75 | 2011-02-01 | 2011-02-01 | NSTXU-CALC-12-04-00 | 8
95 | 30 | 2011-02-08 | 2011-02-08 | NSTXU-CALC-55-01-00 | 1
75 | 10 | 2010-09-10 | 2011-02-15 | NSTXU-CALC-133-07-00 | 1
30 | 75 | 2011-02-22 | 2011-02-22 | NSTXU-CALC-12-08-00
29 | 40 | 2011-02-22 | 2011-02-22 | NSTXU-CALC-12-07-00 | 2
51 | 60 | 2011-03-01 | 2011-03-01 | NSTXU-CALC-132-04-00
69 | 0 |  | 2011-03-01 | NSTXU-CALC-133-01-01 | 2
5 | 30 | 2010-12-15 | 2011-03-08 | NSTXU-CALC-10-01-02
3 | 75 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-10-01-02
64 | 75 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-09-00
49 | 60 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-04-00
50 | 60 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-04-00
52 | 60 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-04-00
31 | 50 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-12-09-00
65 | 50 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-10-00
6 | 10 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-10-01-02
4 | 5 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-10-01-02 | 10
24 | 75 | 2011-03-22 | 2011-03-22 | NSTXU-CALC-12-05-00
25 | 75 | 3/9-3/22 | 2011-03-22 | NSTXU-CALC-12-05-00 | 2
89 | 60 | 2010-11-24 | 2011-03-30 | Initial calc complete and will be filed, 3D calc to be performed. Needs Calc # | 2
78 |  | 2011-08-15 | 2011-08-15 |  | 44
| 6359 |  |  |  | 44
[5 empty] | 85 | 74.8118

## Sheet3
Line # | WBS Name | WBS | Calc Title | Preparer | COG | Preparation % Complete | Schedule Date (COG) | Forecast Date (Preparer) | Calc # | Preparer Sign date | Reviewer | Review % Complete | Reviewer Sign date | WBS | Job # (WAF) | Act ID | Comments
95 | General Power Systems | WBS 55 | Bus Bar Analysis | A. Khodak | Smith | 30 | 2011-02-08 |  | NSTXU-CALC-55-01-00 |  | H.Zhang? |  |  | 1.5.5 | 5501 | 0049-0076
63 | Toroidal Field Coils | WBS 132 | TF Flag Key | A. Zolfaghari | Chrzanowski | 90 | 2011-01-05 |  | NSTXU-CALC-132-08-00 |  | T.Willard |  |  | 1.1.3 | 1304 | 0190 & 0210
16 | Plasma Facing Components | WBS 11 | Fastener Analysis | A.Brooks | Tresemer | 29 | 2011-01-10 |  | NSTXU-CALC-11-04-00 |  |  |  |  | 1.1.1 | 1001 | 0041
15 | Plasma Facing Components | WBS 11 | Final Tile Stress Analysis (ATJ Tiles) | A.Brooks | Tresemer | 80 | 2011-01-20 | 2011-01-20 | NSTXU-CALC-11-03-00 |  |  |  |  | 1.1.1 | 1001 | 0040
90 | NBI | WBS 24 | HHFW Antenna (needs to be modified for upgrade loads) | Han Zhang | Bob Ellis | 90 | 2011-01-15 |  | NSTXU-CALC-24-03-00 |  | R.Hatcher |  |  | 1.2.4
53 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Analysis | Han Zhang | Chrzanowski | 50 | 2011-01-31 | 2011-01-31 | NSTXU-CALC-132-05-00 |  |  |  |  | 1.1.3 | 1304 | 0220
48 | Toroidal Field Coils | WBS 132 | Analysis of TF Outer Leg | Han Zhang | Smith | 60 | 2011-01-31 | 2011-01-31 | NSTXU-CALC-132-04-00 |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
29 | Vacuum Vessel | WBS 12 | Umbrella Reinforcement Details | Han Zhang | Smith | 40 | 2011-02-22 |  | NSTXU-CALC-12-07-00 |  | P.Titus / H.Zhang |  |  | 1.1.2 | 1205 | 0029 0090
51 | Toroidal Field Coils | WBS 132 | Outer Leg Insulation Bond Shear Stress | Han Zhang | Chrzanowski | 60 | 2011-03-01 |  | NSTXU-CALC-132-04-00 |  |  |  |  | 1.1.3 | 1304 | 0210
49 | Toroidal Field Coils | WBS 132 | Loads at Knuckle Clevis | Han Zhang | Smith | 60 | 2011-03-08 |  | NSTXU-CALC-132-04-00 |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
50 | Toroidal Field Coils | WBS 132 | Loads and Moments on Ring | Han Zhang | Smith | 60 | 2011-03-08 |  | NSTXU-CALC-132-04-00 |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
52 | Toroidal Field Coils | WBS 132 | Umbrella Rinforcement | Han Zhang | Smith | 60 | 2011-03-08 |  | NSTXU-CALC-132-04-00 |  |  |  |  | 1.1.2 | 1205 | 0029 0037
21 | Vacuum Vessel | WBS 12 | OPERA 2D Disruption Analyses (Just needs writeup) | Hatcher | Titus | 90 | 2011-01-17 |  | NSTXU-CALC-12-03-00 |  | A.Brooks |  |  | 1.1.1 | 1002 | 0014
89 | NBI | WBS 24 | Magnetic Shielding Calculation | L. Bryant | Priniski | 60 | 2011-03-30 | 2011-03-30 | Initial calc complete and will be filed, 3D calc to be performed. Needs Calc # |  | A. Brooks |  |  | 1.2.4 | 2485 | 0016A
69 | Center Stack | WBS 133 | Structural Analysis of the PF1 Coils, leads and Supports, Rev 1 | L.Myatt | Chrzanowski | 0 | 2011-03-01 | 2011-03-01 | NSTXU-CALC-133-01-01
75 | Center Stack | WBS 133 | OH Coax Lead Analysis | M. Mardenfeld | Chrzanowski | 10 | 2011-02-15 | 2011-02-15 | NSTXU-CALC-133-07-00 |  |  |  |  | 1.1.3 | 1305 | 120
61 | Toroidal Field Coils | WBS 132 | Maximum Torsional Shear Stress | P. Titus | Chrzanowski | 75 | 2011-01-15 | 2011-01-15 | NSTXU-CALC-132-07-00 |  |  |  |  | 1.1.3 | 1304 | 0230
22 | Vacuum Vessel | WBS 12 | PF2 Bolting and Bracket Stress | P. Titus | Smith | 75 | 2011-02-01 |  | NSTXU-CALC-12-03-00 |  | M.Smith |  |  | 1.1.2 | 1202 | 0032
23 | Vacuum Vessel | WBS 12 | PF3 Bolting, Bracket, and weld Stress | P. Titus | Smith | 75 | 2011-02-01 |  | NSTXU-CALC-12-04-00 |  | M.Smith |  |  | 1.1.2 | 1203 | 0032
4 | Torus Systems | WBS 10 | Leg and Brace Hiltis | P. Titus | Smith | 5 | 2011-03-08 |  | NSTXU-CALC-10-01-02 |  | M.Smith |  |  | 1.1.2 | 1207 | 0032
6 | Torus Systems | WBS 10 | Pedestal Loads | P. Titus | Smith | 10 | 2011-03-08 |  | NSTXU-CALC-10-01-02 |  | M.Smith |  |  | 1.1.2 | 1206 | 0029 0032
3 | Torus Systems | WBS 10 | Torques to Lids and TF Teeth | P. Titus | Smith | 75 | 2011-03-08 |  | NSTXU-CALC-10-01-02 |  | A.Zolfaghari |  |  | 1.1.2 | 1201 | 0031
64 | Toroidal Field Coils | WBS 132 | Analysis of Knuckle Clevis | P. Titus | Smith | 75 | 2011-03-08 |  | NSTXU-CALC-132-09-00 |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
24 | Vacuum Vessel | WBS 12 | PF4 and 5 Support Analysis | P. Titus | Smith | 75 | 2011-03-22 |  | NSTXU-CALC-12-05-00 |  | M.Smith |  |  | 1.1.2 | 1208 | 0029-0032
25 | Vacuum Vessel | WBS 12 | PF4 and 5 Lead Support Analysis | P. Titus | Smith | 75 | 3/9-3/22 |  | NSTXU-CALC-12-05-00 |  | M.Smith |  |  | 1.1.2 | 1204 | 0032
2 | Torus Systems | WBS 10 | Global Model | P.Titus | Titus | 60 | 2011-01-17 |  | NSTXU-CALC-10-01-02 |  | Group |  |  | 1.1.1 | 1000 | 0011 | Replaces Calc-13-01-01
19 | Vacuum Vessel | WBS 12 | Update of Analysis of Vacuum Vessel & Passive Plates | P.Titus | Titus | 65 | 2011-01-20 | 2011-01-20 | NSTXU-CALC-12-01-01 |  |  |  |  | 1.1.1 | 1002 | 0019
20 | Vacuum Vessel | WBS 12 | Dome/PF Rib Stresses | P.Titus | Smith | 75 | 2011-02-01 |  | NSTXU-CALC-12-02-00 |  | M.Smith |  |  | 1.1.2 | 1220 | 0016
5 | Torus Systems | WBS 10 | Full Load Inventory | P.Titus | Titus | 30 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-10-01-02 |  |  |  |  | 1.1.1 | 1000 | 0016 | Per M Smith email
30 | Vacuum Vessel | WBS 12 | Lid/Spoke Assembly, Upper and Lower | P.Titus/Smith | Smith | 75 | 2011-02-22 |  | NSTXU-CALC-12-08-00 |  |  |  |  | 1.1.2 | 1205 | 31 & 89
31 | Vacuum Vessel | WBS 12 | Pedestal Analysis | P.Titus/Smith | Smith | 50 | 2011-03-08 |  | NSTXU-CALC-12-09-00 |  |  |  |  | 1.1.2 | 1206 | 0029 0032
79 | Center Stack | WBS 133 | Center Stack Casing Bellows | Peter Rogoff | Chrzanowski | 90 | 2011-01-15 | 2011-01-15 | NSTXU-CALC-133-10-00 |  |  |  |  | 1.1.3 | 1307 | 1050
65 | Toroidal Field Coils | WBS 132 | Ring Bolted Joint | Peter Rogoff | Smith | 50 | 2011-03-08 |  | NSTXU-CALC-132-10-00 |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
83 | NBI | WBS 24 | Vessel Port Re-Work for NB and Thompson Scattering Port | T. Willard | Priniski / Labik | 90 | 2011-01-19 | 2011-01-19 | NSTXU-CALC-24-01-00 |  | A.Zolfaghari |  |  | 1.2.4 | 2480 | 0035
84 | NBI | WBS 24 | NB Reinforcement | T. Willard | Priniski | 90 | 2011-01-19 | 2011-01-19 | NSTXU-CALC-24-01-00 |  |  |  |  | 1.2.4 | 2480 | 0037
85 | NBI | WBS 24 | Thompson Scattering Port | T. Willard | Labik | 90 | 2011-01-19 | 2011-01-19 | NSTXU-CALC-24-01-00 |  |  |  |  | 1.4.5 | 4500 | 0009
60 | Toroidal Field Coils | WBS 132 | DLF for Disruption | T.Willard | Chrzanowski | 0 | 2011-01-15 | 2011-01-15 | NSTXU-CALC-132-06-01 |  |  |  |  | 1.1.3 | 1304 | 0230
37 | Magnet Systems | WBS 13 | DCPS TF Inner Leg Torsional Shear Stress | Wooley/Titus | R.Hatcher | 50 | 2011-01-28 | 2011-01-28 | NSTXU-CALC-13-04-00 |  |  |  |  | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
38 | Magnet Systems | WBS 13 | DCPS Moment Influence Coefficients | Wooley/Titus | R.Hatcher | 95 | 2011-01-30 | 2011-01-30 | NSTXU-CALC-13-05-00 |  |  |  |  | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
42 | Polodal Field Coils | WBS 131 | Poloidal Magnetic Quantites for the May 2010 Design Point | Woolley | Chrzanowski | 95 | 2011-01-30 | 2011-01-30 | NSTXU-CALC 131-03-00
40 | Polodal Field Coils | WBS 131 | Analysis of CSU Poloidal Field Coils | Woolley | Chrzanowski | 100 |  |  | NSTXU-CALC 131-01-00 |  |  |  |  | 1.1.3 | 1306 | 1020
41 | Polodal Field Coils | WBS 131 | Poloidal Magnetic Quantites for the Feb 2010 Provisional Design | Woolley | Chrzanowski | 100 |  |  | NSTXU-CALC 131-02-00 |  |  |  |  | 1.1.3 | 1306 | 1020
10 | Plasma Facing Components | WBS 11 | Heat Balance | A.Brooks | Chrzanowski | 100 |  |  | NSTXU-CALC-11-01-00 |  | H.Zhang |  |  | 1.1.1 | 1307 | 0011
11 | Plasma Facing Components | WBS 11 | Sizing of Coolant Capabilities | A.Brooks | Chrzanowski | 100 | 2010-06-01 |  | NSTXU-CALC-11-01-00 |  |  |  |  | 1.3.2 | 3200 | 0023
12 | Plasma Facing Components | WBS 11 | Divertor Tile Thermal Stress (CFC Tiles) | A.Brooks | Tresemer | 100 |  |  | NSTXU-CALC-11-01-00 |  |  |  |  | 1.1.1 | 1001
13 | Plasma Facing Components | WBS 11 | General Tile Program | J. Boales | Tresemer | 100 |  |  | NSTXU-CALC-11-02-00 | 2010-10-01 | A. Brooks | A. Brooks |  | 1.1.1 | 1001 | 0040
18 | Vacuum Vessel | WBS 12 | Disruption Analysis of Vacuum Vessel and Passive Plates | S.Avasarala | Titus | 100 |  |  | NSTXU-CALC-12-01-00 |  |  |  |  | 1.1.1 | 1002 | 0016
26 | Vacuum Vessel | WBS 12 | Alunimum Block | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 |  | M.Smith | 10 |  | 1.1.2 | 1205 | 0029 0037 | Per M Smith email
27 | Vacuum Vessel | WBS 12 | TFO Leg | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 |  | M.Smith | 10 |  | 1.1.2 | 1205 | 0029, 0037 | Moments Loads
28 | Vacuum Vessel | WBS 12 | Bolt details | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 |  | M.Smith | 10 |  | 1.1.2 | 1205 | 0029, 0037 | Moments Loads
35 | Magnet Systems | WBS 13 | NSTX Influence Matrix | Hatcher | Titus | 100 |  |  | NSTXU-CALC-13-03-00 |  |  |  |  | 1.1.3 | 1300 | 0010
36 | Magnet Systems | WBS 13 | DCPS Force Influence Coefficients | R.Hatcher | R.Hatcher | 100 | 2010-11-24 |  | NSTXU-CALC-13-03-01 |  |  |  |  | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
46 | Toroidal Field Coils | WBS 132 | OOP PF/TF Torques on TF | Wooley | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-03-00 |  |  |  |  | 1.1.3 | 1304 | 0220
54 | Toroidal Field Coils | WBS 132 | Cooldown of Flex | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | 1.1.3 | 1304 | 0220
55 | Toroidal Field Coils | WBS 132 | Benchmarh I^2 t Calcs | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | 1.1.3 | 1304 | 0220
56 | Toroidal Field Coils | WBS 132 | TF Peak Temps at Corner | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | 1.1.3 | 1304 | 0220
57 | Toroidal Field Coils | WBS 132 | TF Flex Joint and Bundle Stub | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  | A.Zolfaghari? |  |  | 1.1.3 | 1304 | 0230
58 | Toroidal Field Coils | WBS 132 | Joint Electrical Contact Resistance | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  |  |  |  | 1.1.3 | 1304 | 0220
59 | Toroidal Field Coils | WBS 132 | Flex Stress for Inplane and OOP Loads | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  |  |  |  | 1.1.3 | 1304 | 1030
62 | Toroidal Field Coils | WBS 132 | Determination of shear Forces Between the TF conductors and Insulation and the G-10 Insulating Crown. | A. Zolfaghari | Chrzanowski | 100 |  |  | NSTXU-CALC-132-08-00 |  |  |  |  | 1.1.3 | 1304 | 0230
66 | Toroidal Field Coils | WBS 132 | TF Cooldown using FCOOL | A. Zolfaghari | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-11-00 |  | M.Kalish? |  |  | 1.1.3 | 1304 | 0230
68 | Center Stack | WBS 133 | Structural Analysis of the PF1 Coils, leads and Supports | L.Myatt | Chrzanowski | 100 | 2010-08-19 | 2010-12-07 | NSTXU-CALC-133-01-00 |  | A.Khodak? |  |  | 1.1.3 | 1306 | 1020
70 | Center Stack | WBS 133 | Thermal Stresses on OH-TF Coils | S.Avasarala | Chrzanowski | 100 |  |  | NSTXU-CALC-133-02-00 |  |  |  |  | 1.1.3 | 1307 | 1050
71 | Center Stack | WBS 133 | Center Stack Casing Disruption Inductive and Halo Current Loads | P.Titus | Chrzanowski | 100 | 2010-08-12 |  | NSTXU-CALC-133-03-00 | 2010-04-13 | P.Titus |  |  | 1.1.3 | 1307 | 1030
72 | Center Stack | WBS 133 | OH Preload System and Belleville Spring Design | Peter Rogoff | Chrzanowski | 100 |  |  | NSTXU-CALC-133-04-00 |  | T.Kozub/Test |  |  | 1.1.3 | 1302
73 | Center Stack | WBS 133 | Halo Current Analysis of Center Stack Casing | A.Brooks | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-133-05-00 |  |  |  |  | 1.1.3 | 1307 | 1050
74 | Center Stack | WBS 133 | OH Coolant Hole Optimization | A. Zolfaghari | Chrzanowski | 100 |  |  | NSTXU-CALC-133-06-00 |  | M.Mardenfeld |  |  | 1.1.3 | 1305 | 100
76 | Center Stack | WBS 133 | OH Stress Analyses | A. Zolfaghari | Chrzanowski | 100 | 2010-07-29 |  | NSTXU-CALC-133-08-00 |  |  |  |  | 1.1.3 | 1305 | 100
77 | Center Stack | WBS 133 | OH Fatigue and Fracture Mechanics | P. Titus | Chrzanowski | 100 | 2010-09-10 | 2011-01-15 | NSTXU-CALC-133-09-00 |  | I. Zatz |  |  | 1.1.3 | 1302 | 140
86 | NBI | WBS 24 | Armor Plate Backing Plate | L. Bryant | Priniski | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00 |  |  |  |  | 1.2.4 | 2460 | 0026
87 | NBI | WBS 24 | Disruption Loading | L. Bryant | Priniski | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00 |  |  |  |  | 1.2.4 | 2460 | 0026
92 | Diagnostics | WBS 41 | Diagnostics Review and Database | J. Boales | Titus | 100 | 09/01/10 |  | NSTXU-CALC-40-01-00 |  | Bob Kiata to assign? |  |  | 1.2.3 | 2300 | 0015
[6 empty] | 5614 | 77.9722 |  | 72
93 | Diagnostics | WBS 41 | Thomson Scattering Port | Labik | Kaita | 0 |  |  | NSTXU-CALC-40-02-00 |  |  |  |  | 1.4.0 | 4500 |  | Covered under Vessel Port Re-Work for NB and Thompson Scattering Port #23
88 | NBI | WBS 24 | Thermal Stress Analysis(Not Req per Craig P.) | L. Bryant | Priniski | N/R | 2011-02-21 |  | NSTXU-CALC-24-02-00 |  | I. Zatz |  |  | 1.2.4 | 2460 | 0026 | Not Req per Craig P.
14 | Plasma Facing Components | WBS 11 | Inner CS Casing Tile Stress | J. Boales | Tresemer | 100 |  |  | Will be part of the above calc | 2010-10-01 | A. Brooks |  |  | 1.1.1 | 1001
47 | Toroidal Field Coils | WBS 132 | Torque Egns for Design Point | Wooley | Titus | 95 | 2011-01-17 | 2011-01-31 | Will be part of the above calc |  |  |  |  | 1.1.0 | 1000 | 0011
1 | Torus Systems | WBS 10
7 | Torus Systems | WBS 10 | VV Leg | P.Titus | Smith |  | 2010-11-30 | [6 empty] | 1.1.2 | 1207 | 0032 | Per M Smith email
8 | Torus Systems | WBS 10 | VV Interface Welds | P.Titus | Smith | 50 | 2010-11-30 | [6 empty] | 1.1.2 | 1207 | 0032
9 | Plasma Facing Components | WBS 11
17 | Vacuum Vessel | WBS 12
32 | Magnet Systems | WBS 13
39 | Polodal Field Coils | WBS 131
43 | Toroidal Field Coils | WBS 132
67 | Center Stack | WBS 133
78 | CentStack | WBS 133 | Centerstack Fixtures |  | Chrzanowski |  | 2011-08-15 | [6 empty] | 1.1.4 | 1302 | 140
80 | Center Stack | WBS 133 | CS Casing Halo Ind and Res Cur | A.Brooks | Chrzanowski | 100 | 2010-12-01 | 2010-12-15 | [5 empty] | 1.1.3 | 1307 | 1050
81 | Center Stack | WBS 133 | CS Casing Static and Dynamic | A.Brooks | Chrzanowski | 100 | 2010-12-01 | 2010-12-15 | [5 empty] | 1.1.3 | 1307 | 1050
82 | NBI | WBS 24
91 | Diagnostics | WBS 41
94 | General Power Systems | WBS 55
33 | Magnet Systems | WBS 13 | Global Model | P. Titus | Titus |  | N/A |  | NSTX-CALC-13-01-01
34 | Magnet Systems | WBS 13 | Maximum and Minimum Loads on the NSTX OH and PF Coils, and Coil Groupings | P.Titus | Titus | 100 | N/A |  | NSTX-CALC-13-02-00
44 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Diffusion Analysis(to be superceded by #48) | P.Titus | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-01-00 |  |  |  |  | 1.1.3 | 1304
45 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Analysis (to be superceded by #48) | P.Titus | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-02-00 |  |  |  |  | 1.1.3 | 1304