## Sheet1
Calc # |  | Before Feb 2011 | 2011-02-04 | 2011-02-11 | 2011-02-18 | 2011-02-25 | 2011-03-04 | 2011-03-11 | 2011-03-18 | 2011-03-25 | 2011-04-01 | 2011-04-08 | 2011-04-15 | 2011-04-22 | 2011-04-29 | 2011-05-06 | 2011-05-13 | 2011-05-20 | 2011-05-27 | 2011-06-03 | 2011-06-10 |  | Comment
10-01-02 | Global Model | [20 empty] | Draft of calc due week of 3/25/2011 (Delayed from 2/25) | 2011-05-11 | bar: 2011-03-11
10-02-00 | Seismic Analysis | [20 empty] | Draft of calc due week of 3/25/2011 (Delayed from 11/302010) | F.DAHLGREN
11-01-00 | Heat Balance | ?? | [19 empty] | Sent out for final review 2/21/2011 | When??
11-02-00 | General Tile Program | ?? | [19 empty] | Parts of calc received 2/21/2011, but missing ENG-033 form - with Art to resolve with Joe (Will be superceded by 11-03 & 04) | When??
11-03-00 | Final Tile Stresse (ATJ Tiles) | [20 empty] | Draft of calc due week of 3/25/2011 (Delayed from 2/25) | 2011-05-04 | bar: 2011-02-25
11-04-00 | Fastener Analysis | [20 empty] | Draft of calc due week of 3/30/2011 (Delayed from 2/25) | 2011-05-04 | bar: 2011-02-25
12-01-00 | Disruption Analysis of VV & Passive Plates | [20 empty] | Draft of calc due week of 3/25/2011 (Delayed from 3/4) | Overdue (May 11) | bar: 2011-03-04
12-02-00 | Dome/PF Rib Stresses | [20 empty] | Draft of calc due week of 3/25/2011 (Delayed from 3/4) | 5/11/2011 (May be deleted, covered elsewhere) | bar: 2011-02-25
12-03-00 | Opera 2D Analysis | [20 empty] | Revised memo being prepared by Ron Hatcher per Pete Titus request -- expect this week. Then will be ready for final review. | Possibly this week | bar: 2011-02-18
12-04-00 | PF2 & PF3 Bolting , Bracket & weld Stresses | [20 empty] | Draft of calc due week of 3/25/2011 (Delayed from 2/25) - combined PF2 & PF3 analyses | 5/12/2011 (with Pete) | bar: 2011-02-25
12-05-00 | PF 4 & PF5 Support Analysis | [20 empty] | Sent out for final review 4/11/2011 | with Irv 5/13 | bar: 2011-03-25
12-06-00 | Al Block Analyses | X | [19 empty] | Sent out for final review 2/10/2011 | with Mark
12-07-00 | Umbrella Reinf. Details | [20 empty] | Draft of calc due week of 3/25/2011 | 2011-05-11 | bar: 2011-03-04
12-08-00 | Lid/Spoke Assy, U & L | [20 empty] | Draft of calc due week of 3/25/2011 | 2011-05-04 | bar: 2011-03-04
12-09-00 | Pedistal Analysis | [20 empty] | Draft of calc due week of 3/25/2011 | 2011-05-06 | bar: 2011-03-11
13-01-00 | SUPERSEDED BY 10-01-00
13-02-00 | SUPERSEDED BY 10-01-00
13-03-00 | DCPS Force Influence Coefficients | X | [19 empty] | Sent out for final review 2/11/2011 | Ron to run new numbers 5/6
13-04-00 | WILL BE SUPERSEDED BY 132-07-00
13-05-00 | DCPS Moment Influence Coefficients | X | [19 empty] | Sent out for final review 2/10/2011 | 2011-05-06
131-01-00 | Analysis of CSU Poloidal Coils | [20 empty] | Memo issued on 6/26/2009 - was this ever updated? If not, then will provide ENG-033 form and cover page. | When??
131-02-00 | Calculated Poloidal Magnets Quanties (February 2010 Design) | [20 empty] | Sent out for final review 2/10/2011 | Pete
131-03-00 | Calculated Poloidal Magnets Quanties (May 2010 Design) | [20 empty] | Sent out for final review 2/16/2011 - BUT IS THIS MERELY AN UPDATE TO 132-02??? | When??
132-01-00 | SUPERSEDED BY 132-03-00
132-02-00 | SUPERSEDED BY 132-03-00
132-03-01 | OOP PF/TF Torques on TF | X | [19 empty] | Updated memo sent by Bob Woolley - 2/11/2011. Will be update of this calc. | When??
132-04-00 | Analysis of TF Outer Leg | [20 empty] | Sent out for Review 3/29/2011 | When??(Leg brace deletion needs to be justified)Han | bar: 2011-03-11
132-05-00 | Coupled EM-Thermal Analysis | [20 empty] | Sent out for Review 3/29/2011 | 5/6/2011 (comments need to be incorporated) | bar: 2011-02-25
132-06-01 | TF Flex Joint & Bundle Stub | X | [19 empty] | APPROVED
132-07-00 | Max Torsional Shear Stress | X | [19 empty] | In signature cycle on 2/11/2011 | Woolley
132-08-00 | Determination of Shear Forces between TF Conductors & Insulation & G-10 Insulating Crown | [20 empty] | APPROVED
132-09-00 | Analysis of Knuckle Clevis | [20 empty] | Draft of calc due week of 3/11/2011 | 2011-05-12 | bar: 2011-03-11
132-10-00 | TF Cooldown Using FCOOL | X | [19 empty] | APPROVED
132-11-00 | Ring Bolted Joint | [20 empty] | Out for Final Signature 4/10/2011 | Approved?? Simmons to check | bar: 2011-03-11
133-01-01 | Structural Analysis of PF1 Coils, Leads, & Supports | [20 empty] | Draft of calc due week of 4/4/2011 (Delayed from 3/4) | 2011-05-16 | bar: 2011-03-04
133-02-00 | Thermal Stresses on OH-TF Coils | ?? | [19 empty] | Sent out for Review 3/29/2011 | (REVW CMPLTD 4/22/2011)
133-03-00 | Center Stack Casing Disruption Inductive & Halo Current Loads | [20 empty] | Sent out for final review 2/10/2011 | Pete | bar: 2011-04-15
133-04-00 | OH Preload System & Belleville Spring Design | ?? | [19 empty] | Sent out for final review 2/11/2011- | (REVW CMPLTD)
133-05-00 | Halo Current Analysis of Center Stack Casing | ?? | [19 empty] | Sent out for final review 2/21/2011 | Pete
133-06-00 | OH Coolant Hole Optimization | ?? | [19 empty] | Sent out for final review 2/11/2011 | 2011-05-09
133-07-00 | OH Coax Lead Analysis | [20 empty] | Draft of calc due week of 3/18/2011 | 2011-05-09 | bar: 2011-03-18
133-08-00 | OH Stress Analysis | ?? | [19 empty] | Sent out for final review 2/11/2011 | F.DAHLGREN
133-09-00 | OH Fatigue & Fracture Mechanics | [20 empty] | APPROVED
133-10-00 | Center Stack Casing Bellows | X | [19 empty] | Sent out for signature 2/17/2011 | 2011-05-20
133-11-00 | OH & PF1 Electromagnet Stability Analysis | [20 empty] | Sent out for Review 3/29/2011 | H.M.FAN
133-12-00 | Center Stack Manufacturing Fixture | [20 empty] | Delayed until August 2011
24-01-00 | Vessel Port Re-Work & Thomson Scattering | [20 empty] | APPROVED
24-02-00 | Armor Plate Backing Plate | [20 empty] | APPROVED | bar: 2011-02-25
24-03-00 | HHFW | X | [19 empty] | In final signature process week of May 2nd.
24-04-00 | Magnetic Shielding | [20 empty] | APPROVED
40-01-00 | Diagnostic Review & Database | X | [19 empty] | Missing copy of CALC - please provide | 2011-05-12
55-01-00 | Bus Bar Analysis | [20 empty] | Out for final review 5/4/2011