## Sheet1
Calc # |  | Before Feb 2011 | 2011-02-04 | 2011-02-11 | 2011-02-18 | 2011-02-25 | 2011-03-04 | 2011-03-11 | 2011-03-18 | 2011-03-25 | 2011-04-01 | 2011-04-08 | 2011-04-15 | 2011-04-22 | 2011-04-29 | 2011-05-06 | 2011-05-13 | 2011-05-20 | 2011-05-27 | 2011-06-03 | 2011-06-10 |  | Comment
10-01-02 | Global Model | [20 empty] | Draft of calc due week of 5/11/2011 (Delayed from 3/25) | bar: 2011-03-11
10-02-00 | Seismic Analysis | [20 empty] | In review cycle - awaiting comments from F. Dahlgren | When??
10-03-00 | Design Point sreadsheet | [20 empty] | In review cycle - Need schedule to complete review
11-01-00 | Heat Balance | ?? | [19 empty] | In final review -- A. Brooks incorportating comments
11-02-00 | General Tile Program - SUPERSEDED BY CALCS 11-03 & 11-04 | ??
11-03-00 | Final Tile Stresse (ATJ Tiles) | [20 empty] | Draft of calc due week of 5/4/2011 (Delayed from 3/25) | bar: 2011-02-25
11-04-00 | Fastener Analysis | [20 empty] | Draft of calc due week of 5/4/2011 (Delayed from 3/25) | bar: 2011-02-25
12-01-00 | Disruption Analysis of VV & Passive Plates | [20 empty] | Draft of calc due week of 3/25/2011 (Delayed from 3/4) | Overdue -- When?? | bar: 2011-03-04
12-02-00 | Dome/PF Rib Stresses | [20 empty] | Draft of calc due week of 3/25/2011 (Delayed from 3/4) | DELETE?? | bar: 2011-02-25
12-03-00 | Opera 2D Analysis | [20 empty] | Revised memo being prepared by Ron Hatcher per Pete Titus request -- expect this week. Then will be ready for final review. | Possibly this week | bar: 2011-02-18
12-04-00 | PF2 & PF3 Bolting , Bracket & weld Stresses | [20 empty] | P. Titus incorporating comments from I. Zatz - expect out week of 5/12 | bar: 2011-02-25
12-05-00 | PF 4 & PF5 Support Analysis | [20 empty] | Sent out for final review 4/11/2011 - w/ I. Zatz for review | When?? | bar: 2011-03-25
12-06-00 | Al Block Analyses | X | [19 empty] | Sent out for final review 2/10/2011 - waiting on Pete and Bob Woolley to resolve comments. | When??
12-07-00 | Umbrella Reinf. Details | [20 empty] | Draft of calc due week of 5/11/2011 (Delayed from 3/25) | bar: 2011-03-04
12-08-00 | Lid/Spoke Assy, U & L | [20 empty] | Draft of calc due week of 5/4/2011 (Delayed from 3/25) | bar: 2011-03-04
12-09-00 | Pedistal Analysis | [20 empty] | Draft of calc due week of 5/4/2011 (Delayed from 3/25) | bar: 2011-03-11
13-01-00 | SUPERSEDED BY 10-01-00
13-02-00 | SUPERSEDED BY 10-01-00
13-03-00 | DCPS Force Influence Coefficients | X | [19 empty] | R. Hatcher updating per comments - expect by 5/6 | Completed via Memo from Hatcher
13-04-00 | WILL BE SUPERSEDED BY 132-07-00
13-05-00 | DCPS Moment Influence Coefficients | X | [19 empty] | Sent out for final review 5/5/2011 - updated reviewers
131-01-00 | Analysis of CSU Poloidal Coils - WILL BE SUPERSEDED BY CALC-131-03
131-02-00 | Calculated Poloidal Magnets Quanties (February 2010 Design) - WILL BE SUPERSEDED BY CALC-131-03
131-03-00 | Calculated Poloidal Magnets Quanties (May 2010 Design) | [20 empty] | Sent out for final review 2/16/2011 | Titus, Woolley overdue - When???
132-01-00 | SUPERSEDED BY 132-05-01
132-02-00 | SUPERSEDED BY 132-05-01
132-03-01 | OOP PF/TF Torques on TF | X | [19 empty] | Updated memo sent by Bob Woolley - 2/11/2011. Bob will be update of this calc. | When??
132-04-00 | Analysis of TF Outer Leg | [20 empty] | Han is updating calc to reflect comments & latest design point info. | bar: 2011-03-11
132-05-01 | Coupled EM-Thermal Analysis | [20 empty] | Out for Final Signature 5/5/2011 - awaiting return of Jim Chrzanowski on 5/16 to complete signatures. | bar: 2011-02-25
132-06-01 | TF Flex Joint & Bundle Stub | X | [19 empty] | APPROVED
132-07-00 | Max Torsional Shear Stress | X | [19 empty] | In signature cycle on 2/11/2011 -- Pete believes that Bob Woolley is very close to completing his review. Waiting on Bob Woolley. | When??
132-08-00 | Determination of Shear Forces between TF Conductors & Insulation & G-10 Insulating Crown | [20 empty] | APPROVED
132-09-00 | Analysis of Knuckle Clevis | [20 empty] | Draft of calc due week of 5/12/2011 (Delayed from 3/11) | bar: 2011-03-11
132-10-00 | TF Cooldown Using FCOOL | X | [19 empty] | APPROVED
132-11-00 | Ring Bolted Joint | [20 empty] | Out for Final Signature 4/10/2011 | bar: 2011-03-11
133-01-01 | Structural Analysis of PF1 Coils, Leads, & Supports | [20 empty] | Draft of calc due week of 5/16/2011 (Delayed from 4/4) | bar: 2011-03-04
133-02-00 | Thermal Stresses on OH-TF Coils | ?? | [19 empty] | Review supposedly completed on 4/22 -- When will the calc be ready to sign? | When??
133-03-00 | Center Stack Casing Disruption Inductive & Halo Current Loads | [20 empty] | Sent out for final review 2/10/2011 - waiting on Pete to complete - No reviewer assigned? | When?? | bar: 2011-04-15
133-04-00 | OH Preload System & Belleville Spring Design | ?? | [19 empty] | Review supposedly completed -- When will the calc be ready to sign? | When??
133-05-00 | Halo Current Analysis of Center Stack Casing | ?? | [19 empty] | Sent out for final review 2/21/2011 - waiting on Pete to complete his review. | When??
133-06-00 | OH Coolant Hole Optimization | ?? | [19 empty] | Sent out for final review 2/11/2011 - expect to resolve comments week of 5/9
133-07-00 | OH Coax Lead Analysis | [20 empty] | Draft of calc due week of 5/12/2011 (Delayed from 3/18) | bar: 2011-03-18
133-08-00 | OH Stress Analysis | ?? | [19 empty] | Sent out for final review 2/11/2011 -- Waiting on Fred Dahlgren to provide comments. | When??
133-09-00 | OH Fatigue & Fracture Mechanics | [20 empty] | APPROVED
133-10-00 | Center Stack Casing Bellows | X | [19 empty] | In final review - waiting on Irv Zatz to complete his review.
133-11-00 | OH & PF1 Electromagnet Stability Analysis | [20 empty] | Sent out for Review 3/29/2011 - awaiting comments from HM Fan | When??
133-12-00 | Center Stack Manufacturing Fixture | [20 empty] | Delayed until August 2011
24-01-00 | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | Vessel Port Re-Work & Thomson Scattering | APPROVED
24-02-00 | Armor Plate Backing Plate | [20 empty] | APPROVED | bar: 2011-02-25
24-03-00 | HHFW | X | [19 empty] | APPROVED
24-04-00 | Magnetic Shielding | [20 empty] | APPROVED
40-01-00 | Diagnostic Review & Database | X | [19 empty] | Missing copy of CALC - please provide
55-01-00 | Bus Bar Analysis | [20 empty] | Out for final review 5/4/2011