## Sheet1
1 |  | NSTX Calculation Log
2 | [5 empty] | Preparation | [6 empty] | Reviewed |  |  | Cog Review & Signoff
3 |  | Line # | WBS Name | WBS | Calc Title | Preparer | COG | Preparation Complete | Schedule Date (COG) | Forecast Date (Preparer) | Calc # | Preparer Sign date | Reviewer | Reviewed | Reviewer Sign date | COG | Cog Signature | WP Form | WBS | Job # (WAF) | Act ID | Comments
[8 empty] | 48 |  |  | 51 |  |  | 35 |  |  | 19
7 | 1 | 1 | Torus Systems | WBS 10 | Global Model | P.Titus | Titus | YES | 2011-01-17 | 2011-06-17 | NSTXU-CALC-10-01-02 | 2011-06-22 | Han Zhang | yes | 2011-07-15 | Titus |  | 1511 | 1.1.1 | 1000 | 0011 | Replaces Calc-13-01-01
10 | 1 | 2 | Torus Systems | WBS 10 | Seismic Analysis | P.Titus | Titus | YES | 2011-01-17 | 2011-04-21 | NSTXU-CALC-10-02-00 | 2011-02-10 | F. Dahlgren | yes | 2011-06-17 | Titus | Yes | 1511 | 1.1.1 | 1000 | 0011
11 | 1 | 3 |  |  | Design point Spreadsheet | C.Neumeyer | Various | YES |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Physics-Menard | Y |  | Various
12 | 1 | 4 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Physics-Hatcher | Y |  | Various
[13 empty] | Inductance matrix-Woolley | 2011-08-17
13 | 1 | 5 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Raidal Build-Chrzanowski | Y |  | Various
14 | 1 | 6 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Raidal Build-Tresemer | Y |  | Various
15 | 1 | 7 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | CSC Dims-Tresemer | Y |  | Various
16 | 1 | 8 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | TF Coil -Chrzanowski | Y |  | Various
17 | 1 | 9 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | TF Coil -Zolfaghari | Y |  | Various
18 | 1 | 10 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | TF Coil -Raki | Y |  | Various
19 | 1 | 11 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | TF Coil -Hatcher | Y |  | Various
20 | 1 | 12 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | TF Coil -Zhang | Y |  | Various
21 | 1 | 13 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | OH Coil -Chrzanowski | Y |  | Various
22 | 1 | 14 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | OH Coil -Zolfaghari | Y |  | Various
23 | 1 | 15 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | OH Coil -Raki | Y |  | Various
24 | 1 | 16 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | OH Coil -Hatcher | Y |  | Various
25 | 1 | 17 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Inner PF Coils -Chrzanowski | Y |  | Various
26 | 1 | 18 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Inner PF Coils -Raki | Y |  | Various
27 | 1 | 19 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Inner PF Coils -Hatcher | Y |  | Various
28 | 1 | 20 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | PF Coil Smry-Chrzanowski | Y |  | Various
29 | 1 | 21 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | PF Coil Smry-Hatcher | Y |  | Various
30 | 1 | 22 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Coil Insul Smry-Chrzanowski | Y |  | Various
31 | 1 | 23 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Circuit Smry-Raki | Y |  | Various
32 | 1 | 24 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | OH PF Forces-Hatcher | Y |  | Various
33 | 1 | 25 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Combo Force Moment-Hatcher | Y |  | Various
34 | 1 | 26 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Power Sys-Raki | Y |  | Various
35 | 1 | 27 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Power Sys-Hatcher | Y |  | Various
36 | 1 | 28 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | Heat Loads-Menard | Y |  | Various
37 | 1 | 29 |  |  | Design point Spreadsheet | C.Neumeyer | Various |  |  |  | NSTXU-CALC-10-03-00 | 2011-05-25 | I TF-Hatcher | Y |  | Various
38 | 1 | 30 | Plasma Facing Components | WBS 11 | Heat Balance | A.Brooks | Chrzanowski | YES |  |  | NSTXU-CALC-11-01-00 | 2011-02-21 | H.Zhang | Yes | 2011-06-17 | Chrzanowski | Yes | 1672 | 1.1.1 | 1307 | 0011 | With Art to incorp revwr commts
40 | 1 | 31 | Plasma Facing Components | WBS 11 | Final Tile Stress Analysis (ATJ Tiles) | A.Brooks | Tresemer | YES | 2010-11-19 | 2011-05-16 | NSTXU-CALC-11-03-00 |  | L.Myatt | ? |  | Tresemer |  | 1707 | 1.1.1 | 1001 | 0040
|  | 31A | Plasma Facing Components | WBS 11 | Armor | K.Tresemer | Tresemer | YES | 2010-11-19 | 2011-05-16 | NSTXU-CALC-11-05-00 |  | T.Stevenson | 2011-09-19 | ? | Tresemer
42 | 1 | 32 | Vacuum Vessel | WBS 12 | Update of Analysis of Vacuum Vessel & Passive Plates | P.Titus | Titus | YES | 2011-01-05 | 2011-04-15 | NSTXU-CALC-12-01-01 |  | Y.Zhai | Yes | 2011-06-17 | Titus |  | 1511 | 1.1.1 | 1002 | 0019
44 | 1 | 33 | Vacuum Vessel | WBS 12 | OPERA 2D Disruption Analyses | Hatcher | Titus | YES | 2011-01-17 | 2011-03-04 | NSTXU-CALC-12-03-00 | 2011-05-13 | A.Brooks | Yes | 2011-06-12 | Titus | Yes | 1511 | 1.1.1 | 1002 | 0014
45 | 1 | 34 | Vacuum Vessel | WBS 12 | PF2 / PF3 Bolting, Bracket, and weld Stress | P. Titus | Smith | YES | 2011-02-01 | 2011-03-25 | NSTXU-CALC-12-04-00 |  | I.Zatz | Yes | 2011-06-24 | Smith | 2011-08-31 | 1677 | 1.1.2 | 1203 | 0032 | With Pete to incorp revwr commts
46 | 1 | 35 | Vacuum Vessel | WBS 12 | PF4 and PF5 Support Analysis | P. Titus | Smith | YES | 2011-03-22 | 2011-04-05 | NSTXU-CALC-12-05-00 | 2011-04-05 | I.Zatz | Yes | 2011-06-24 | Smith |  | 1677 | 1.1.2 | 1208 | 0029-0032 | With Pete to incorp revwr commts
47 | 1 | 36 | Vacuum Vessel | WBS 12 | Alunimum Block (To Be Revise by Pete T.) | P.Titus | Smith | 2011-08-01 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 | 2011-02-10 | M.Smith (waiting for Pete to respond to comments) |  |  | Smith |  | 1677 | 1.1.2 | 1205 | 0029 0037 | Per M Smith email
48 | 1 | 37 | Vacuum Vessel | WBS 12 | Umbrella Reinforcement Details | P. Titus | Smith | YES | 2011-02-22 | 2011-05-16 | NSTXU-CALC-12-07-00 |  | I.Zatz | Yes | 2011-06-24 | Smith |  | 1677 | 1.1.2 | 1205 | 0029 0090
49 | 1 | 38 | Vacuum Vessel | WBS 12 | Lid/Spoke Assembly, Upper and Lower | P.Titus/Smith | Smith | YES | 2011-02-22 | 2011-05-27 | NSTXU-CALC-12-08-00 | 2011-05-27 | I.Zatz | Yes | 2011-07-05 | Smith |  | 1677 | 1.1.2 | 1205 | 31 & 89
50 | 1 | 39 | Vacuum Vessel | WBS 12 | Pedestal Analysis | P.Titus/Smith | Smith | YES | 2011-03-08 | 2011-05-06 | NSTXU-CALC-12-09-00 | 2011-05-19 | A.Zolfaghari | Yes | 2011-06-23 | Smith | 2011-08-26 | 1677 | 1.1.2 | 1206 | 0029 0032
51 | 1 | 40 | Magnet Systems | WBS 13 | DCPS Force Influence Coefficients | Hatcher | R.Hatcher | YES | 2010-11-24 |  | NSTXU-CALC-13-03-01 | 2011-02-11 | P.Titus | Yes | 2011-06-17 | R.Hatcher |  | 1511 | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
52 | 1 | 41 | Magnet Systems | WBS 13 | DCPS Moment Influence Coefficients | Wooley/Titus | R.Hatcher | YES | 2010-12-15 | 2011-01-30 | NSTXU-CALC-13-05-00 | 2011-02-10 | Woolley | Yes | 2011-06-12 | R.Hatcher |  | 1511 | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
53 | 1 | 42 | Polodal Field Coils | WBS 131 | Analysis of CSU Poloidal Field Coils | Woolley | Chrzanowski | YES |  |  | NSTXU-CALC-131-01-00 replaced by 131-03-00 |  | Neumeyer | Not required: Superceded by 131-03 |  | Chrzanowski |  | 1672 | 1.1.3 | 1306 | 1020 | Superseded by Calc 131-03
59 | 1 | 43 | Polodal Field Coils | WBS 131 | Poloidal Magnetic Quantites for the May 2010 Design Point | Woolley | Chrzanowski | YES |  | 2011-01-30 | NSTXU-CALC-131-03-00 | 2011-02-10 | R. Hatcher | Yes |  | Chrzanowski |  | 1672
62 | 1 | 44 | Toroidal Field Coils | WBS 132 | Torque Egns for Design Point | Wooley | Titus | YES | 2011-01-17 | 2011-01-31 | NSTXU-CALC-132-03-00 |  | P.Titus | 2011-07-20 |  | Titus |  | 1511 | 1.1.0 | 1000 | 0011
63 | 1 | 45 | Plasma Facing Components | WBS 11 | General Tile Program | J. Boales | Tresemer | YES |  |  | NSTXU-CALC-11-02-00 |  | Superseded by Calc 11-03 |  |  | Tresemer |  | 1707 | 1.1.1 | 1001
65 | 1 | 46 | Toroidal Field Coils | WBS 132 | Analysis of TF Outer Leg | Han Zhang | Smith | YES | 2010-10-27 | 2011-03-11 | NSTXU-CALC-132-04-00 | 2011-03-29 | Y.Zhai | Yes | 2011-05-06 | Smith |  | 1677 | 1.1.2 | 1201 | 0031, 0032 | Han/Pete to incorp revwr commts
66 | 1 | 47 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Analysis | Han Zhang | Chrzanowski | YES | 2010-12-01 | 2011-03-25 | NSTXU-CALC-132-05-00 | 2011-03-29 | Y.Zhai | Yes | 2011-05-05 | Chrzanowski | Yes | 1672 | 1.1.3 | 1304 | 0220 | With Han to incorp revwr commts
71 | 1 | 48 | Toroidal Field Coils | WBS 132 | TF Flex Joint and Bundle Stub | T.Willard | Chrzanowski | YES |  |  | NSTXU-CALC-132-06-00 | 2011-02-03 | A.Zolfaghari | Yes | 2011-02-03 | Chrzanowski | Yes | 1672 | 1.1.3 | 1304 | 0230
72 | 1 | 49 | Toroidal Field Coils | WBS 132 | Maximum Torsional Shear Stress | P. Titus | Chrzanowski | YES | 2010-12-15 | 2011-02-01 | NSTXU-CALC-132-07-00 | 2011-02-11 | Woolley | Yes | 2011-04-08 | Chrzanowski |  | 1672 | 1.1.3 | 1304 | 0230
74 | 1 | 50 | Toroidal Field Coils | WBS 132 | Determination of shear Forces Between the TF conductors and Insulation and the G-10 Insulating Crown. | A. Zolfaghari | Chrzanowski | YES |  |  | NSTXU-CALC-132-08-00 | 2011-02-10 | T.Willard | Yes | 2011-02-10 | Chrzanowski | Yes | 1672 | 1.1.3 | 1304 | 0230
75 | 1 | 51 | Toroidal Field Coils | WBS 132 | Analysis of Knuckle Clevis | P. Titus | Smith | YES | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-09-00 | 2011-03-23 | Han Zhang | Yes | 2011-06-20 | Smith |  | 1677 | 1.1.2 | 1201 | 0031, 0032 | With Pete to incorp revwr commts
76 | 1 | 52 | Toroidal Field Coils | WBS 132 | TF Cooldown using FCOOL | A. Zolfaghari | Chrzanowski | YES | 2010-12-01 |  | NSTXU-CALC-132-10-00 | 2011-02-10 | M.Kalish | Yes | 2011-02-10 | Chrzanowski | Yes | 1672 | 1.1.3 | 1304 | 0230
77 | 1 | 53 | Toroidal Field Coils | WBS 132 | Ring Bolted Joint | Peter Rogoff | Smith | YES | 2011-03-08 | 2011-03-25 | NSTXU-CALC-132-11-00 | 2011-03-29 | I.Zatz | Yes | 2011-04-11 | Smith | Yes | 1677 | 1.1.2 | 1201 | 0031, 0032
82 | 1 | 54 | Center Stack | WBS 133 | Structural Analysis of the PF1 Coils, leads and Supports, Rev 1 | L.Myatt | Chrzanowski | 2011-08-15 |  | 2011-03-26 | NSTXU-CALC-133-01-01 |  | A.Brooks (waiting for Myatt to respond to comments) | 2011-08-15 |  | Chrzanowski |  | 1672
90 | 1 | 55 | Center Stack | WBS 133 | Thermal Stresses on OH-TF Coils | S.Avasarala | Chrzanowski | YES |  | 2011-03-27 | NSTXU-CALC-133-02-00 | 2011-03-29 | Han Zhang | Yes | 2011-04-22 | Chrzanowski | Cancel | 1672 | 1.1.3 | 1307 | 1050 | With Pete to incorp revwr commts
94 | 1 | 56 | Center Stack | WBS 133 | Center Stack Casing Disruption Inductive and Halo Current Loads | P.Titus | Chrzanowski | YES | 2010-08-12 | 2011-03-28 | NSTXU-CALC-133-03-00 | 2011-02-10 | various |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1307 | 1030
95 | 1 | 57 | Center Stack | WBS 133 | OH Preload System and Belleville Spring Design | Peter Rogoff | Chrzanowski | YES |  | 2011-03-29 | NSTXU-CALC-133-04-00 | 2011-02-11 | T.Kozub/Test | Yes | 2011-05-09 | Chrzanowski | Yes | 1672 | 1.1.3 | 1304
97 | 1 | 58 | Center Stack | WBS 133 | CS Casing Halo Ind and Res Cur | A.Brooks | Chrzanowski | YES | 2010-12-01 | 2011-03-30 | NSTXU-CALC-133-05-00 | 2011-02-21 | P.Titus | Comments sent to Brooks |  | Chrzanowski |  | 1672 | 1.1.3 | 1307 | 1050
98 | 1 | 59 | Center Stack | WBS 133 | OH Cooling | A. Zolfaghari | Chrzanowski | YES |  | 2011-03-31 | NSTXU-CALC-133-06-00 | 2011-02-11 | M. Mardenfeld | 2011-09-14 | 2011-06-12 | Chrzanowski |  | 1672 | 1.1.3 | 1305 | 100
99 | 1 | 60 | Center Stack | WBS 133 | OH Coax Lead Analysis | M. Mardenfeld | Chrzanowski | YES | 2010-09-10 | 2011-04-01 | NSTXU-CALC-133-07-00 |  | A.Zolfaghari | ? |  | Chrzanowski |  | 1677 | 1.1.3 | 1305 | 120
100 | 1 | 61 | Center Stack | WBS 133 | OH Stress Analyses | A. Zolfaghari | Chrzanowski | YES | 2010-07-29 | 2011-04-02 | NSTXU-CALC-133-08-00 | 2011-02-11 | M. Mardenfeld | 2011-09-16 |  | Chrzanowski |  | 1672 | 1.1.3 | 1305 | 100
101 | 1 | 62 | Center Stack | WBS 133 | OH Fatigue and Fracture Mechanics | P. Titus | Chrzanowski | YES | 2010-09-10 | 2011-01-15 | NSTXU-CALC-133-09-00 | 2011-02-04 | I. Zatz | Yes | 2011-02-28 | Chrzanowski | Yes | 1672 | 1.1.3 | 1304 | 140
102 | 1 | 63 | Center Stack | WBS 133 | Center Stack Casing Bellows | Peter Rogoff | Chrzanowski | YES |  | 2011-01-31 | NSTXU-CALC-133-10-00 | 2011-02-17 | I.Zatz | Yes | 2011-06-09 | Chrzanowski | Yes | 1672 | 1.1.3 | 1307 | 1050
103 | 1 | 64 | Center Stack | WBS 133 | OH & PF1 Electromagnectic Stability Analysis | P. Titus/Zolfaghari | Chrzanowski | YES |  | 2011-03-25 | NSTXU-CALC-133-11-00 | 2011-03-29 | A.Zolfaghari | ? |  | Chrzanowski |  | 1672 | 1.1.3 | 1307 | 1050
105 | 1 | 65 | CentStack | WBS 133 | Centerstack Manufacturing Fixtures | Raftopolous | Chrzanowski | 2011-12-11 | 2011-08-15 | 2011-03-26 | NSTXU-CALC-133-12-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.4 | 1304 | 140
|  | 65A |  |  | Modal Analysis / Normal Ops Transient Load | Titus |  | YES |  |  | NSTXU-CALC-133-13-00 |  | Dahlgren | ? |  | Titus
107 | 1 | 66 | NBI | WBS 24 | Vessel Port Re-Work for NB and Thompson Scattering Port | T. Willard | Priniski / Labik | YES | 2011-01-05 | 2011-01-24 | NSTXU-CALC-24-01-00 |  | A.Zolfaghari | Yes | 2011-02-03 | Priniski / Labik | Yes | 1627/1506 | 1.2.4 | 2480 | 0035
108 | 1 | 67 | NBI | WBS 24 | Armor Plate Backing Plate | L. Bryant | Priniski | YES | 2011-02-21 |  | NSTXU-CALC-24-02-00 | 2011-02-28 | I. Zatz | Yes | 2011-02-03 | Priniski | Yes | 1508 | 1.2.4 | 2460 | 0026
109 | 1 | 68 | NBI | WBS 24 | HHFW Antenna (needs to be modified for upgrade loads) | Han Zhang/Ellis | Bob Ellis | YES | 2011-01-15 |  | NSTXU-CALC-24-03-00 |  | R.Hatcher | Yes | 2011-05-03 | Bob Ellis | Yes | 1511 | 1.2.4
112 | 1 | 69 | NBI | WBS 24 | Magnetic Shielding Calculation | Y.Zhai | Blanchard | YES | 2010-11-24 | 2011-04-08 | NSTXU-CALC-24-04-00 | 2011-04-21 | A.Zolfaghari | Yes | 2011-04-22 | Blanchard | Yes |  | 1.2.4 | 2485 | 0016A
115 | 1 | 70 | Diagnostics | WBS 41 | Diagnostics Review and Database | J. Boales | Titus | YES | 09/01/10 | 2011-04-11 | NSTXU-CALC-40-01-00 |  | Y.Zhai | Yes | 2011-07-08 | Titus |  | 1511 | 1.2.3 | 2300 | 0015
116 | 1 | 71 | General Power Systems | WBS 55 | Modification of the TF Coil Power System PSCAD Model | Nayak Corp | S. Ramakrisnan | YES | N/A | N/A | NSTXU-CALC-53-01-00 | N/A | W. Quo | Yes | 2011-06-15 | S. Ramakrisnan | Yes
117 | 1 | 72 | General Power Systems | WBS 55 | Modification of the OH Coil Power System PSCAD Model | Nayak Corp | S. Ramakrisnan | YES | N/A | N/A | NSTXU-CALC-53-02-00 | N/A | W. Quo | Yes | 2011-06-15 | S. Ramakrisnan | Yes
118 | 1 | 73 | General Power Systems | WBS 55 | TF Cabling from the Transition Area to NSTX-U Test Cell | C. Neumeyer | S. Ramakrisnan | YES | N/A | N/A | NSTXU-CALC-53-03-00 | N/A | S. Ramakrisnan | Yes | 2011-06-15 | S. Ramakrisnan | Yes
119 | 1 | 74 | General Power Systems | WBS 55 | TF Cabling from the Rectifiers to SDS | C. Neumeyer | S. Ramakrisnan | YES | N/A | N/A | NSTXU-CALC-53-04-00 | N/A | S. Ramakrisnan | Yes | 2011-06-15 | S. Ramakrisnan | Yes
120 | 1 | 75 | General Power Systems | WBS 55 | Bus Bar Analysis | A. Khodak | Smith/Chrzanowski | YES | 2011-02-08 | 2011-05-06 | NSTXU-CALC-55-01-00 | 2011-05-04 | H.Zhang | Yes | 2011-06-20 | Smith/Chrzanowski |  | 1672 | 1.5.5 | 5501 | 0049-0076
4 | x | 0 | Torus Systems | WBS 10 | Full Load Inventory | P.Titus | Titus | 90 | 2010-12-15 | 2011-06-17 | NSTXU-CALC-10-01-02 |  |  |  |  | Titus |  | 1511 | 1.1.1 | 1000 | 0016 | Per M Smith email
5 | x | 0 | Torus Systems | WBS 10 | Leg and Brace Hiltis | P. Titus | Smith | 90 | 2011-03-08 | 2011-06-17 | NSTXU-CALC-10-01-02 |  | M.Smith |  |  | Smith |  | 1677 | 1.1.2 | 1207 | 0032
6 | x | 0 | Torus Systems | WBS 10 | Torques to Lids and TF Teeth | P. Titus | Smith | 90 | 2011-03-08 | 2011-06-17 | NSTXU-CALC-10-01-02 |  | A.Zolfaghari |  |  | Smith |  | 1677 | 1.1.2 | 1201 | 0031
8 | x | 0 | Torus Systems | WBS 10 | VV Leg | P.Titus | Smith | 90 | 2010-11-30 | 2011-06-17 | NSTXU-CALC-10-01-02 |  |  |  |  | Smith |  | 1677 | 1.1.2 | 1207 | 0032 | Per M Smith email
9 | x | 0 | Torus Systems | WBS 10 | VV Interface Welds | P.Titus | Smith | 90 | 2010-11-30 | 2011-06-17 | NSTXU-CALC-10-01-02 |  |  |  |  | Smith |  | 1677 | 1.1.2 | 1207 | 0032
39 | x | 4 | Plasma Facing Components | WBS 11 | General Tile Program | J. Boales | Tresemer | 100 |  |  | NSTXU-CALC-11-02-00 |  | A. Brooks | Superseded |  | Tresemer |  | 1707 | 1.1.1 | 1001 | 0040 | Superseded by Calc 11-03/11-04
41 | x | 6 | Plasma Facing Components | WBS 11 | Fastener Analysis | A.Brooks | Tresemer | 100 | 2011-01-10 | 2011-05-16 | NSTXU-CALC-11-04-00 |  |  | Superseded |  | Tresemer |  | 1707 | 1.1.1 | 1001 | 0041 | Superseded by Calc 11-03
43 | x | 8 | Vacuum Vessel | WBS 12 | Dome/PF Rib Stresses | P.Titus | Smith | 100 | 2011-02-01 | 2011-05-16 | NSTXU-CALC-12-02-00 |  | M.Smith | Merge |  | Smith |  | 1677 | 1.1.2 | 1220 | 0016 | Merge with CALC-12-07-00
54 | x | 26 | Vacuum Vessel | WBS 12 | PF4 and 5 Lead Support Analysis | P. Titus | Smith | 100 | 2011-03-22 | 2011-03-30 | NSTXU-CALC-12-05-00 |  | M.Smith |  | 2011-04-11 | Smith |  | 1677 | 1.1.2 | 1204 | 0032 | Superseded by Calc 11-03
55 | x | 19 | Vacuum Vessel | WBS 12 | Disruption Analysis of Vacuum Vessel and Passive Plates | P.Titus | Titus | 100 |  |  | NSTXU-CALC-12-01-00 |  |  |  | 2011-04-11 | Titus |  | 1511 | 1.1.1 | 1002 | 0016 | Superseded by Calc 11-03
56 | x | 23 | Vacuum Vessel | WBS 12 | PF2 Bolting and Bracket Stress | P. Titus | Smith | 100 | 2011-02-01 | 2011-03-25 | NSTXU-CALC-12-04-00 |  | I.Zatz |  | 2011-04-11 | Smith |  | 1677 | 1.1.2 | 1202 | 0032 | Superseded by Calc 11-03
57 | x | 6 | Torus Systems | WBS 10 | Pedestal Loads | P. Titus | Smith | N/A | 2011-03-08 |  | NSTXU-CALC-10-01-02 |  | M.Smith |  | 2011-04-11 | Smith |  | 1677 | 1.1.2 | 1206 | 0029 0032 | Superseded by Calc 11-03
58 | x | 19 | Polodal Field Coils | WBS 131 | Poloidal Magnetic Quantites for the Feb 2010 Provisional Design | Woolley | Chrzanowski | 100 |  |  | NSTXU-CALC-131-02-00 | 2011-02-10 | P.Titus |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1306 | 1020 | Superseded by Calc 131-03
60 | x | 12 | Plasma Facing Components | WBS 11 | Sizing of Coolant Capabilities | A.Brooks | Chrzanowski | 100 | 2010-06-01 |  | NSTXU-CALC-11-01-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.3.2 | 3200 | 0023
61 | x | 13 | Plasma Facing Components | WBS 11 | Divertor Tile Thermal Stress (CFC Tiles) | A.Brooks | Tresemer | 100 |  |  | NSTXU-CALC-11-01-00 |  |  |  |  | Tresemer |  | 1707 | 1.1.1 | 1001
64 | x | 36 | Magnet Systems | WBS 13 | NSTX Influence Matrix | Hatcher | Titus | 100 |  |  | NSTXU-CALC-13-03-00 | 2011-02-11 | P.Titus |  |  | Titus |  | 1511 | 1.1.3 | 1300 | 0010
67 | x | 28 | Vacuum Vessel | WBS 12 | TFO Leg | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 |  | Y.Zhai | Yes |  | Smith | Yes | 1677 | 1.1.2 | 1205 | 0029, 0037 | Moments Loads
68 | x | 29 | Vacuum Vessel | WBS 12 | Bolt details | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 |  | Y.Zhai | Yes |  | Smith | Yes | 1677 | 1.1.2 | 1205 | 0029, 0037 | Moments Loads
69 | x | 34 | Magnet Systems | WBS 13 | Global Model | P. Titus | Titus | N/A | N/A |  | NSTXU-CALC-13-01-01 |  | Y.Zhai | Yes |  | Titus | Yes | 1511
70 | x | 35 | Magnet Systems | WBS 13 | Maximum & Minimum Loads on the NSTX OH & PF Coils, & Coil Groupings | P.Titus | Titus | N/A | N/A |  | NSTXU-CALC-13-02-00 |  | Y.Zhai | Yes |  | Titus | Yes | 1511
73 | x | 38 | Magnet Systems | WBS 13 | DCPS TF Inner Leg Torsional Shear Stress | P. Titus | R.Hatcher | N/A | 2010-10-27 | 2011-01-28 | NSTXU-CALC-13-04-00 |  |  |  |  | R.Hatcher |  | 1511 | 1.5.2 | 5200 | R.Hatcher | Incorp into Calc NSTXU-CALC-132-07-00
78 | x | 45 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Diffusion Analysis(to be superceded by #48) | P.Titus | Chrzanowski | N/A | 2010-12-01 |  | NSTXU-CALC-132-01-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304
79 | x | 46 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Analysis (to be superceded by #48) | P.Titus | Chrzanowski | N/A | 2010-12-01 |  | NSTXU-CALC-132-02-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304
80 | x | 55 | Toroidal Field Coils | WBS 132 | Cooldown of Flex | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304 | 0220
81 | x | 47 | Toroidal Field Coils | WBS 132 | OOP PF/TF Torques on TF | Wooley | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-03-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304 | 0220
83 | x | 50 | Toroidal Field Coils | WBS 132 | Loads at Knuckle Clevis | Han Zhang | Smith | 100 | 2011-03-08 | 2011-03-11 | NSTXU-CALC-132-04-00 |  |  |  |  | Smith |  | 1677 | 1.1.2 | 1201 | 0031, 0032
84 | x | 51 | Toroidal Field Coils | WBS 132 | Loads and Moments on Ring | Han Zhang | Smith | 100 | 2011-03-08 | 2011-03-11 | NSTXU-CALC-132-04-00 |  |  |  |  | Smith |  | 1677 | 1.1.2 | 1201 | 0031, 0032
85 | x | 52 | Toroidal Field Coils | WBS 132 | Outer Leg Insulation Bond Shear Stress | Han Zhang | Chrzanowski | 100 | 2011-03-01 | 2011-03-11 | NSTXU-CALC-132-04-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304 | 0210
86 | x | 53 | Toroidal Field Coils | WBS 132 | Umbrella Rinforcement | Han Zhang | Smith | 100 | 2011-03-08 | 2011-03-11 | NSTXU-CALC-132-04-00 |  |  |  |  | Smith |  | 1677 | 1.1.2 | 1205 | 0029 0037
87 | x | 69 | Center Stack | WBS 133 | Structural Analysis of the PF1 Coils, leads and Supports | L.Myatt | Chrzanowski | 100 | 2010-08-19 | 2010-12-07 | NSTXU-CALC-133-01-00 |  | Khodak |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1306 | 1020
88 | x | 56 | Toroidal Field Coils | WBS 132 | Benchmarh I^2 t Calcs | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304 | 0220
89 | x | 57 | Toroidal Field Coils | WBS 132 | TF Peak Temps at Corner | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304 | 0220
91 | x | 59 | Toroidal Field Coils | WBS 132 | Joint Electrical Contact Resistance | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304 | 0220
92 | x | 60 | Toroidal Field Coils | WBS 132 | Flex Stress for Inplane and OOP Loads | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304 | 1030
93 | x | 61 | Toroidal Field Coils | WBS 132 | DLF for Disruption | T.Willard | Chrzanowski | 100 | 2010-12-15 | 2011-01-24 | NSTXU-CALC-132-06-01 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304 | 0230
96 | x | 64 | Toroidal Field Coils | WBS 132 | TF Flag Key | A. Zolfaghari | Chrzanowski | 100 | 2011-01-05 |  | NSTXU-CALC-132-08-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1304 | 0190 & 0210
104 | x | 74 | Center Stack | WBS 133 | Halo Current Analysis of Center Stack Casing | A.Brooks | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-133-05-00 |  |  |  |  | Chrzanowski |  | 1672 | 1.1.3 | 1307 | 1050
106 | x | 42 | CentStack | WBS 133 | Modal Analysis & Normal Operation Load Effects | P.Titus |  | 0 |  | 2011-06-17 | NSTXU-CALC-133-13-00
110 | x | 86 | NBI | WBS 24 | NB Reinforcement | T. Willard | Priniski | 100 | 2011-02-25 | 2011-01-24 | NSTXU-CALC-24-01-00 |  |  | 100 | 2011-02-03 | Priniski |  | 1506 | 1.2.4 | 2480 | 0037
111 | x | 87 | NBI | WBS 24 | Thompson Scattering Port | T. Willard | Labik | 100 | 2011-01-05 | 2011-01-24 | NSTXU-CALC-24-01-00 |  |  | 100 | 2011-02-03 | Labik |  | 1627 | 1.4.5 | 4500 | 0009
113 | x | 89 | NBI | WBS 24 | Disruption Loading | L. Bryant | Priniski | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00 |  |  |  |  | Priniski |  | 1508 | 1.2.4 | 2460 | 0026
114 | x | 90 | NBI | WBS 24 | Thermal Stress Analysis(Not Req per Craig P.) | L. Bryant | Priniski | N/R | 2011-02-21 |  | NSTXU-CALC-24-02-00 |  |  |  |  | Priniski |  | 1508 | 1.2.4 | 2460 | 0026 | Not Req per Craig P.

## Sheet2
Line # | Preparation % Complete | Schedule Date (COG) | Forecast Date (Preparer) | Calc #
88 | N/R | 2011-02-21 |  | NSTXU-CALC-24-02-00
33 | N/A | N/A |  | NSTX-CALC-13-01-01
93 | N/A |  |  | NSTXU-CALC-40-02-00
10 | 100 |  |  | NSTXU-CALC-11-01-00
11 | 100 | 2010-06-01 |  | NSTXU-CALC-11-01-00
12 | 100 |  |  | NSTXU-CALC-11-01-00
13 | 100 |  |  | NSTXU-CALC-11-02-00
14 | 100 |  |  | Will be part of the above calc
18 | 100 |  |  | NSTXU-CALC-12-01-00
26 | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00
27 | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00
28 | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00
34 | 100 | N/A |  | NSTX-CALC-13-02-00
35 | 100 |  |  | NSTXU-CALC-13-03-00
36 | 100 | 2010-11-24 |  | NSTXU-CALC-13-03-01
40 | 100 |  |  | NSTXU-CALC 131-01-00
41 | 100 |  |  | NSTXU-CALC 131-02-00
44 | 100 | 2010-12-01 |  | NSTXU-CALC-132-01-00
45 | 100 | 2010-12-01 |  | NSTXU-CALC-132-02-00
46 | 100 | 2010-12-01 |  | NSTXU-CALC-132-03-00
54 | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00
55 | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00
56 | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00
57 | 100 |  |  | NSTXU-CALC-132-06-00
58 | 100 |  |  | NSTXU-CALC-132-06-00
59 | 100 |  |  | NSTXU-CALC-132-06-00
62 | 100 |  |  | NSTXU-CALC-132-08-00
66 | 100 | 2010-12-01 |  | NSTXU-CALC-132-11-00
68 | 100 | 2010-08-19 | 2010-12-07 | NSTXU-CALC-133-01-00
70 | 100 |  |  | NSTXU-CALC-133-02-00
71 | 100 | 2010-08-12 |  | NSTXU-CALC-133-03-00
72 | 100 |  |  | NSTXU-CALC-133-04-00
73 | 100 | 2010-12-01 |  | NSTXU-CALC-133-05-00
74 | 100 |  |  | NSTXU-CALC-133-06-00
76 | 100 | 2010-07-29 |  | NSTXU-CALC-133-08-00
77 | 100 | 2010-09-10 | 2011-01-15 | NSTXU-CALC-133-09-00
80 | 100 | 2010-12-01 | 2010-12-15
81 | 100 | 2010-12-01 | 2010-12-15
86 | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00
87 | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00
92 | 100 | 09/01/10 |  | NSTXU-CALC-40-01-00 | 41
8 | 50 | 2010-11-30 | 2010-11-30
7 |  | 2010-11-30 | 2010-11-30
63 | 90 | 2011-01-05 | 2011-01-05 | NSTXU-CALC-132-08-00
16 | 29 | 2011-01-10 | 2011-01-10 | NSTXU-CALC-11-04-00
61 | 75 | 2010-12-15 | 2011-01-15 | NSTXU-CALC-132-07-00
60 |  | 2010-12-15 | 2011-01-15 | NSTXU-CALC-132-06-01
90 | 90 | 2011-01-15 | 2011-01-15 | NSTXU-CALC-24-03-00
79 | 90 |  | 2011-01-15 | NSTXU-CALC-133-10-00
21 | 90 | 2011-01-17 | 2011-01-17 | NSTXU-CALC-12-03-00
2 | 60 | 2011-01-17 | 2011-01-17 | NSTXU-CALC-10-01-02
83 | 90 | 2011-01-05 | 2011-01-19 | NSTXU-CALC-24-01-00
85 | 90 | 2011-01-05 | 2011-01-19 | NSTXU-CALC-24-01-00
84 | 90 | 2011-02-25 | 2011-01-19 | NSTXU-CALC-24-01-00
15 | 80 | 2010-11-19 | 2011-01-20 | NSTXU-CALC-11-03-00
19 | 65 | 2011-01-05 | 2011-01-20 | NSTXU-CALC-12-01-01 | 15
37 | 50 | 2010-10-27 | 2011-01-28 | NSTXU-CALC-13-04-00 | 1
38 | 95 | 2010-12-15 | 2011-01-31 | NSTXU-CALC-13-05-00
42 | 95 |  | 2011-01-31 | NSTXU-CALC 131-03-00
48 | 60 | 2010-10-27 | 2011-01-31 | NSTXU-CALC-132-04-00
53 | 50 | 2010-12-01 | 2011-01-31 | NSTXU-CALC-132-05-00
47 | 95 | 2011-01-17 | 2011-01-31 | Will be part of the above calc
20 | 75 | 2011-02-01 | 2011-02-01 | NSTXU-CALC-12-02-00
22 | 75 | 2011-02-01 | 2011-02-01 | NSTXU-CALC-12-03-00
23 | 75 | 2011-02-01 | 2011-02-01 | NSTXU-CALC-12-04-00 | 8
95 | 30 | 2011-02-08 | 2011-02-08 | NSTXU-CALC-55-01-00 | 1
75 | 10 | 2010-09-10 | 2011-02-15 | NSTXU-CALC-133-07-00 | 1
30 | 75 | 2011-02-22 | 2011-02-22 | NSTXU-CALC-12-08-00
29 | 40 | 2011-02-22 | 2011-02-22 | NSTXU-CALC-12-07-00 | 2
51 | 60 | 2011-03-01 | 2011-03-01 | NSTXU-CALC-132-04-00
69 | 0 |  | 2011-03-01 | NSTXU-CALC-133-01-01 | 2
5 | 30 | 2010-12-15 | 2011-03-08 | NSTXU-CALC-10-01-02
3 | 75 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-10-01-02
64 | 75 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-09-00
49 | 60 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-04-00
50 | 60 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-04-00
52 | 60 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-04-00
31 | 50 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-12-09-00
65 | 50 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-132-10-00
6 | 10 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-10-01-02
4 | 5 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-10-01-02 | 10
24 | 75 | 2011-03-22 | 2011-03-22 | NSTXU-CALC-12-05-00
25 | 75 | 3/9-3/22 | 2011-03-22 | NSTXU-CALC-12-05-00 | 2
89 | 60 | 2010-11-24 | 2011-03-30 | Initial calc complete and will be filed, 3D calc to be performed. Needs Calc # | 2
78 |  | 2011-08-15 | 2011-08-15 |  | 44
| 6359 |  |  |  | 44
[5 empty] | 85 | 74.8118

## Sheet3
Line # | WBS Name | WBS | Calc Title | Preparer | COG | Preparation % Complete | Schedule Date (COG) | Forecast Date (Preparer) | Calc # | Preparer Sign date | Reviewer | Review % Complete | Reviewer Sign date | WBS | Job # (WAF) | Act ID | Comments
95 | General Power Systems | WBS 55 | Bus Bar Analysis | A. Khodak | Smith | 30 | 2011-02-08 |  | NSTXU-CALC-55-01-00 |  | H.Zhang? |  |  | 1.5.5 | 5501 | 0049-0076
63 | Toroidal Field Coils | WBS 132 | TF Flag Key | A. Zolfaghari | Chrzanowski | 90 | 2011-01-05 |  | NSTXU-CALC-132-08-00 |  | T.Willard |  |  | 1.1.3 | 1304 | 0190 & 0210
16 | Plasma Facing Components | WBS 11 | Fastener Analysis | A.Brooks | Tresemer | 29 | 2011-01-10 |  | NSTXU-CALC-11-04-00 |  |  |  |  | 1.1.1 | 1001 | 0041
15 | Plasma Facing Components | WBS 11 | Final Tile Stress Analysis (ATJ Tiles) | A.Brooks | Tresemer | 80 | 2011-01-20 | 2011-01-20 | NSTXU-CALC-11-03-00 |  |  |  |  | 1.1.1 | 1001 | 0040
90 | NBI | WBS 24 | HHFW Antenna (needs to be modified for upgrade loads) | Han Zhang | Bob Ellis | 90 | 2011-01-15 |  | NSTXU-CALC-24-03-00 |  | R.Hatcher |  |  | 1.2.4
53 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Analysis | Han Zhang | Chrzanowski | 50 | 2011-01-31 | 2011-01-31 | NSTXU-CALC-132-05-00 |  |  |  |  | 1.1.3 | 1304 | 0220
48 | Toroidal Field Coils | WBS 132 | Analysis of TF Outer Leg | Han Zhang | Smith | 60 | 2011-01-31 | 2011-01-31 | NSTXU-CALC-132-04-00 |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
29 | Vacuum Vessel | WBS 12 | Umbrella Reinforcement Details | Han Zhang | Smith | 40 | 2011-02-22 |  | NSTXU-CALC-12-07-00 |  | P.Titus / H.Zhang |  |  | 1.1.2 | 1205 | 0029 0090
51 | Toroidal Field Coils | WBS 132 | Outer Leg Insulation Bond Shear Stress | Han Zhang | Chrzanowski | 60 | 2011-03-01 |  | NSTXU-CALC-132-04-00 |  |  |  |  | 1.1.3 | 1304 | 0210
49 | Toroidal Field Coils | WBS 132 | Loads at Knuckle Clevis | Han Zhang | Smith | 60 | 2011-03-08 |  | NSTXU-CALC-132-04-00 |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
50 | Toroidal Field Coils | WBS 132 | Loads and Moments on Ring | Han Zhang | Smith | 60 | 2011-03-08 |  | NSTXU-CALC-132-04-00 |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
52 | Toroidal Field Coils | WBS 132 | Umbrella Rinforcement | Han Zhang | Smith | 60 | 2011-03-08 |  | NSTXU-CALC-132-04-00 |  |  |  |  | 1.1.2 | 1205 | 0029 0037
21 | Vacuum Vessel | WBS 12 | OPERA 2D Disruption Analyses (Just needs writeup) | Hatcher | Titus | 90 | 2011-01-17 |  | NSTXU-CALC-12-03-00 |  | A.Brooks |  |  | 1.1.1 | 1002 | 0014
89 | NBI | WBS 24 | Magnetic Shielding Calculation | L. Bryant | Priniski | 60 | 2011-03-30 | 2011-03-30 | Initial calc complete and will be filed, 3D calc to be performed. Needs Calc # |  | A. Brooks |  |  | 1.2.4 | 2485 | 0016A
69 | Center Stack | WBS 133 | Structural Analysis of the PF1 Coils, leads and Supports, Rev 1 | L.Myatt | Chrzanowski | 0 | 2011-03-01 | 2011-03-01 | NSTXU-CALC-133-01-01
75 | Center Stack | WBS 133 | OH Coax Lead Analysis | M. Mardenfeld | Chrzanowski | 10 | 2011-02-15 | 2011-02-15 | NSTXU-CALC-133-07-00 |  |  |  |  | 1.1.3 | 1305 | 120
61 | Toroidal Field Coils | WBS 132 | Maximum Torsional Shear Stress | P. Titus | Chrzanowski | 75 | 2011-01-15 | 2011-01-15 | NSTXU-CALC-132-07-00 |  |  |  |  | 1.1.3 | 1304 | 0230
22 | Vacuum Vessel | WBS 12 | PF2 Bolting and Bracket Stress | P. Titus | Smith | 75 | 2011-02-01 |  | NSTXU-CALC-12-03-00 |  | M.Smith |  |  | 1.1.2 | 1202 | 0032
23 | Vacuum Vessel | WBS 12 | PF3 Bolting, Bracket, and weld Stress | P. Titus | Smith | 75 | 2011-02-01 |  | NSTXU-CALC-12-04-00 |  | M.Smith |  |  | 1.1.2 | 1203 | 0032
4 | Torus Systems | WBS 10 | Leg and Brace Hiltis | P. Titus | Smith | 5 | 2011-03-08 |  | NSTXU-CALC-10-01-02 |  | M.Smith |  |  | 1.1.2 | 1207 | 0032
6 | Torus Systems | WBS 10 | Pedestal Loads | P. Titus | Smith | 10 | 2011-03-08 |  | NSTXU-CALC-10-01-02 |  | M.Smith |  |  | 1.1.2 | 1206 | 0029 0032
3 | Torus Systems | WBS 10 | Torques to Lids and TF Teeth | P. Titus | Smith | 75 | 2011-03-08 |  | NSTXU-CALC-10-01-02 |  | A.Zolfaghari |  |  | 1.1.2 | 1201 | 0031
64 | Toroidal Field Coils | WBS 132 | Analysis of Knuckle Clevis | P. Titus | Smith | 75 | 2011-03-08 |  | NSTXU-CALC-132-09-00 |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
24 | Vacuum Vessel | WBS 12 | PF4 and 5 Support Analysis | P. Titus | Smith | 75 | 2011-03-22 |  | NSTXU-CALC-12-05-00 |  | M.Smith |  |  | 1.1.2 | 1208 | 0029-0032
25 | Vacuum Vessel | WBS 12 | PF4 and 5 Lead Support Analysis | P. Titus | Smith | 75 | 3/9-3/22 |  | NSTXU-CALC-12-05-00 |  | M.Smith |  |  | 1.1.2 | 1204 | 0032
2 | Torus Systems | WBS 10 | Global Model | P.Titus | Titus | 60 | 2011-01-17 |  | NSTXU-CALC-10-01-02 |  | Group |  |  | 1.1.1 | 1000 | 0011 | Replaces Calc-13-01-01
19 | Vacuum Vessel | WBS 12 | Update of Analysis of Vacuum Vessel & Passive Plates | P.Titus | Titus | 65 | 2011-01-20 | 2011-01-20 | NSTXU-CALC-12-01-01 |  |  |  |  | 1.1.1 | 1002 | 0019
20 | Vacuum Vessel | WBS 12 | Dome/PF Rib Stresses | P.Titus | Smith | 75 | 2011-02-01 |  | NSTXU-CALC-12-02-00 |  | M.Smith |  |  | 1.1.2 | 1220 | 0016
5 | Torus Systems | WBS 10 | Full Load Inventory | P.Titus | Titus | 30 | 2011-03-08 | 2011-03-08 | NSTXU-CALC-10-01-02 |  |  |  |  | 1.1.1 | 1000 | 0016 | Per M Smith email
30 | Vacuum Vessel | WBS 12 | Lid/Spoke Assembly, Upper and Lower | P.Titus/Smith | Smith | 75 | 2011-02-22 |  | NSTXU-CALC-12-08-00 |  |  |  |  | 1.1.2 | 1205 | 31 & 89
31 | Vacuum Vessel | WBS 12 | Pedestal Analysis | P.Titus/Smith | Smith | 50 | 2011-03-08 |  | NSTXU-CALC-12-09-00 |  |  |  |  | 1.1.2 | 1206 | 0029 0032
79 | Center Stack | WBS 133 | Center Stack Casing Bellows | Peter Rogoff | Chrzanowski | 90 | 2011-01-15 | 2011-01-15 | NSTXU-CALC-133-10-00 |  |  |  |  | 1.1.3 | 1307 | 1050
65 | Toroidal Field Coils | WBS 132 | Ring Bolted Joint | Peter Rogoff | Smith | 50 | 2011-03-08 |  | NSTXU-CALC-132-10-00 |  |  |  |  | 1.1.2 | 1201 | 0031, 0032
83 | NBI | WBS 24 | Vessel Port Re-Work for NB and Thompson Scattering Port | T. Willard | Priniski / Labik | 90 | 2011-01-19 | 2011-01-19 | NSTXU-CALC-24-01-00 |  | A.Zolfaghari |  |  | 1.2.4 | 2480 | 0035
84 | NBI | WBS 24 | NB Reinforcement | T. Willard | Priniski | 90 | 2011-01-19 | 2011-01-19 | NSTXU-CALC-24-01-00 |  |  |  |  | 1.2.4 | 2480 | 0037
85 | NBI | WBS 24 | Thompson Scattering Port | T. Willard | Labik | 90 | 2011-01-19 | 2011-01-19 | NSTXU-CALC-24-01-00 |  |  |  |  | 1.4.5 | 4500 | 0009
60 | Toroidal Field Coils | WBS 132 | DLF for Disruption | T.Willard | Chrzanowski | 0 | 2011-01-15 | 2011-01-15 | NSTXU-CALC-132-06-01 |  |  |  |  | 1.1.3 | 1304 | 0230
37 | Magnet Systems | WBS 13 | DCPS TF Inner Leg Torsional Shear Stress | Wooley/Titus | R.Hatcher | 50 | 2011-01-28 | 2011-01-28 | NSTXU-CALC-13-04-00 |  |  |  |  | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
38 | Magnet Systems | WBS 13 | DCPS Moment Influence Coefficients | Wooley/Titus | R.Hatcher | 95 | 2011-01-30 | 2011-01-30 | NSTXU-CALC-13-05-00 |  |  |  |  | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
42 | Polodal Field Coils | WBS 131 | Poloidal Magnetic Quantites for the May 2010 Design Point | Woolley | Chrzanowski | 95 | 2011-01-30 | 2011-01-30 | NSTXU-CALC 131-03-00
40 | Polodal Field Coils | WBS 131 | Analysis of CSU Poloidal Field Coils | Woolley | Chrzanowski | 100 |  |  | NSTXU-CALC 131-01-00 |  |  |  |  | 1.1.3 | 1306 | 1020
41 | Polodal Field Coils | WBS 131 | Poloidal Magnetic Quantites for the Feb 2010 Provisional Design | Woolley | Chrzanowski | 100 |  |  | NSTXU-CALC 131-02-00 |  |  |  |  | 1.1.3 | 1306 | 1020
10 | Plasma Facing Components | WBS 11 | Heat Balance | A.Brooks | Chrzanowski | 100 |  |  | NSTXU-CALC-11-01-00 |  | H.Zhang |  |  | 1.1.1 | 1307 | 0011
11 | Plasma Facing Components | WBS 11 | Sizing of Coolant Capabilities | A.Brooks | Chrzanowski | 100 | 2010-06-01 |  | NSTXU-CALC-11-01-00 |  |  |  |  | 1.3.2 | 3200 | 0023
12 | Plasma Facing Components | WBS 11 | Divertor Tile Thermal Stress (CFC Tiles) | A.Brooks | Tresemer | 100 |  |  | NSTXU-CALC-11-01-00 |  |  |  |  | 1.1.1 | 1001
13 | Plasma Facing Components | WBS 11 | General Tile Program | J. Boales | Tresemer | 100 |  |  | NSTXU-CALC-11-02-00 | 2010-10-01 | A. Brooks | A. Brooks |  | 1.1.1 | 1001 | 0040
18 | Vacuum Vessel | WBS 12 | Disruption Analysis of Vacuum Vessel and Passive Plates | S.Avasarala | Titus | 100 |  |  | NSTXU-CALC-12-01-00 |  |  |  |  | 1.1.1 | 1002 | 0016
26 | Vacuum Vessel | WBS 12 | Alunimum Block | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 |  | M.Smith | 10 |  | 1.1.2 | 1205 | 0029 0037 | Per M Smith email
27 | Vacuum Vessel | WBS 12 | TFO Leg | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 |  | M.Smith | 10 |  | 1.1.2 | 1205 | 0029, 0037 | Moments Loads
28 | Vacuum Vessel | WBS 12 | Bolt details | P.Titus | Smith | 100 | 2010-11-30 | 2010-12-15 | NSTXU-CALC-12-06-00 |  | M.Smith | 10 |  | 1.1.2 | 1205 | 0029, 0037 | Moments Loads
35 | Magnet Systems | WBS 13 | NSTX Influence Matrix | Hatcher | Titus | 100 |  |  | NSTXU-CALC-13-03-00 |  |  |  |  | 1.1.3 | 1300 | 0010
36 | Magnet Systems | WBS 13 | DCPS Force Influence Coefficients | R.Hatcher | R.Hatcher | 100 | 2010-11-24 |  | NSTXU-CALC-13-03-01 |  |  |  |  | 1.5.2 | 5200 | R.Hatcher | I would suggest DCPS should be in WBS 13, not WBS 15
46 | Toroidal Field Coils | WBS 132 | OOP PF/TF Torques on TF | Wooley | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-03-00 |  |  |  |  | 1.1.3 | 1304 | 0220
54 | Toroidal Field Coils | WBS 132 | Cooldown of Flex | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | 1.1.3 | 1304 | 0220
55 | Toroidal Field Coils | WBS 132 | Benchmarh I^2 t Calcs | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | 1.1.3 | 1304 | 0220
56 | Toroidal Field Coils | WBS 132 | TF Peak Temps at Corner | Han Zhang | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-05-00 |  |  |  |  | 1.1.3 | 1304 | 0220
57 | Toroidal Field Coils | WBS 132 | TF Flex Joint and Bundle Stub | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  | A.Zolfaghari? |  |  | 1.1.3 | 1304 | 0230
58 | Toroidal Field Coils | WBS 132 | Joint Electrical Contact Resistance | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  |  |  |  | 1.1.3 | 1304 | 0220
59 | Toroidal Field Coils | WBS 132 | Flex Stress for Inplane and OOP Loads | T.Willard | Chrzanowski | 100 |  |  | NSTXU-CALC-132-06-00 |  |  |  |  | 1.1.3 | 1304 | 1030
62 | Toroidal Field Coils | WBS 132 | Determination of shear Forces Between the TF conductors and Insulation and the G-10 Insulating Crown. | A. Zolfaghari | Chrzanowski | 100 |  |  | NSTXU-CALC-132-08-00 |  |  |  |  | 1.1.3 | 1304 | 0230
66 | Toroidal Field Coils | WBS 132 | TF Cooldown using FCOOL | A. Zolfaghari | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-11-00 |  | M.Kalish? |  |  | 1.1.3 | 1304 | 0230
68 | Center Stack | WBS 133 | Structural Analysis of the PF1 Coils, leads and Supports | L.Myatt | Chrzanowski | 100 | 2010-08-19 | 2010-12-07 | NSTXU-CALC-133-01-00 |  | A.Khodak? |  |  | 1.1.3 | 1306 | 1020
70 | Center Stack | WBS 133 | Thermal Stresses on OH-TF Coils | S.Avasarala | Chrzanowski | 100 |  |  | NSTXU-CALC-133-02-00 |  |  |  |  | 1.1.3 | 1307 | 1050
71 | Center Stack | WBS 133 | Center Stack Casing Disruption Inductive and Halo Current Loads | P.Titus | Chrzanowski | 100 | 2010-08-12 |  | NSTXU-CALC-133-03-00 | 2010-04-13 | P.Titus |  |  | 1.1.3 | 1307 | 1030
72 | Center Stack | WBS 133 | OH Preload System and Belleville Spring Design | Peter Rogoff | Chrzanowski | 100 |  |  | NSTXU-CALC-133-04-00 |  | T.Kozub/Test |  |  | 1.1.3 | 1302
73 | Center Stack | WBS 133 | Halo Current Analysis of Center Stack Casing | A.Brooks | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-133-05-00 |  |  |  |  | 1.1.3 | 1307 | 1050
74 | Center Stack | WBS 133 | OH Coolant Hole Optimization | A. Zolfaghari | Chrzanowski | 100 |  |  | NSTXU-CALC-133-06-00 |  | M.Mardenfeld |  |  | 1.1.3 | 1305 | 100
76 | Center Stack | WBS 133 | OH Stress Analyses | A. Zolfaghari | Chrzanowski | 100 | 2010-07-29 |  | NSTXU-CALC-133-08-00 |  |  |  |  | 1.1.3 | 1305 | 100
77 | Center Stack | WBS 133 | OH Fatigue and Fracture Mechanics | P. Titus | Chrzanowski | 100 | 2010-09-10 | 2011-01-15 | NSTXU-CALC-133-09-00 |  | I. Zatz |  |  | 1.1.3 | 1302 | 140
86 | NBI | WBS 24 | Armor Plate Backing Plate | L. Bryant | Priniski | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00 |  |  |  |  | 1.2.4 | 2460 | 0026
87 | NBI | WBS 24 | Disruption Loading | L. Bryant | Priniski | 100 | 2011-02-21 |  | NSTXU-CALC-24-02-00 |  |  |  |  | 1.2.4 | 2460 | 0026
92 | Diagnostics | WBS 41 | Diagnostics Review and Database | J. Boales | Titus | 100 | 09/01/10 |  | NSTXU-CALC-40-01-00 |  | Bob Kiata to assign? |  |  | 1.2.3 | 2300 | 0015
[6 empty] | 5614 | 77.9722 |  | 72
93 | Diagnostics | WBS 41 | Thomson Scattering Port | Labik | Kaita | 0 |  |  | NSTXU-CALC-40-02-00 |  |  |  |  | 1.4.0 | 4500 |  | Covered under Vessel Port Re-Work for NB and Thompson Scattering Port #23
88 | NBI | WBS 24 | Thermal Stress Analysis(Not Req per Craig P.) | L. Bryant | Priniski | N/R | 2011-02-21 |  | NSTXU-CALC-24-02-00 |  | I. Zatz |  |  | 1.2.4 | 2460 | 0026 | Not Req per Craig P.
14 | Plasma Facing Components | WBS 11 | Inner CS Casing Tile Stress | J. Boales | Tresemer | 100 |  |  | Will be part of the above calc | 2010-10-01 | A. Brooks |  |  | 1.1.1 | 1001
47 | Toroidal Field Coils | WBS 132 | Torque Egns for Design Point | Wooley | Titus | 95 | 2011-01-17 | 2011-01-31 | Will be part of the above calc |  |  |  |  | 1.1.0 | 1000 | 0011
1 | Torus Systems | WBS 10
7 | Torus Systems | WBS 10 | VV Leg | P.Titus | Smith |  | 2010-11-30 | [6 empty] | 1.1.2 | 1207 | 0032 | Per M Smith email
8 | Torus Systems | WBS 10 | VV Interface Welds | P.Titus | Smith | 50 | 2010-11-30 | [6 empty] | 1.1.2 | 1207 | 0032
9 | Plasma Facing Components | WBS 11
17 | Vacuum Vessel | WBS 12
32 | Magnet Systems | WBS 13
39 | Polodal Field Coils | WBS 131
43 | Toroidal Field Coils | WBS 132
67 | Center Stack | WBS 133
78 | CentStack | WBS 133 | Centerstack Fixtures |  | Chrzanowski |  | 2011-08-15 | [6 empty] | 1.1.4 | 1302 | 140
80 | Center Stack | WBS 133 | CS Casing Halo Ind and Res Cur | A.Brooks | Chrzanowski | 100 | 2010-12-01 | 2010-12-15 | [5 empty] | 1.1.3 | 1307 | 1050
81 | Center Stack | WBS 133 | CS Casing Static and Dynamic | A.Brooks | Chrzanowski | 100 | 2010-12-01 | 2010-12-15 | [5 empty] | 1.1.3 | 1307 | 1050
82 | NBI | WBS 24
91 | Diagnostics | WBS 41
94 | General Power Systems | WBS 55
33 | Magnet Systems | WBS 13 | Global Model | P. Titus | Titus |  | N/A |  | NSTX-CALC-13-01-01
34 | Magnet Systems | WBS 13 | Maximum and Minimum Loads on the NSTX OH and PF Coils, and Coil Groupings | P.Titus | Titus | 100 | N/A |  | NSTX-CALC-13-02-00
44 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Diffusion Analysis(to be superceded by #48) | P.Titus | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-01-00 |  |  |  |  | 1.1.3 | 1304
45 | Toroidal Field Coils | WBS 132 | Coupled EM-Thermal Analysis (to be superceded by #48) | P.Titus | Chrzanowski | 100 | 2010-12-01 |  | NSTXU-CALC-132-02-00 |  |  |  |  | 1.1.3 | 1304