NSTX Upgrade Project

IPT Meeting Minutes

The minutes from the NSTX Upgrade Project IPT meeting of Wednesday, September 2, 2009 at 10:00am are as follows:

Attendees: 	DOE-PSO:	J. Makiel

DOE HQ: 	B. Sullivan

PPPL:   	E. Perry, M. Ono, R. Templon, T. Egebo, T. Stevenson, R. Strykowsky, L. Dudek, J. Levine, M. Williams, J. Menard

1. DOE News (Barry)

a)	The FY10 budget for the NSTX Upgrade Project will be ~$5,505K.  However, the Project has identified an optimum budget of ~$9,000K.  It is unclear how much the project budget can be augmented internally by PPPL.

[Action:  As per Barry’s recommendation, Masa & Jon will call Steve Eckstrand to discuss options within the FY10 NSTX Program, such as reduced experimental run week scenarios, as to help support the funding shortfall for the NSTX Upgrade Project in FY10];

b)	An SC Readiness Review for CD-1 has been set for Dec 15th & 16th at PPPL.  A draft charge letter has been prepared for OFES-AD signature.  At this time, it is uncertain whether the review will be one or two days.  Jeff gave a brief outline of how these reviews are typically performed.  Barry also recommended that Kin join our IPT meeting as a guest in the near future to help assist in the preparations.  [Action:  Jeff will ask for Kin’s assistance in early November].

2. Safety Management (Jerry)

a)	There were no NSTX Upgrade Project related safety incidents;

b)	At the last IPT meeting, it was reported that PPPL was having difficulty in procuring a health physics (HP) technician to support Lab-wide HP oversight activities.  However, PPPL was able to obtain an HP technician who previously worked at PPPL.

3. Project technical progress (Larry and Tim)

Centerstack Upgrade (Larry)

a)	Design and analysis activities continue and are proceeding well;

b)	A successful peer review of the Centerstack Upgrade design was accomplished.  About 40 chits were generated but did not reveal any major new concerns.  During the review it was pointed out that a more robust design of the PF coil support may be warranted.

c)	The project is now in the midst of preparing Work Authorization Forms (WAFs) to capture the work scope and cost/schedule range.  The WAFs will undergo an internal independent review and then be provided to the project office so a resource loaded schedule can be developed.  The WAFs are on schedule to be completed by mid-September.  A tracking list, prepared by the Project Office, will track the WAF progress.

Second Neutral Beam (Tim)

a)	The second neutral beam continues to undergo inspection and decontamination investigation.  The cryogenic panels have been inspected and appear to be in good condition as well as other components.  The main ion dump shows wear, but this was expected.  Overall, things are going well.

b)	All Work Authorization Forms (WAFs) have been prepared and submitted to the Project Office.  As discussed above for the Centerstack Upgrade, an internal independent review will be performed followed by the development of a resource loaded schedule.

4.	Management (Erik)

a)	The development of the cost and schedule range is going well and will support the internal CDR scheduled for October 28-29.

b)  The CD-1 Requirements List continues to be worked.  See paragraph (8) below for update on the List’s status.

5.  Procurement (Rod)

a)  Procurement has no actions at this time but is aware that requisitions for long lead items will require procurement support in FY10 upon CD-1 approval.

6.  Risk Management (Erik)

a)	The risk registry continues to mature.

b)	There are no new significant risk items identified since the last IPT meeting.  This includes the results from both peer reviews.

7. 	Project performance (Ron)

a)	The Project has spent ~$5M to date (end of August).  Expected carryover is ~$500K;

b)	A concern was expressed about a potential delay of receiving CD-1 approval as the project continues to move forward into preliminary design.  [Action:  Jeff will draft an email to OFES (Barry) that will document this concern and propose that PPPL continue with advanced conceptual design pending CD-1 approval];

c)	As previously discussed, the current anticipated budget for the NSTX Upgrade Project in FY10 cannot sustain the current burn rate of labor to support CD-2.  PPPL is looking within to identify offsets as discussed in paragraph 1(b) above.

8. 	6 Month look Ahead (Erik/Ron)

a)	Ron provided a brief overview of upcoming deliverables as follows:

- Ron is working on the cost & schedule task;

- Erik is working on the Acquisition Strategy and risk registry;

- Masa is working on the Alternative Analysis and Cost Range document;

- A draft preliminary PEP prepared by Erik is being circulated for comment [Action: Jeff will ask Kin what the signature authority is for a ‘prelim’ PEP vs. final PEP].

b)	At this time, Erik does not foresee any major technical issues and continues to believe that the project will be ready for CD-1 review in December.

9.	Planned IPT meetings (and other events) are as follows:

Sep 23	Next IPT Meeting at 10:00am

Oct 28-29	PPPL Conceptual Design Review

Dec 15-16	Lehman Review

Dec/Jan	CD-1 approval